**TRANSPORTATION POOLED FUND PROGRAM**

**QUARTERLY PROGRESS REPORT**

Lead Agency (FHWA or State DOT): \_\_\_**FHWA**\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**INSTRUCTIONS:**

*Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active. Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any. List all tasks, even if no work was done during this period.*

|  |  |
| --- | --- |
| **Transportation Pooled Fund Program Project #**TPF-5(475) | **Transportation Pooled Fund Program - Report Period:**X Quarter 1 (January 1 – March 31) □ Quarter 2 (April 1 – June 30) □ Quarter 3 (July 1 – September 30)□ Quarter 4 (October 1 – December 31) |
| **Project Title:**Update Precipitation Frequency Estimates for Delaware, Maryland, North Carolina, Virginia, Pennsylvania, and South Carolina (NOAA Atlas 14, Vol. 13) |
| **Name of Project Manager(s):**Megan Frye | **Phone Number:**(303) 396-9847 | **E-Mail**megan.frye@dot.gov |
| **Lead Agency Project ID:**FHWA | **Other Project ID (i.e., contract #):** | **Project Start Date:**March 19, 2021 |
| **Original Project End Date:**June 2024 | **Current Project End Date:**December 2025 | **Number of Extensions:** |

Project schedule status:

□ On schedule □ On revised schedule □ Ahead of schedule X Behind schedule

Overall Project Statistics:

|  |  |  |
| --- | --- | --- |
| **Total Project Budget** | **Total Cost to Date for Project** |  **Percentage of Work**  **Completed to Date** |
| $1,802,000 | $350,000 | 10% |

***Quarterly*** Project Statistics:

|  |  |  |
| --- | --- | --- |
|  **Total Project Expenses**  **and Percentage This Quarter** |  **Total Amount of Funds**  **Expended This Quarter** |  **Total Percentage of**  **Time Used to Date** |
| $0 / 0% | $0 | 30% |

|  |
| --- |
| **Project Description**:The purpose of this project is to update precipitation frequency estimates for Delaware, Maryland, North Carolina, Virginia, Pennsylvania, and South Carolina published in NOAA Atlas 14 Volume 2. Like previous NOAA Atlas 14 volumes, the estimates and associated bounds of 90% confidence intervals will be provided at 30 arc-sec resolution for durations of 5-minute through 60-day at average recurrence intervals (ARIs) of 1-year through 1,000-year. The study results will be published as NOAA Atlas 14 Volume 13, a wholly web-based publication available at Precipitation Frequency Data Server (PFDS). The publication will include the artifacts provided in previous NOAA Atlas 14 Volumes, including access through the PFDS, base grids in standard formats together with error estimates, electronic copies of maps, charts of seasonal distributions and probabilistic temporal distributions of heavy precipitation, and detailed documentation. Updated areal reduction factors, which are needed to calculate analogous areal precipitation frequency estimates, will not be developed as a part of this project. |

|  |
| --- |
| **Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.):**NOAA continued searching and compiling a list of the precipitation networks that will be considered for the development of the Atlas 14 Volume 13 estimates and formatting the NCEI datasets for this project area. The status of the collection of various data sources is available in Table 2 of the Hydrometeorological Design Studies Center Progress Report for January to 31 March 2023.This work falls under Task 1 in the Scope of Work for the project.Additional information on the status of the Atlas 14, Volume 13 work is available at: https://www.weather.gov/owp/hdsc\_current\_projects |
| **Anticipated work next quarter**:Continued work under Task 1. NOAA will continue with data collection, reformatting, and station metadata checks for NCEI stations. All collected data will be examined and formatted into a common format, where appropriate. Data collection, formatting, and initial quality control is anticipated to be complete by end of Q2 2023. |

|  |
| --- |
| **Significant Results:**Completion of Task 1 will result in a database of observations and extracted AMS data for durations from 15- min to 60-day, as available. Those data will be used in subsequent analyses. Observations found lacking in quality in subsequent analyses will be excluded from the database for that time, and any time series such data contributes to will be re-extracted. Non-NCEI data digitized as part of this activity will be shared with the NCEI for inclusion in the NOAA archive for broader public access. This task will result in a database of observations and extracted AMS data for durations from 15- min to 60-day, as available. Those data will be used in subsequent analyses. |
| **Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that** **might affect the completion of the project within the time, scope and fiscal constraints set forth in the** **agreement, along with recommended solutions to those problems).**Delay in finalizing the IAA with NOAA. Estimated timeline to complete the work is late 2025 now. |

|  |
| --- |
| **Potential Implementation:** All deliverables will be accessible through the Precipitation Frequency Data Server (PFDS). That includes:* Interactive map of the United States. Via this map, IDF/DDF tables and curves will be available for any location in the project area.
* Precipitation frequency grids in GIS compatible formats.
* Metadata in Federal Geographic Data Transfer Standard format.
* Cartographic maps of precipitation frequency estimates.
* Charts of the seasonal distribution of annual maxima
* Probabilistic temporal distributions for 6-hour, 12-hour, 24-hour, and 96-hour durations in both chart and digital form
* Rainfall frequency estimates with corresponding upper and lower bounds of 90% confidence intervals will be available at 30-arc sec grid for durations of 1, 2, 3, 6, 12 and 24 hours.
 |