TRANSPORTATION POOLED FUND PROGRAM

QUARTERLY PROGRESS REPORT

Lead Agency (FHWA or State DOT):  __FHWA___________________________________________

INSTRUCTIONS:

Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active.  Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any.  List all tasks, even if no work was done during this period.

| Transportation Pooled Fund Program Project # (i.e, SPR-2(XXX), SPR-3(XXX) or TPF-5(XXX) TPF-5(150) | Transportation Pooled Fund Program - Report Period: □ Quarter 1 (January 1 – March 31) □ Quarter 2 (April 1 – June 30) □ Quarter 3 (July 1 – September 30) ( Quarter 4 (October 4 – December 31) |
| --- | --- |
| Project Title: Extending the Season for Concrete Construction and Repair, Phase III – Guidance for Optimizing Admixture Dosage Rate |
| Project Manager: Phone: E-mail: Fred Faridazar (202-493-3076) Fred.Faridazar@dot.gov |
| Project Investigator: Phone: E-mail: Lynette Barna (603-646-4503) Lynette.A.Barna@usace.army.mil |
| Lead Agency Project ID: | Other Project ID (i.e., contract #): IAA DTFH61-08-X-30031 | Project Start Date: IAA Effective Date Aug. 7, 2008 |
| Original Project End Date: Period of Performance 45 months from effective date ( 7 May 2012) | Current Project End Date: 01 JUNE 2013 | Number of Extensions: zero |

Project schedule status:

□ On schedule	□ On revised schedule		□ Ahead of schedule		□ Behind schedule

Overall Project Statistics:

| Total Project Budget | Total Cost to Date for Project | Total Percentage of Work Completed |
| --- | --- | --- |
| $325,000 proposed project cost $325,000 received to date | $221,500 | 68% (based on project proposal) |

Quarterly Project Statistics:

| Total Project Expenses This Quarter | Total Amount of Funds Expended This Quarter | Percentage of Work Completed This Quarter |
| --- | --- | --- |
| $7,500 | $7,500 | 21% |

Project Description:

The purpose of the Phase III study is to develop tools and guidance to specify dosage levels of chemical admixtures used in antifreeze concrete to correspond with the varying weather conditions experienced at any job location. A user guide, including a series of design tables, will be developed describing admixture dosages to be adjusted for a specific level of protection. The guide will set dosage rates for general sets of conditions to provide a conservative level of concrete protection during the curing period. The dosage rates will account for the environmental conditions and concrete geometry. The guide will allow technicians to tailor mixture proportions and protective measures based on weather predictions for the first few days following concrete placement.

This quarterly progress report provides a summary of the effort expended and fulfills the reporting requirement in support of Interagency Agreement (IAA) DTFH61-08-X-30031, Modification 1 (signed 6 January 2009) between FHWA and the U.S. Army Engineer Research and Development Center, Cold Regions Research and Engineering Laboratory (ERDC-CRREL), entitled Extending the Season for Concrete Construction and Repair, Phase III – Guidance for Optimizing Admixture Dosage Rates.

Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.):

Contract. Efforts continued this quarter to secure a contract with Dr. Korhonen to continue assessing the datasets used in developing the design guidance;

Draft final report. Preparation of the final report continued.

Figure 2. Cumulative project expenditures updated for 1st Quarter Fiscal Year 2013 shown by quarter beginning January 2009 when initial funding for Part 1 was confirmed.

An estimated project timeline for Part 2 of the project is given in the table below.

Table 1. Part 2 – Develop design guidance project tasks identified and estimated percent completion for 1st Quarter Fiscal Year 2013.

Anticipated work next quarter:

Work will continue in the following areas during the next quarter:

Contract. Completion of establishing a contract with Dr. Charles Korhonen. This will continue the task of assessing the datasets used in developing the design guidance. It is anticipated the process to complete this contract will be completed in a timely manner so as not to adversely impact project progress;

Draft final report. Preparation of the final report will continue.

Significant Results:

A mathematical model, based on heat transfer principles, has been developed describing the interaction of a 6-in thick concrete slab placed on grade. Currently, the model neglects the effects of solar radiation and evaporation, and does not include insulation. For the case of the slab on grade, the material layers and thicknesses are defined, including the substrate. Daily maximum and minimum air temperatures, and the time of occurrence were used as input parameters. Measured air temperatures may be used as input, or maximum and minimum predicted daily temperatures may be used. With the daily maximum and minimum temperatures, hourly temperatures are generated using a sinusoidal function.

The heat of hydration of the cement in the mixture is input to determine the amount of heat generated as the concrete cures. The estimated internal concrete temperatures as the concrete cures are output on an hourly basis in tabular form. During this quarter, heat of hydration curves were generated from our dataset and then used in the one-dimensional thermal concrete model. The heat of hydration curve for each slab were different, showing the effects of varying the admixture dosage.

The thermal modeling tool enables predicting internal concrete temperatures as it cures to compare with measured temperatures collected from field cured antifreeze concrete. The output showed good agreement with the measured concrete temperatures. The model will be a valuable tool to evaluate differing admixture dosages for antifreeze concrete formulations. This is a significant step in further building our understanding to predict the strength gain of antifreeze concrete subjected to freezing or sub-freezing temperatures.

The report for Part 1 of the project is available at: http://www.crrel.usace.army.mil/innovations/cold_weather_concreting/antifreeze_admixtures/extending_the_season.html

Circumstance affecting project or budget (Describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope, and fiscal constraints set forth in the agreement, along with recommended solutions to those problems).

Nothing to report at this time.

# Footnotes

Effective 21 December 2011, project end date changed as per scope of work approved 7 August 2008.

Phase III Extending the Season for Concrete Construction and Repair, Guidance for Optimizing Admixture Dosage Rates, Project Proposal, USAERDC-CRREL, submitted 2004.