TRANSPORTATION POOLED FUND PROGRAM

QUARTERLY PROGRESS REPORT

Lead Agency (FHWA or State DOT):  __FHWA___________________________________________

INSTRUCTIONS:

Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active.  Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any.  List all tasks, even if no work was done during this period.

| Transportation Pooled Fund Program Project # (i.e, SPR-2(XXX), SPR-3(XXX) or TPF-5(XXX) TPF-5(150) | Transportation Pooled Fund Program - Report Period: □Quarter 1 (January 1 – March 31) □Quarter 2 (April 1 – June 30) □Quarter 3 (July 1 – September 30) □Quarter 4 (October 4 – December 31) |
| --- | --- |
| Project Title: Extending the Season for Concrete Construction and Repair, Phase III – Guidance for Optimizing Admixture Dosage Rate |
| Project Manager: Phone: E-mail: Fred Faridazar (202-493-3076) Fred.Faridazar@dot.gov |
| Project Investigator: Phone: E-mail: Lynette Barna (603-646-4503) Lynette.A.Barna@usace.army.mil |
| Lead Agency Project ID: | Other Project ID (i.e., contract #): IAA DTFH61-08-X-30031 | Project Start Date: IAA Effective Date Aug. 7, 2008 |
| Original Project End Date: Period of Performance 45 months from effective date ( 7 May 2012) | Current Project End Date: 01 JUNE 2013 | Number of Extensions: zero |

Project schedule status:

□ On schedule	□ On revised schedule		□ Ahead of schedule		□ Behind schedule

Overall Project Statistics:

| Total Project Budget | Total Cost to Date for Project | Total Percentage of Work Completed |
| --- | --- | --- |
| $325,000 proposed project cost $325,000 received to date | $102,072 | 31% (based on project proposal) |

Quarterly Project Statistics:

| Total Project Expenses This Quarter | Total Amount of Funds Expended This Quarter | Percentage of Work Completed This Quarter |
| --- | --- | --- |
| $12,352 | $12,352 | 8% |

Project Description:

Note: This report was initially submitted to reflect 1st quarter progress from the time period January to March 2012. The filename was called TPF-5(150) Progress Report.doc. The information in this report remains unchanged.

The purpose of the Phase III study is to develop tools and guidance to specify dosage levels of chemical admixtures used in antifreeze concrete to correspond with the varying weather conditions experienced at any job location. A user guide, including a series of design tables, will be developed describing admixture dosages to be adjusted for a specific level of protection. The guide will set dosage rates for general sets of conditions to provide a conservative level of concrete protection during the curing period. The dosage rates will account for the environmental conditions and concrete geometry. The guide will allow technicians to tailor mixture proportions and protective measures based on weather predictions for the first few days following concrete placement.

This quarterly progress report provides a summary of the effort expended and fulfills the reporting requirement in support of Interagency Agreement (IAA) DTFH61-08-X-30031, Modification 1 (signed 6 January 2009) between FHWA and the U.S. Army Engineer Research and Development Center, Cold Regions Research and Engineering Laboratory (ERDC-CRREL), entitled Extending the Season for Concrete Construction and Repair, Phase III – Guidance for Optimizing Admixture Dosage Rates.

Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.):

1. Part 2: Developing design guidance. Lynette Barna and Chuck Korhonen met at CRREL in October 2011 to work with a one-dimensional thermal concrete model, based on heat transfer principles, developed for this project. The model will be used to assess the effects of varying the admixture dosage rate on concrete curing at freezing or below-freezing temperatures. Input values for air temperature can be either actual measurements or forecasted minimum and maximum air temperatures. Up to 29 days worth of data may be entered into the thermal model.

Data collected from field demonstration projects located at Ft. Wainwright, Alaska; Fairbanks, Alaska; and Rhinelander, Wisconsin (Rhinelander was a field demonstration location as part of Phase I) were used to create input files for the thermal model. The Fairbanks demonstration project was a slab on grade with five separate sections (Figure 1) that used varying dosages of chemical admixtures. Five input files, one for each test section were created.

A total of nine data files have been prepared for use as input into the thermal model. Each data file contains the hourly temperature readings collected at each location in the structure. The data file contains the following fields: date/time of day, elapsed time (hours), measured air temperature, measured concrete temperature. An example of the data file for a Ft. Wainwright test section is shown in Figure 2.

Figure 1. Test area layout of the Ft. Wainwright, Alaska demonstration project.

Figure 2. Example of temperature input file. This dataset was generated from Test Section 1 from Ft. Wainwright, Alaska. Temperatures were recorded every 10 minutes. The dataset focuses on the 12-day duration following concrete placement.

2. Project update meeting with FHWA. A teleconference was held on 17 November 2011 with FHWA. The agenda items included an update on the project progress, preparation for the upcoming 91st TRB Annual Meeting, and future funding and technology promotion.

3. ASCE Journal article publication. A paper entitled, “A Energy Efficient Approach to Cold Weather Concreting,” (authored by L. Barna, P. Seman, and C. Korhonen) was published in the ASCE Journal of Materials in Civil Engineering, special issue on “Energy Efficient and Environmentally Friendly Paving Materials.” Vol. 23, No. 11, pps. 1544-1551;

4. Transportation Research Board. Preparations were made to present paper number 12-601 entitled, “Extending the Season for Concrete Construction and Repair,” (authored by L. Barna and C. Korhonen) during the 91st Annual TRB Meeting during the Innovative Concrete Technology poster session sponsored by committees: Strength and Deformation Characteristics of Pavement Sections (AFD80); Basic Research and Emerging Technologies Related to Concrete (AFN10); and Nanotechnology-Based Concrete Materials (AFN15T). The paper will be included in the annual meeting compendium of papers and described the cold weather concreting approach using higher dosages of chemical admixtures to depress the freezing point of the concrete mix water. The paper discussed the eight formulations developed in the laboratory and used in full-scale field demonstrations at low temperature.

5. Funding for Part 3. Funding was received for Part 3 of the project.

Figure 1. Cumulative project expenditures updated for 4th Quarter 2011 to 1st Quarter 2012 shown by quarter from January 2009 when initial funding for Part 1 was confirmed.

An estimated project timeline for Part 2 of the project is given in the table below. The vertical red dotted line indicates which task is currently under way. Application of the energy balance approach will continue during the 4th quarter of Fiscal Year 2011.

Table 1. Part 2 – Develop design guidance project tasks identified and estimated percent completion for Fiscal year 2011 4th Quarter. (Red dotted line indicates current quarter).

Anticipated work next quarter:

- Part 2 – Develop design guidance. Task 1 and associated subtasks will continue. This includes inputting field data to generate concrete temperatures. The effect of the admixture dosage rates will be examined through the heat of hydration curves for the mixtures.

The heat of hydration of cement is modeled mathematically based on the cement content used in the mixture over a realistic amount of time elapsed. Based on the thermal history, the heat of hydration can be backcalculated. This will be done for the input files to begin developing a library of heat of hydration curves.

  - Development of a library of heat of hydration curves;

  - Predicted vs actual concrete temperatures. Continue using field data as input into the thermal model;

  - Developing analysis ‘tool’;

  - Prepare an outline for the final report.

Significant Results:

A mathematical model, based on heat transfer principles, has been developed describing the interaction of a 6-in thick concrete slab placed on grade. Currently, the model neglects the effects of solar radiation and evaporation, and does not include insulation. For the case of the slab on grade, the material layers and thicknesses are defined, including the substrate. Daily maximum and minimum air temperatures, and the time of occurrence were used as input parameters. The heat of hydration of the cement in the mixture is input to determine the amount of heat generated as the concrete cures. The estimated internal concrete temperatures as the concrete cures are output on an hourly basis in tabular form.

The thermal modeling tool enables predicting internal concrete temperatures as it cures to compare with measured temperatures collected from field cured antifreeze concrete. This is a first step in our understanding of the effects of conditions on antifreeze concrete curing under field conditions, in particular the cement content and the heat generation, for early-strength gain when subjected to below freezing temperatures.

The report for Part 1 of the project is available at: http://www.crrel.usace.army.mil/innovations/cold_weather_concreting/antifreeze_admixtures/extending_the_season.html

Circumstance affecting project or budget (Describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope, and fiscal constraints set forth in the agreement, along with recommended solutions to those problems).

Nothing to report at this time.

# Footnotes

Effective 21 December 2011, project end date changed as per scope of work approved 7 August 2008.

Phase III Extending the Season for Concrete Construction and Repair, Guidance for Optimizing Admixture Dosage Rates, Project Proposal, USAERDC-CRREL, submitted 2004.