**TRANSPORTATION POOLED FUND PROGRAM**

**QUARTERLY PROGRESS REPORT**

Lead Agency (FHWA or State DOT): \_\_Iowa DOT\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**INSTRUCTIONS:**

*Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active. Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any. List all tasks, even if no work was done during this period.*

|  |  |
| --- | --- |
| **Transportation Pooled Fund Program Project #***TPF-5(303)* | **Transportation Pooled Fund Program - Report Period:**□Quarter 1 (January 1 – March 31, 2014)XQuarter 2 (April 1 – June 30, 2014)□Quarter 3 (July 1 – September 30)□Quarter 4 (October 1 – December 31) |
| **Project Title:** 2015 Performance Measures Technical Transfer Conference and Asset Management Peer Exchange |
| **Name of Project Manager(s):**

|  |
| --- |
| Matthew Haubrich, Iowa DOT Tom Palmerlee, TRB  |

 | **Phone Number:**

|  |
| --- |
| (515) 233-7902 (202) 334-2907  |

 | **E-Mail**

|  |
| --- |
| Matthew.Haubrich@dot.iowa.gov TPalmerlee@nas.edu  |

 |
| **Lead Agency Project ID:**TPF-5(303) | **Other Project ID (i.e., contract #):**T.B.D. | **Project Start Date:**T.B.D. |
| **Original Project End Date:**June 30, 2016 | **Current Project End Date:**June 30, 2016 | **Number of Extensions:**None |

Project schedule status:

X On schedule □ On revised schedule □ Ahead of schedule □ Behind schedule

Overall Project Statistics:

|  |  |  |
| --- | --- | --- |
|  **Total Project Budget** |  **Total Cost to Date for Project** |  **Percentage of Work**  **Completed to Date** |
| $264,000 committed | $0; no PF funds expended yet |  |

***Quarterly*** Project Statistics:

|  |  |  |
| --- | --- | --- |
|  **Total Project Expenses**  **and Percentage This Quarter** |  **Total Amount of Funds**  **Expended This Quarter** |  **Total Percentage of**  **Time Used to Date** |
| $0; no PF funds expended yet | N/A |  |

|  |  |  |
| --- | --- | --- |
| **Project Description**:

|  |
| --- |
| **Background:**Section 1203 of the MAP-21 stipulates USDOT to promulgate performance measures in the areas of the National Highway Performance Program (NHPP), Highway Safety Improvement Program (HSIP), the Congestion Mitigation and Air Quality Improvement Program (CMAQ), and the National Freight Movement (Freight) within 18 months after the date of enactment of the MAP-21. State DOTs are tasked with developing performance measures plans, which include asset management plans. The focus of this pooled fund project will be in the area of the NHPP.  |
| **Objectives:**The focus of this pooled fund project will be in the area of NHPP. The primary activities of this pooled fund project are technology exchange, information sharing, and the facilitation of partnering relationships among state agencies, AASHTO, FHWA and other appropriate associates. Specifically this pooled fund will: 1. Provide communication and information sharing among member states. Discuss research, development and technology transfer needs in the areas of performance measures and asset management and provide research ideas to TRB in connection with the 2015 PM&AM. 2. Performance Measures Conference (Conference): Provide a technology and knowledge exchange forum to enhance the practical knowledge of conference participants concerning performance measures with a focus on development and refinement of State DOT performance measures plans. 3. 1 Day State DOT Meeting on Asset Management: Provide a technology and knowledge exchange forum focused on the development and refinement of asset management processes for state DOTs. 4. Enhance the working knowledge of the performance measures and asset management communities. **Work Completed this Quarter:**Scoping, budgeting, and partnering have occurred. IA DOT staff is planning a TAC conference call.**Work Proposed next Quarter:**An understanding between FHWA and the Iowa DOT for the Iowa DOT to administer this pooled fund project will be completed early in the in the quarter. A Memorandum of Understanding between the Iowa DOT and TRB will be finalized after FHWA authorization of funds early in the quarter. |

 |

|  |
| --- |
| **Significant Results:** |
| **Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that** **might affect the completion of the project within the time, scope and fiscal constraints set forth in the** **agreement, along with recommended solutions to those problems).** |

|  |
| --- |
| **Potential Implementation:** Implementation is inherent to this project’s activities. |