**TRANSPORTATION POOLED FUND PROGRAM**

**QUARTERLY PROGRESS REPORT**

Lead Agency (FHWA or State DOT): \_\_\_FHWA\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**INSTRUCTIONS:**

*Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active. Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any. List all tasks, even if no work was done during this period.*

|  |  |  |  |
| --- | --- | --- | --- |
| **Transportation Pooled Fund Program Project #**  *TPF-5(454)* | | **Transportation Pooled Fund Program - Report Period:**  □Quarter 1 (January 1 – March 31)  XQuarter 2 (April 1 – June 30) 2021  □Quarter 3 (July 1 – September 30)  □Quarter 4 (October 1 – December 31) | |
| **Project Title:**  Updating U.S. Precipitation Frequency Estimates for the Northwest | | | |
| **Name of Project Manager(s):**  Cynthia Nurmi | **Phone Number:**  (404) 895-0996 | | **E-Mail**  cynthia.nurmi@dot.gov |
| **Lead Agency Project ID:**  **FHWA** | **Other Project ID (i.e., contract #):** | | **Project Start Date:**  June 3, 2020 |
| **Original Project End Date:**  December 2023 | **Current Project** End Date:  December 2023 | | **Number of Extensions:** |

Project schedule status:

X On schedule □ On revised schedule □ Ahead of schedule □ Behind schedule

Overall Project Statistics:

|  |  |  |
| --- | --- | --- |
| **Total Project Budget** | **Total Cost to Date for Project** | **Percentage of Work**  **Completed to Date** |
| $640,895 | $231000 | 1 |

***Quarterly*** Project Statistics:

|  |  |  |
| --- | --- | --- |
| **Total Project Expenses**  **and Percentage This Quarter** | **Total Amount of Funds**  **Expended This Quarter** | **Total Percentage of**  **Time Used to Date** |
| $6409 | $6409 | 1 |

|  |
| --- |
| **Project Description**:  Update of NOAA Atlas XIV for Montana and Idaho. Results will be published in Volume 12. |

|  |
| --- |
| **Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.):**  Received full amount of annual funds. Initiated process to add funds to existing Interagency Agreement with NOAA to  begin project research.  Held kick off meeting with Montana and Idaho April 21 and 22, 2021. |
| **Anticipated work next quarter**:  Begin Task 1 Data collection and formatting; Metadata examination and station cleanup |

|  |
| --- |
| **Significant Results:**  **Kick Off Meeting.**  **https://www.weather.gov/media/owp/oh/hdsc/docs/202107\_HDSC\_PR.pdf** |
| **Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that**  **might affect the completion of the project within the time, scope and fiscal constraints set forth in the**  **agreement, along with recommended solutions to those problems).**  **None** |

|  |
| --- |
| **Potential Implementation:**  N/A |