HSM Implementation Pooled Fund Study

TPF-5(255)

https://www.pooledfund.org/Details/Study/484

Quarterly Report

January – March 2022

Participating Agencies: CA, CT, ID, IL, KS, KY, LA, MI, MS, MO, NV, NJ, NC, OH, OK, OR, PA, TX, UT, WA, WV, and WI

Total Funds Committed: 			$1,555,000

Total Funds Transferred to FHWA: 	$1,508,558

Total Funds Obligated: 			$ 1,197696

Transferred Unobligated Funds: 		$   310,862

Activities Accomplished During Reporting Period (January 1 – March 31, 2022):

- A statement of work for the three project proposals – 1) use of multiple analysis methods in alternatives analysis, implementation approaches for NCHRP 17-62 (Improved prediction Models for Crash Types and Severities), and 3) communications guide for explaining safety analysis to non-safety professionals was developed and a task order proposal request under the FHWA 2020 Safety IDIQ contract was advertised on .  Proposals were reviewed and a contractor (VHB) was selected on March 29.  A kick-off meeting will be scheduled in April.

- Updates on ongoing projects:

  - HSM Case Studies

    - The contractor (VHB) has been developing case studies.  The following case studies were completed: District of Columbia, Arizona, and Florida and will be posted to the FHWA RSDP case studies website soon.  California and Vermont are currently under development.

Activities Planned for Next Quarter (April 1 – June 30, 2022):

- Work will continue on developing HSM Case Studies highlighting projects in California and Connecticut.

- A kick-off meeting for the Advancing Applications of DDSA task order will be conducted (tentatively scheduled for April 26).

- In April, FHWA will post a new transportation pooled fund solicitation to create a Highway Safety Manual Second Edition (HSM2) Implementation pooled fund, anticipated to begin in 2023.