QUARTERLY PROGRESS REPORT

April through June 2024

Improving Traffic Detection Through New Innovative i-LST Technology Demonstration Pilot

FHWA Pooled Fund Study # TPF-5(520)

Submitted by:

FHWA

WORK CONDUCTED THIS QUARTER

- SOW and contract package completed – sent to contracts office

- Agenda set for TAC meeting – update provided in May to all TAC members

- 7 agency contributions missing, let all TAC members know of this issue

- AMR funding ready to go

- FMCSA funding done

- Remote TAC update meeting held

WORK PLANNED FOR NEXT QUARTER

- Contract out for bid

- Contractor selection

- TAC member and contractor initial meeting - remotely

- Conduct briefings for agencies

- All TAC member funding received

- Select corridors to study

- Write MOU draft for use for i-LST locations to be part of the study

SIGNIFICANT ISSUES

- TAC members funds needed from all PF members