Click here to enter Program or Project Title

Progress Report – Click here to enter a date.

Title: Assessment and Repair of Prestressed Bridge Girders Subjected to Over-height Truck Impacts Pooled Fund Project

Project Number: TR202011

Principal Investigator (PI): Mohamed ElGawady PhD (PI)

Co-PI(s): William Schonberg PhD, PE (Co-PI)

| Award date: | 1/1/2021 |  |  |
| --- | --- | --- | --- |
| Scheduled completion date: | 12/31/2023 | % of project completed to date: | 83% |
| Total budget: | $805,000 | % of budget expended to date: | 84% |
| Draft report due: | 9/30/2023 | Final report due: | 12/1/2023 |  |

Provide a short description of the work currently underway.

Use additional notes section if you need to provide more information.

Task 2. Experimental testing of bridge girders subjected to lateral impacts:

- The 7th and 8th girders were tested. Both girders were tested with intermediate diaphragms

Task 3. Determine the residual flexural and shear strengths of the damaged bridge girders

- Girders 2 through 4 were tested under four pint bending. The girders are as follows:

G2: Sustained only minor impact damage and served as the baseline for comparison.

G3: Suffered severe mid-span damage, losing 3 of its 12 strands due to the impact.

G4: Experienced even more significant damage, with half of its strands (6 out of 12) severed.

Task 5: Repair Evaluation:

- Girders 5 and 6 are being repaired and prepared for flexural testing. Girder 5 are being repaired using strand splice and 6 using CFRP

Provide a short description of the noteworthy activities/accomplishments during this reporting period.

Use additional notes section if you need to provide more information.

Task 2. Experimental testing of bridge girders subjected to lateral impacts

| Impact side | Back side |
| --- | --- |

Fig. 1. Testing girders 7 and 8 with intermediate diaphragm

Task 3. Determine the residual flexural and shear strengths of the damaged bridge girders

- The residual capacity of the damaged girders were determined using four point testing.

Table 1. Summary of damaged girders

| Girder | Number of severed strands | Level of damage | Damage classification per NCHRP 20-07/Task 307 |
| --- | --- | --- | --- |
| 2 | 0 | 0% | Minor |
| 3 | 3 | 25% | Severe III |
| 4 | 6 | 50% | Severe IV |

Hydraulic jack Load cell

Fig. 2. Experimental test setup

Fig.3 Testing of girder 2

Fig.4. Failure of girder 2

| Cross section showing loss of strands | Section along the girder showing strand loss (before flexural test) |
| --- | --- |

Fig.5 Girder 3 with 25% strand loss

| Fig. 6. Failure of girder 3 |  |
| --- | --- |

| Cross section showing loss of strands | Section along the girder showing strand loss (before flexural test) |
| --- | --- |

| Fig.7. Failure of girder 4 at 72kips |  |
| --- | --- |