TRANSPORTATION POOLED FUND PROGRAM

QUARTERLY PROGRESS REPORT

Lead Agency (FHWA or State DOT):  ___FHWA_____________________________________

INSTRUCTIONS:

Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active.  Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any.  List all tasks, even if no work was done during this period.

| Transportation Pooled Fund Program Project # TPF-5(454) |  | Transportation Pooled Fund Program - Report Period: □ Quarter 1 (January 1 – March 31) X Quarter 2 (April 1 – June 30) □ Quarter 3 (July 1 – September 30) □ Quarter 4 (October 1 – December 31) |  |
| --- | --- | --- | --- |
| Project Title: ## Update Precipitation Frequency Estimates for the Northwest (NOAA Atlas 14, Vol. 12) |  |  |  |
| Name of Project Manager(s): Megan Frye | Phone Number: (303) 396-9847 |  | E-Mail megan.frye@dot.gov |
| Lead Agency Project ID: FHWA | Other Project ID (i.e., contract #): |  | Project Start Date: June 3, 2020 |
| Original Project End Date: December 2023 | Current Project End Date: September 2024 |  | Number of Extensions: |

Project schedule status:

□ On schedule	□ On revised schedule		□ Ahead of schedule		X Behind schedule

Overall Project Statistics:

| Total Project Budget | Total Cost to Date for Project | Percentage of Work Completed to Date |
| --- | --- | --- |
| $640,894 | $614,335 | 95% |

Quarterly Project Statistics:

| Total Project Expenses and Percentage This Quarter | Total Amount of Funds Expended This Quarter | Total Percentage of Time Used to Date |
| --- | --- | --- |
| $26,560 / 5% | $26,560 | 95% |

Project Description: The purpose of this study is to determine precipitation frequency estimates for Idaho, Montana and other the Northwest States for durations of 5-minute through 60-day at average recurrence intervals (ARIs) of 1-year through 1,000-year. The estimates and associated bounds of 90% confidence intervals will be provided at 30 arc-sec resolution (approximately 800 x 800 m; varies with latitude). The study results will be published as volumes of NOAA Atlas 14, a wholly web-based publication available at www.nws.noaa.gov/ohd/hdsc. The publication will include the artifacts provided in previous NOAA Atlas 14 Volumes, including access through the Precipitation Frequency Data Server, base grids in standard formats together with error estimates, electronic copies of maps, charts of seasonal distributions and probabilistic temporal distributions of heavy precipitation, and detailed documentation. Updated areal reduction factors, which are needed to calculate analogous areal precipitation frequency estimates, will be developed as a separate appendix to NOAA Atlas 14 for the entire U.S. They include regional frequency analysis based on L-moments including error estimates, a combination of PRISM based techniques and CRAB for spatial interpolation, techniques for the analysis of climatic trend, temporal distribution and seasonality, internal consistency checks and variety of automated processes designed to enhance productivity. Intermediate results in the form of hourly and daily estimates at several ARIs will be distributed for peer review as will the final documentation.

Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.): During this reporting period, NOAA finalized mean annual maxima grids across all durations with the help of the Oregon State University, PRISM group. They updated estimates across all duration, 1-day through 60-day, and began reviewing the spatial patterns and final depth-duration frequency (DDF) curves. NOAA also finalized development of the supplementary information, such as trend analysis, temporal analysis and confidence intervals, and started drafting documentation. Additional information is on the status of the Atlas 14, Volume 12 work is available at: https://www.weather.gov/owp/hdsc_current_projects

Anticipated work next quarter: During the next reporting period, NOAA will work on finalizing the data and supplementary information for the web publication. This includes completing the final gridded AMS-based and partial duration series (PDS)-based estimates, as well as gridded upper and lower confidence limits for 90% confidence interval for all durations and frequencies, creating cartographic maps, documentation, and other web documents. NOAA will also develop final rainfall frequency estimates and expects to publish estimates on the PFDS by the end of September.

Significant Results: Spatial interpolation and analysis of mean annual maximum (MAM) data - Spatial interpolation of MAM values estimated at gauged locations is done by the Oregon State University’s PRISM Climate Group using their hybrid statistical-geographic approach for mapping Hydrometeorological Design Studies Center Progress Report, October 2024 6 climate data. During this reporting period, three additional iterations were done with the PRISM group to ensure realistic spatial patterns and consistency in gridded MAMs for 1-hour, 6-hour, 1-day, 4-day, 10-day, 30-day, and 60-day durations. In the process, NOAA reviewed MAM data for each station for inconsistencies relative to MAMs at nearby stations in order to identify locations where MAMs are affected by short periods of record or missed extreme amounts. Flagged MAMs were investigated and either adjusted or removed from the analysis. Revision of spatially interpolated precipitation frequency estimates - The grids of mean annual maxima (MAM) at 30 arc-sec resolution, together with at station precipitation frequency estimates, are the basis for calculation of gridded annual maximum series (AMS)-based and partial duration series (PDS)-based precipitation frequency estimates and corresponding upper and lower bounds of the 90% confidence interval. Mean annual maximum grids serve as the basis for calculation of the precipitation frequency estimates for the 2-year average recurrence interval (ARI), which are then used to calculate gridded 5-year estimates and so on. During this reporting period, NOAA reviewed spatial patterns for the 2-year, 100-year and 1000-year grids across all durations and revisited and improved at-station and regional estimates where needed. The resulting adjustments were then carried through to other recurrence intervals in an iterative process. Typically, several iterations are required to ensure realistic spatial patterns and consistency in gridded estimates for 13 selected durations from 1 hour to 60 days (1-hr, 2-hr, 3-hr, 6-hr, 12-hr, 24-hr, 2-day, 4- day, 7-day, 20-day, 30-day, 45-day and 60-day). To ensure consistency in grid cell values across all durations and frequencies (e.g., a 24-hour estimate has to be at least equal to the corresponding 12-hour estimate), NOAA also conducted duration-based internal consistency checks across durations and frequencies. Development of PFDS web pages for Volume 12 - During this reporting period, NOAA worked on the development of updated PFDS web pages for the new project area of Volume 12 and have prepared pertinent Federal Geographic Data Committee (FGDC) compliant metadata. They also developed templates for all PFDS cartographic maps.

Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope and fiscal constraints set forth in the agreement, along with recommended solutions to those problems). Delay in finalizing the IAA with NOAA. NOAA has faced delays in the availability of existing personnel to commit to the project. The project milestone schedule has been updated and completion of the project has been delayed from Q4 of 2023 to Q3 of 2024. Current Schedule: - Data collection, formatting, and initial quality control [Completed] - Extraction of annual maximum series (AMS); additional quality control and data reliability tests (e.g., outliers, independence, consistency across durations, duplicate stations, candidates for merging)] [Completed] - Regionalization and frequency analysis [Completed] - Initial spatial interpolation of precipitation frequency (PF) estimates and consistency checks across durations [Completed] - Peer review [Completed] - Revision of PF estimates [In Progress, Q3 2024] - Remaining tasks (e.g., development of precipitation frequency estimates for partial duration series, seasonality, temporal distributions, documentation) [In progress, Q3 2024] - Web publication [In progress, Q3 2024]

Potential Implementation: All deliverables will be accessible through the Precipitation Frequency Data Server (PFDS). That includes: - Interactive map of the United States. Via this map, IDF/DDF tables and curves will be available for any location in the project area. - Precipitation frequency grids in GIS compatible formats. - Metadata in Federal Geographic Data Transfer Standard format. - Cartographic maps of precipitation frequency estimates. - Charts of the seasonal distribution of annual maxima - Probabilistic temporal distributions for 6-hour, 12-hour, 24-hour, and 96-hour durations in both chart and digital form - Rainfall frequency estimates with corresponding upper and lower bounds of 90% confidence intervals will be available at 30-arc sec grid for durations of 1, 2, 3, 6, 12 and 24 hours. Web publication is anticipated in September 2024.