TRANSPORTATION POOLED FUND PROGRAM

QUARTERLY PROGRESS REPORT

Lead Agency (FHWA or State DOT):  ___FHWA_____________________________________

INSTRUCTIONS:

Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active.  Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any.  List all tasks, even if no work was done during this period.

| Transportation Pooled Fund Program Project # TPF-5(454) |  | Transportation Pooled Fund Program - Report Period: □ Quarter 1 (January 1 – March 31) □ Quarter 2 (April 1 – June 30) X Quarter 3 (July 1 – September 30) □ Quarter 4 (October 1 – December 31) |  |
| --- | --- | --- | --- |
| Project Title: ## Update Precipitation Frequency Estimates for the Northwest (NOAA Atlas 14, Vol. 12) |  |  |  |
| Name of Project Manager(s): Megan Frye | Phone Number: (303) 396-9847 |  | E-Mail megan.frye@dot.gov |
| Lead Agency Project ID: FHWA | Other Project ID (i.e., contract #): |  | Project Start Date: June 3, 2020 |
| Original Project End Date: December 2023 | Current Project End Date: September 2024 |  | Number of Extensions: |

Project schedule status:

□ On schedule	□ On revised schedule		□ Ahead of schedule		X Behind schedule

Overall Project Statistics:

| Total Project Budget | Total Cost to Date for Project | Percentage of Work Completed to Date |
| --- | --- | --- |
| $640,894 | $640,894 | 100% |

Quarterly Project Statistics:

| Total Project Expenses and Percentage This Quarter | Total Amount of Funds Expended This Quarter | Total Percentage of Time Used to Date |
| --- | --- | --- |
| $26,560 / 5% | $26,560 | 100% |

Project Description: The purpose of this study is to determine precipitation frequency estimates for Idaho, Montana and other the Northwest States for durations of 5-minute through 60-day at average recurrence intervals (ARIs) of 1-year through 1,000-year. The estimates and associated bounds of 90% confidence intervals will be provided at 30 arc-sec resolution (approximately 800 x 800 m; varies with latitude). The study results will be published as volumes of NOAA Atlas 14, a wholly web-based publication available at www.nws.noaa.gov/ohd/hdsc. The publication will include the artifacts provided in previous NOAA Atlas 14 Volumes, including access through the Precipitation Frequency Data Server, base grids in standard formats together with error estimates, electronic copies of maps, charts of seasonal distributions and probabilistic temporal distributions of heavy precipitation, and detailed documentation. Updated areal reduction factors, which are needed to calculate analogous areal precipitation frequency estimates, will be developed as a separate appendix to NOAA Atlas 14 for the entire U.S. They include regional frequency analysis based on L-moments including error estimates, a combination of PRISM based techniques and CRAB for spatial interpolation, techniques for the analysis of climatic trend, temporal distribution and seasonality, internal consistency checks and variety of automated processes designed to enhance productivity. Intermediate results in the form of hourly and daily estimates at several ARIs will be distributed for peer review as will the final documentation.

Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.): During this reporting period, NOAA we finalized estimates across all durations, 1-day through 60-day, after extensively reviewing the spatial patterns and corresponding depth-duration frequency (DDF) curves. Once the review of estimates was complete, NOAA finalized development of the supplementary information, such as trend analysis, temporal analysis and confidence intervals, and documentation. Additional information is on the status of the Atlas 14, Volume 12 work is available at: https://www.weather.gov/owp/hdsc_current_projects

Anticipated work next quarter: The project was completed this quarter, anticipated work in next quarter will include TPF project closeout and some minor revisions to Section 5 of the NOAA Atlas 14 documentation.

Significant Results: Finalization of spatially interpolated precipitation frequency estimates - During this reporting period, NOAA finalized spatial patterns for the 2-year, 100-year and 1000-year grids across all durations, and revisited and improved at-station and regional estimates where needed. Corresponding depth-duration frequency curves were adjusted to ensure consistent transition between durations and return periods. The resulting adjustments were then carried through to other recurrence intervals in an iterative process. Typically, several iterations are required to ensure realistic spatial patterns and consistency in gridded estimates for 13 selected durations from 1 hour to 60 days (1-hr, 2-hr, 3-hr, 6-hr, 12-hr, 24-hr, 2-day, 4-day, 7-day, 20-day, 30-day, 45-day and 60-day). To ensure consistency in grid cell values across all durations and frequencies (e.g., a 24-hour estimate has to be at least equal to the corresponding 12-hour estimate), NOAA also conducted duration-based internal consistency checks across durations and frequencies. Documentation - During this reporting period, NOAA completed work on the Atlas 14 Volume 12 Version 2 documentation which is available for download here: https://www.weather.gov/media/owp/oh/hdsc/docs/Atlas14_Volume12.pdf. The documentation is similar in layout, coverage and depth to documentation prepared for previous NOAA Atlas 14 volumes. It describes all aspects of the development of each artifact in sufficient depth to allow the knowledgeable user to understand the basis of the estimates and their scope and applicability. It also includes information on the comments received during the peer review process and HDSC follow-up actions (see Appendix 5), and relates current NOAA Atlas 14 estimates with corresponding estimates from superseded NOAA publications (Section 7). Development of PFDS web pages for Volume 12 - Precipitation frequency estimates for the Interior Northwest with supplementary products were published as NOAA Atlas 14 Volume 12 Version 2 on September 19, 2024. All NOAA Atlas 14 Volume 12 products are available for download from the PFDS page for the Interior Northwest. Section 5 of the NOAA Atlas 14 documentation provides additional information on the underlying data and functioning of the PFDS. Section 5 will be updated over the next reporting period.

Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope and fiscal constraints set forth in the agreement, along with recommended solutions to those problems). Delay in finalizing the IAA with NOAA. NOAA has faced delays in the availability of existing personnel to commit to the project. The project milestone schedule has been updated and completion of the project has been delayed from Q4 of 2023 to Q3 of 2024. Current Schedule: - Data collection, formatting, and initial quality control [Completed] - Extraction of annual maximum series (AMS); additional quality control and data reliability tests (e.g., outliers, independence, consistency across durations, duplicate stations, candidates for merging)] [Completed] - Regionalization and frequency analysis [Completed] - Initial spatial interpolation of precipitation frequency (PF) estimates and consistency checks across durations [Completed] - Peer review [Completed] - Revision of PF estimates [Completed] - Remaining tasks (e.g., development of precipitation frequency estimates for partial duration series, seasonality, temporal distributions, documentation) [Completed] - Web publication [Completed]

Potential Implementation: All deliverables will be accessible through the Precipitation Frequency Data Server (PFDS). That includes: - Interactive map of the United States. Via this map, IDF/DDF tables and curves will be available for any location in the project area. - Precipitation frequency grids in GIS compatible formats. - Metadata in Federal Geographic Data Transfer Standard format. - Cartographic maps of precipitation frequency estimates. - Charts of the seasonal distribution of annual maxima - Probabilistic temporal distributions for 6-hour, 12-hour, 24-hour, and 96-hour durations in both chart and digital form - Rainfall frequency estimates with corresponding upper and lower bounds of 90% confidence intervals will be available at 30-arc sec grid for durations of 1, 2, 3, 6, 12 and 24 hours. Precipitation frequency estimates for the Interior Northwest with supplementary products were published as Atlas 14 Volume 12 Version 2 on September 19, 2024. All NOAA Atlas 14 Volume 12 products are available for download from the PFDS page for the Interior Northwest