**TRANSPORTATION POOLED FUND PROGRAM**

**QUARTERLY PROGRESS REPORT**

Lead Agency (FHWA or State DOT): Virginia DOT (VDOT) .

**INSTRUCTIONS:**

*Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active. Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any. List all tasks, even if no work was done during this period.*

|  |  |
| --- | --- |
| **Transportation Pooled Fund Program Project #***(i.e, SPR-2(XXX), SPR-3(XXX) or TPF-5(XXX)***TPF-5(518) Implementation of Structural Data from Traffic Speed Deflection Devices** | **Transportation Pooled Fund Program - Report Period:**🞎 Quarter 1 (January 1 – March 31)🗹 Quarter 2 (April 1 – June 30)🞎 Quarter 3 (July 1 – September 30)🞎 Quarter 4 (October 1 – December 31) |
| **Project Title:****Implementation of Structural Data from Traffic Speed Deflection Devices** |
| **Name of Project Manager(s):**Brian Diefenderfer | **Phone Number:**(434) 293-1944 | **E-Mail**brian.diefenderfer@vdot.virginia.gov |
| **Lead Agency Project ID:** | **Other Project ID (i.e., contract #):**467764 (VT) | **Project Start Date:**2/1/2024 |
| **Original Project End Date:**9/30/2028 | **Current Project End Date:**9/30/2028 | **Number of Extensions:**-- |

Project schedule status:

* On schedule 🞎 On revised schedule 🞎 Ahead of schedule 🞎 Behind schedule

Overall Project Statistics:

|  |  |  |
| --- | --- | --- |
| **Total Project Budget** | **Total Cost to Date for Project** | **Percentage of Work****Completed to Date** |
| $4,494,000\* | $ 252,423 | 5% |

***Quarterly*** Project Statistics:

|  |  |  |
| --- | --- | --- |
|  **Total Project Expenses**  **and Percentage This Quarter** |  **Total Amount of Funds**  **Expended This Quarter** |  **Total Percentage of**  **Time Used to Date** |
| $ 252,423 (5%) | $ 252,423 | 5% |

\* Committed; the actual contracted budget is $1,963,000(VTTI)

|  |
| --- |
| **Project Description**:The objectives of this follow-on pooled fund study include continuation of an existing research consortium that focuses on providing participating agencies guidance on how to specify and implement TSDD data within their respective pavement management systems and processes. Specific tasks within this multi-year program will be developed in cooperation with the partner agencies. |

|  |
| --- |
| **Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.):*** Conducted virtual planning TAC meeting to finalize who will host the 3rd annual symposium (Texas was selected)
* Started planning the 3rd annual symposium meeting with Texas (Selected: Sheraton Down Town Fort Worth Hotel)
* Conducted webinar on possible additional TSDDs becoming available in the US.
* Planned the 3rd phase of TSD validation testing at the Virginia Smart Road.
 |

|  |
| --- |
| **Anticipated work next quarter**:* Conduct the 3rd annual symposium meeting in September
* Analyze and present data from the 3rd phase of TSD validation at the 3rd annual symposium
* Conduct the 3rd phase of TSD validation
* Work on two TSD related papers to be submitted for the TRB annual meeting
 |

|  |
| --- |
| **Significant Results:** |

|  |
| --- |
| **Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope and fiscal constraints set forth in the agreement, along with recommended solutions to those problems).** |

|  |
| --- |
| **Potential Implementation:**  |