**TRANSPORTATION POOLED FUND PROGRAM**

**QUARTERLY PROGRESS REPORT**

Lead Agency (FHWA or State DOT): \_\_Washington State Department of Transportation\_\_\_\_\_\_

**INSTRUCTIONS:**

*Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active. Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any. List all tasks, even if no work was done during this period.*

|  |  |  |  |
| --- | --- | --- | --- |
| **Transportation Pooled Fund Program Project #**  *(i.e, SPR-2(XXX), SPR-3(XXX) or TPF-5(XXX)*  TPF-5(527) | | **Transportation Pooled Fund Program - Report Period:**  □XXQuarter 1 (January 1 – March 31) 2025  □Quarter 2 (April 1 – June 30)  □Quarter 3 (July 1 – September 30)  □Quarter 4 (October 1 – December 31) | |
| **Project Title:**  **International Conference on Ecology & Transportation 2023 Pooled Fund** | | | |
| **Name of Project Manager(s):**  Jon Peterson – Research Coordinator | **Phone Number:**  (360) 705-7499 | | **E-Mail**  peterjn@wsdot.wa.gov |
| **Lead Agency Project ID:** | **Other Project ID (i.e., contract #):** | | **Project Start Date:**  October 2024 |
| **Original Project End Date:** | **Current Project End Date:**  **June 30, 2025** | | **Number of Extensions:** |

Project schedule status:

X□ On schedule On revised schedule □ Ahead of schedule □ Behind schedule

Overall Project Statistics:

|  |  |  |
| --- | --- | --- |
| **Total Project Budget** | **Total Cost to Date for Project** | **Percentage of Work**  **Completed to Date** |
| $88,200 |  |  |

***Quarterly*** Project Statistics:

|  |  |  |
| --- | --- | --- |
| **Total Project Expenses**  **and Percentage This Quarter** | **Total Amount of Funds**  **Expended This Quarter** | **Total Percentage of**  **Time Used to Date** |
|  |  |  |

|  |
| --- |
| **Project Description**:  There have been thirteen biennial International Conferences on Ecology and Transportation (ICOET) since its origin in 1999. The most recent conference was in June of 2023 in Burlington, Vermont and was a combination of in person and virtual.  This pooled fund will support the next conference in 2025 in May that will be an in-person conference in Denver, Colorado cohosted by the Colorado Department of Transportation and the Colorado Parks & Wildlife Department and organized by the University of California Davis Road Ecology Center.  There will be a virtual conference option available.  ICOET continues to serve as an invaluable conduit for transportation and ecology professionals to share applicable research and best practices, and to transfer knowledge between experienced practitioners and future leaders.  The ICOET program includes podium presentations, posters on current research, panels, workshops, field trips, and exhibits on topics of interest to researchers, biologists, engineers, planners, project managers, administrators, and policy makers. The folks that regularly attend ICOET represent thousands of professionals that work for government, Tribal, academic, non-governmental and private industry from the United States and other countries. The 2023 conference had 493 total participants with 354 in person and another 139 virtual participants.  There were 18 countries, 44 U.S. states, and 2 Canadian provinces in attendance.  This new pooled fund will supersede the previous pooled fund (TPF 5-499) that will be completed December 31, 2023.  **Objectives**  Provide one ICOET Conference in May of 2025 for communication, technology transfer and information sharing among transportation professionals on ecology issues and transportation. The ICOET Conference will be in Colorado from May 11-15, 2025, cohosted by the Colorado Department of Transportation and the Colorado Parks & Wildlife Department, with support from FHWA and organized by the Road Ecology Center at Davis.  There will also be a hybrid component to the conference that folks can attend virtually.  Building on the 2023 ICOET Conference this 14th biennial conference in 2025 will:  • Bring experts around the world to exchange knowledge & best practices on the interrelationship of ecology & transportation.  • The sharing of ideas through presentations, panel discussion, breaks, lunches, receptions, and field trips.  • Expand the shared knowledge and learn about the cutting edge of science on the topic of ecology and transportation.  **Scope of Work**  The Washington State Department of Transportation (WSDOT) will serve as the lead state to carry out this pooled fund. The Road Ecology Center at UC Davis will organize the ICOET conference for 2025. The ICOET Steering Committee and FHWA will be assisting WSDOT and the  Road Ecology Center in support of the ICOET Conference.  Project Team:  Contract Manager: Jon Peterson, WSDOT Research & Library Services, peterjn@wsdot.wa.gov, (360) 705-7499  Technical Lead: Jeff Dreier, WSDOT Fish & Wildlife Program Manager, drierj@wsdot.wa.gov, (360) 705-7254  **Comments**  Each pooled fund partner agency will have one representative on the Pooled Fund Technical Advisory Committee (TAC) and as such will be a partner in TAC conference calls. The TAC conference calls will serve to update the partners on the planning activities for the ICOET conference and to collect feedback for the conference planners. The anticipated start date for the pooled fund is July 1, 2024, and the estimated completion date is December 31, 2025.    There is no suggested minimum commitment, however a commitment of $2,000 will allow for 1 free in person registration and a commitment of $1,000 will allow for 1 free virtual registration.   For example, if a partner agency contributes $3,000 that would qualify for a combination of 1 in person registrations and 1 virtual registration or 3 virtual registrations.  Partners may include government agencies, private sector entities and international partners.  The minimum funding required to support this pooled fund is $20,000 from all the partners. |

|  |
| --- |
| **Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.):**  13 states are contributing $83,200 to the pooled fund for the conference. UC Davis sent a Task Order (contract) for signature this quarter for the Conference in the amount of $78,200. |
| **Anticipated work next quarter**:  UC Davis will sign an amendment to the Task Order this quarter for the remaining $5,000 to bring the total amount of the  contract for the conference to $83,200.  The conference will be held this quarter and a final report issued in June.  A new pooled fund will be put out for solicitation in June for the ICOET 2027 conference to be held in Portland, Oregon  and will be a joint conference hosted by Oregon Dept. of Transportation and Washington State Dept. of Transportation  with assistance from their respective wildlife departments and UC Davis. |

|  |
| --- |
| **Significant Results:** |
| **Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that**  **might affect the completion of the project within the time, scope and fiscal constraints set forth in the**  **agreement, along with recommended solutions to those problems).** |

|  |
| --- |
| **Potential Implementation:** |