**TRANSPORTATION POOLED FUND PROGRAM**

**QUARTERLY PROGRESS REPORT**

|  |  |
| --- | --- |
| Lead Agency (FHWA or State DOT):  | Colorado Department of Transportation |

**INSTRUCTIONS:**

*Lead Agency contacts should complete a quarterly progress report for each calendar quarter during which the projects are active. Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any. List all tasks, even if no work was done during this period.*

|  |  |
| --- | --- |
| **Transportation Pooled Fund Program Project #***(i.e, SPR-2(XXX), SPR-3(XXX) or TPF-5(XXX)**TPF-5(441)* | **Transportation Pooled Fund Program - Report Period:**[x] Quarter 1 (January 1 – March 31)[ ] Quarter 2 (April 1 – June 30)[ ] Quarter 3 (July 1 – September 30)[ ] Quarter 4 (October 1 – December 31) |
| **TPF Study Number and Title:**TPF-5(441) No Boundaries Maintenance Innovations |
| **Lead Agency Contact:**James Fox | **Lead Agency Phone Number:**720-241-6309 | **Lead Agency E-Mail**james.fox@state.co.us |
| **Lead Agency Project ID:**R6.3 - TPF-5(441) | **Other Project ID (i.e., contract #):**PO 431009297 (expires 9/1/25) | **Project Start Date:**9/30/2020 |
| **Original Project Start Date:**9/30/2020 | **Original Project End Date:**12/30/2025 | **If Extension has been requested,** **updated project End Date:** Click or tap to enter a date. |

**Project schedule status:**

|  |  |  |  |
| --- | --- | --- | --- |
| [x] On schedule | [ ] On revised schedule | [ ] Ahead of schedule | [ ]  Behind schedule |

**Overall Project Statistics:**

|  |  |  |
| --- | --- | --- |
| **Total Project Budget** | **Total Funds Expended****This Quarter** | **Percentage of Work****Completed to Date** |
| $960,000.00 | $28,206.20 | 79% |

**Project Description:**

|  |
| --- |
| No Boundaries Roadway Maintenance Practices transportation pooled fund program is sponsored by the Federal Highway Administration and is led by Colorado Department of Transportation (CDOT). Increasingly, state departments of transportation (DOTs) are challenged to maintain highway facilities to fluctuating budgets, policies and unknown future issues. Maintenance is a long-term activity to extend the life of highways. One of the strategies for achieving longer life facilities is to use innovative maintenance technologies and practices.No Boundaries is a vital partner in connecting DOT maintenance professionals. By bringing together peers from transportation agencies across the nation and allowing sharing through a variety of channels—face-to-face peer exchanges, technical tours, online clearinghouse database, news distributions, and national partnerships—No Boundaries provides a network that accelerates the transfer of good ideas. This reduces duplication of effort, supports collaboration, and hastens the implementation of maintenance best practices. No Boundaries further fosters collaboration within the transportation community, academia and industry to implement innovative transportation maintenance technologies. The scope of work is divided into five Task Areas, A through E.A. General: staffing and management, updating the operations and procedures manual, and required record keeping.B. Administration: creation of quarterly reports, budget and invoicing, monitoring and coordination of funding transfer among member states, and technical advisory committee meeting (TAC) meetings and peer exchanges.C. Communication: correspondence with TAC members and regular meetings, and creation and delivery of maintenance news items.D. Research and innovation: quick-turnaround synthesis research, innovation database development and launch, and innovation database support.E. Marketing and recruitment: solicitation of new members, marketing (website updates and upkeep, program brochures, innovation one-sheets, and a marketing pan), and partnership and liaison opportunities. |

**Progress this Quarter**

**(includes meetings, work plan status, contract status, significant progress, etc.):**

|  |
| --- |
| A. General* Conducted work in categories A-E below identified on Task Order 4.
* Developed, drafted and finalized a fourth amendment to Task Order 4.
* Conducted ongoing management and record keeping.
* Updated membership roster, including updated technical and research staff from member states.

B. Administration* Planned and facilitated a Steering Committee meeting on February 24, 2025 and documented in detail for members.
* Began the planning for a hybrid in-person/virtual TAC Peer Exchange from April 29-May 1, 2025 in Portland, ME.
	+ Created a travel memo, developed a working draft agenda, coordinated with MaineDOT on the technical site visit and guest presentations, secured a hotel for guest rooms and meeting space, worked with MaineDOT staff on the meeting logistics, arranged air travel for No Boundaries members.
* Kept budget and tracking spreadsheets up to date.
 |

|  |
| --- |
| C. Communication* Continued writing and sending weekly emails, featuring individual news items on research, webinars, events, and program announcements, to the No Boundaries email distribution list.
* Coordinated quick-turnaround surveys and forwarded formal surveys at individual members’ and outside researchers’ requests.
	+ NHI Maintenance Management Systems course – request for beta testers – FHWA
	+ Wearable lighting to increase the visibility of our workers during nighttime ops– IN DOT
* Communicated with individual members to fulfill information requests.

D. Research and Innovation* Continued collecting/creating innovations for the innovations database.

E. Marketing and Recruitment* Updated website with new program information.
 |

**Anticipated work next quarter:**

|  |
| --- |
| A. General* Conduct ongoing management and record keeping.

B. Administration* Finalize planning for a hybrid in-person/virtual TAC Peer Exchange the week of April 28, 2025 in Portland, ME.
	+ Planning will include finalizing the meeting agenda, guest presentations and technical site visit details; book flights; finalize hotel guest room and meeting logistics.
	+ Onsite activities included facilitating and documenting the meeting.
	+ Follow-up activities included posting meeting materials, creating a meeting summary presentation for members to use withing their agencies and assisting with member reimbursements.
* Work with CDOT on financials as the current phase of the pooled fund comes to an end.

C. Communication* Continue writing and sending weekly news emails to the No Boundaries email distribution list.
* Coordinate quick-turnaround surveys and forward formal surveys at individual members’ and outside researchers’ request.

D. Research* As funds allow, summarize member’s quick-turnaround surveys results and post them on the State of the Practice web page.
* Continue collecting/creating innovations to add to the innovations database.

E. Marketing and Recruitment* Update No Boundaries website with latest program information.
* Create a No Boundaries presentation for a member to give at the National Winter Maintenance and Road Weather Briefing and the AASHTO Committee on Maintenance meeting in July 2025.
 |

**Significant Results:**

|  |
| --- |
| See Progress This Quarter section. |

**Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope and fiscal constraints set forth in the agreement, along with recommended solutions to those problems).**

|  |
| --- |
| None. |

**Potential Implementation:**

|  |
| --- |
| This project provides a forum for State DOTs to share their maintenance innovations with each other, support technology transfer activities and develop marketing and deployment plans for the implementation of selected innovations. Innovative products, practices and policies that CDOT and other member DOTs learn about can be readily tried in the field, piloted and implemented. Members can call upon one another for further information, support and guidance. Such implementation among member states has been documented since No Boundaries’ inception, and it is expected to continue. Moreover, the project’s next-generation database and associated innovation communication tools, now in development, is expected to serve as a hub where innovations and research related to highway maintenance can be found and showcased.FHWA, industry and others (domestic and international) will be invited to participate in the project discussions and activities by presenting or demonstrating innovations. No Boundaries members also attend regional state and national meetings and serve as liaisons with national committees (notably AASHTO and TRB). Further implementation of maintenance innovations among such partners beyond state DOTs is fostered through these relationships. |