**TRANSPORTATION POOLED FUND PROGRAM**

**QUARTERLY PROGRESS REPORT**

|  |  |
| --- | --- |
| Lead Agency (FHWA or State DOT):  | Michigan Department of Transportation |

**INSTRUCTIONS:**

*Lead Agency contacts should complete a quarterly progress report for each calendar quarter during which the projects are active. Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any. List all tasks, even if no work was done during this period.*

|  |  |
| --- | --- |
| **Transportation Pooled Fund Program Project #***(i.e, SPR-2(XXX), SPR-3(XXX) or TPF-5(XXX)**TPF-5(532)* | **Transportation Pooled Fund Program - Report Period:**[x] Quarter 1 (January 1 – March 31)[ ] Quarter 2 (April 1 – June 30)[ ] Quarter 3 (July 1 – September 30)[ ] Quarter 4 (October 1 – December 31) |
| **TPF Study Number and Title:****TPF-5(532)** MAASTO Connected Automated Vehicle (CAV) Steering Committee |
| **Lead Agency Contact:****André D. Clover** | **Lead Agency Phone Number:****517-749-9001** | **Lead Agency E-Mail**clovera@michigan.gov |
| **Lead Agency Project ID:****OR23-309** | **Other Project ID (i.e., contract #):**Click or tap here to enter text. | **Project Start Date:**6/24/2024 |
| **Original Project Start Date:****6/24/2024** | **Original Project End Date:****12/31/2028** | **If Extension has been requested,** **updated project End Date:** Click or tap to enter a date. |

**Project schedule status:**

|  |  |  |  |
| --- | --- | --- | --- |
| [ ] On schedule | [x] On revised schedule | [ ] Ahead of schedule | [ ]  Behind schedule |

**Overall Project Statistics:**

|  |  |  |
| --- | --- | --- |
| **Total Project Budget** | **Total Funds Expended****This Quarter** | **Percentage of Work****Completed to Date** |
| $1,500,000.00 | $0.00 | 0 |

**Project Description:**

|  |
| --- |
| The intended purpose of the proposed TPF study is to support a collaborative research and project consortiumon the topic of CAV technology. There is a need to establish a common strategic direction for advancing CAV’s deployments amongst its member states.  This proposed pooled fund project will focus on movement towardresolution of a common direction for the body of ten states; Illinois, Indiana, Iowa, Kansas, Kentucky, Michigan,Minnesota, Missouri, Ohio, and Wisconsin in the Region. |

**Progress this Quarter**

**(includes meetings, work plan status, contract status, significant progress, etc.):**

|  |
| --- |
| The lead agency is in the process of scoring and securing five vendors under contract to perform services as directed to accomplish the study’s goals and fulfill all identified project objectives approved by the TechnicalAdvisory Committee members (CAV Steering Committee). |

**Anticipated work for next quarter:**

|  |
| --- |
| **Continue to secure the recommended selected vendors under contract.** |

**Significant Results:**

|  |
| --- |
| **NA** |

**Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope and fiscal constraints set forth in the agreement, along with recommended solutions to those problems).**

|  |
| --- |
| **NA** |

|  |
| --- |
|  |

**Potential Implementation:**

**As identified by the CAV Steering Committee members.**