TRANSPORTATION POOLED FUND PROGRAM

QUARTERLY PROGRESS REPORT

Lead Agency (FHWA or State DOT):  ___FHWA Pavement and Materials Team _______________________________________________

INSTRUCTIONS:

Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active.  Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any.  List all tasks, even if no work was done during this period.

| Transportation Pooled Fund Program Project # TPF-5(399) |  | Transportation Pooled Fund Program - Report Period: □Quarter 1 (January 1 – March 31) √ □Quarter 2 (April 1 – June 30) □Quarter 3 (July 1 – September 30) □Quarter 4 (October 1 – December 31) |  |
| --- | --- | --- | --- |
| Project Title: Improve pavement surface distress and transverse profile data collection and analysis, Phase II |  |  |  |
| Name of Project Manager(s): Christy Poon-Atkins | Phone Number: (202) 893-0559 |  | E-Mail Christy.Poon-Atkins@dot.gov |
| Lead Agency Project ID: N/A | Other Project ID (i.e., contract #): N/A |  | Project Start Date: December 17, 2024 |
| Original Project End Date: December 18, 2028 | Current Project End Date: December 18, 2028 |  | Number of Extensions: 0 |

√

Project schedule status:

□ On schedule	□ On revised schedule		□ Ahead of schedule		□ Behind schedule

Overall Project Statistics:

| Total Project Budget | Total Cost to Date for Project | Percentage of Work Completed to Date |
| --- | --- | --- |
| $995,392.00 | $190,185.59 | Time = 13.42%; Money = 19.11% |

Quarterly Project Statistics:

| Total Project Expenses and Percentage This Quarter | Total Amount of Funds Expended This Quarter | Total Percentage of Time Used to Date |
| --- | --- | --- |
| $0 | $0 | $0 |

Project Description: The scope of this work plan is to improve the existing American Association of State Highway and Transportation Officials (AASHTO) R87 rut and cross slope definitions, addressing any identified limitations in the current standard. The revised standard will include clear definitions, guidelines and algorithms for data collection, processing, and analysis. These definitions should balance accuracy with computational efficiency. The ultimate objective for this work plan is to standardize these definitions and algorithms in a robust and consistent manner similar to how IRI is standardized for widespread industry use. In revising the standard practice for collecting transverse pavement profiles, AASHTO R88 will also be updated to align with requirements stipulated in AASHTO PP 106-111 standards along with rutting and cross slope definitions in the revised AASHTO R87.The following tasks outline the planned approach to achieve the objectives. - Task 1 Kick-Off Meeting - The kick-off meeting was completed on December 20, 2024. Based on coordination, the research team met virtually with the project panel on Friday, March 21, 2025, to present some of the findings and facilitate a discussion on critical considerations for improving AASHTO R87 existing rut and cross slope definitions. The Technical Advisory Committee meeting was held in conjunction with the Road Profiler Users Group (RPUG) April 28, 2025, annual meeting Pooled Fund session. - Task 2.1 Quantifying Accuracy Requirements for Rut Depth and Cross Slope Based on End-User Applications - Task 2.2. Vendor Practices and Algorithm Review for Rut Depth and Cross Slope Standardization - Task 2.3. Building a Diverse TPP Database - Task 2.4 Development of Data Collection and Processing Protocols - Task 2.5 Development of Rut Depth and Cross-Slope Calculation Algorithm - Task 2.6 Validation of the Developed Definitions and Algorithms - Task 2.7 Refining the Rut Depth and Cross Slope Definitions and Revising AASHTO R88 - Task 2.8 Prepare the Work Plan for Remaining Items - Task 2.9 Execution of the Work Plan for Remaining Items (Optional Task 2.3 in RFP) - Task 2.10 Prepare the Draft Task 2 Report - Task 2.11 Prepare the Final Task 2 Report - Task 3.1 Conduct preparatory activities to conduct TPP tests - Task 3.2 Conduct TPP tests and assess TPP test procedures - Task 3.3 Prepare Task 3 Documents - Task 4.1 Develop Work Plan - Task 4.2 Execute Work Plan - Task 4.4 Prepare Task 4 Documents - Task 5 Technical Assistance and Analysis to implement products developed within TPF-5(299) / (399) and related to TPF-5(299) / (399) - Task 6 Final Report summarizing the work accomplished in Tasks 2, 3, 4, and 5. - Task 7 Travel and Other Direct Costs Task 2: Develop definitions to meet pavement and safety analyses requirements for rutting and cross slope that are not sensitive to equipment variability, operator use, and pavement deterioration. Additionally, the definitions are expected to be explicitly clear to support software algorithm development and improvements. This task will build upon AASHTO R87 and R88, as each section and subsection must be critically reviewed. The rutting and cross-slope definition validations will rely on using diverse pavement surface data sets. Task 3: Conduct transverse pavement profile (TPP) tests and analyze the results to improve AASHTO Transverse Pavement Profile, rutting, and cross slope Standards. More specifically, the standards that will be continually updated and verified by the AASHTO Technical Subcommittee (TS) 5a include the following. - PP106 – Standard Practice for Assessment of Static Performance in Transverse Pavement Profiling Systems. - PP107 – Standard Practice for Assessment of Body Motion Cancellation in Transverse Pavement Profiling Systems - PP108 – Standard Practice for Assessment of Navigation Drift Mitigation in Transverse Pavement Profiling Systems - PP109 – Standard Practice for Assessment of Highway Performance of Transverse Pavement Profiling Systems. - PP110 – Standard Practice for Assessment of Ground Reference Data for Transverse Pavement Profiling System Assessment - PP111 – Standard Practice for Definition of Terms Related to Transverse Pavement Profiling Systems and Ground Reference Equipment Task 4: Conduct activities such as a literature review, obtain information from industry and transportation agencies, and other activities to develop work plans to assess the feasibility of establishing a publicly accessible annotated quality pavement surface condition image library for developers’ and researchers’ use in developing automated image analysis tools. The image library can be accessed and used by end users, including state DOTs, to access the developer’s analysis tools. This task also includes developing and maintaining the image library functionality with clearly defined library attributes, key processes, and definitions.

Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.): State agency partners: AL, AR, CA, CO, FL, GA, IL, KS, KY, MD, MS, MT, NC, ND, NJ, OH, OR, PA, SD, TN, TX, VA, WA, WI This quarterly report covers the new project scope of work to develop improved rut and cross slope definitions and implement TPF-5(299) products. The objectives identified for TPF-5(299) include: improving the Quality of Pavement Surface Distress and Transverse Profile Data Collection and Analysis. To support this objective, the State DOT partners, FHWA, and industry representatives collaborate to: (1) Identify data collection integrity and quality issues, (2) Identify data analysis needs, (3) Suggest approaches to address identified issues and needs. This project includes focus on applying the TPP data collected to improve the AASHTO standards expected to be used with the State DOT pavement data analysis software. Based on invoices: The billing for activities included in the progress report may not reflect in the same month. Total Contract progress as of March 31, 2025: % Time: 7.19%; % Money: 7.33% - Invoice # P24-3401-3 [Performance Period = April 2025], - Task 2.1 Quantifying Accuracy Requirements for Rut Depth and Cross Slope Based on End-User Applications - 73.4% complete: - Completed contract work to assess cross slope and rut depth information and determine updates to the provisional AASHTO standards in preparation for AASHTO balloting. - Task 3.1 Conduct preparatory activities to conduct TPP tests - 92.33% complete: - A State DOT Transverse Pavement Profile Event coordination template was previously developed. - Task 3.2 Conduct TPP tests and assess TPP test procedures - 0.54%. - Task 4.1 Develop Work Plan - 30.99%. - Task 5 Technical Assistance and Analysis to implement products developed within TPF-5(299) / (399) and related to TPF-5(299) / (399) - 8.98% complete - A presentation for the project status was provided during the April 28, 2025, Road Profile Users Group (RPUG) annual meeting Pooled Fund project Technical Advisory Committee (TAC) meeting. - Task 7 Travel and Other Direct Costs - 10.88%. Total Contract progress as of April 30, 2025: % Time: 9.24%; % Money: 10.79% - Invoice # P24-3401-4 [Performance Period = May 2025], - Task 2.1 Quantifying Accuracy Requirements for Rut Depth and Cross Slope Based on End-User Applications - 83.7% complete: - Completed contract work to assess cross slope and rut depth information and determine updates to the provisional AASHTO standards in preparation for AASHTO balloting. The provisional standards PP106, PP107, PP109, and PP110 were submitted for review on May 21, 2025. The initial round of comments on the noted standards were coordinated on May 28, 2025, and resulted in confirming that PP111 will need to be included with the general update considerations for new terms used in the updated standard procedures. One example of a new term used in PP107 is “consensus plane.” - Task 3.1 Conduct preparatory activities to conduct TPP tests - 94.03% complete: - The biweekly preparation meetings included discussion about the TPP event date and tests, testing location, testing site requirements, TPP Participation to confirm the equipment that will be on-site, Testing, TPP System Requirements / Pretesting submittal, confirmation for the scanning vendor, surveying, points of contact, confirm testing site address, confirm other invitees. - Task 3.2 Conduct TPP tests and assess TPP test procedures - 1.48%. - As outlined in the contract, the Contractor assessed the test procedures quality, practicality in conducting the tests, based on the host state testing location. The Contractor verified potential improvements to better meet the test objectives with the minimum resources. The determinations were discussed as part of the pre-testing coordination meetings. - Task 4.1 Develop Work Plan - 56.83%. - Based on the contract, activities such as literature review, information from industry and transportation agencies, and other activities to develop work plan were on-going. The work plan is to help assess the feasibility of establishing publicly accessible reference quality annotated pavement surface condition image library for developers/researchers use in developing automated image analysis tools. - Task 5 Technical Assistance and Analysis to implement products developed within TPF-5(299) / (399) and related to TPF-5(299) / (399) - 22.50% complete - Based on the contract, the Contractor provided assessments of different analysis approaches, on-site and/or remote technical assistance and analysis to State DOTs and their agents relating to implementation of TPF-5(299)/(399) products and other products/technology related to TPF-5(299)/(399). The provisional standard being prepared for balloting were further coordinated in preparation for submittal to the AASHTO Technical Subcommittee (TS) 5a. - On May 30, 2025, a copy of the provisional standards PP106, PP107, PP108, PP109, and PP110 along with TPP Pre-Testing requirements, and the Montana DOT TPP Assessment Event form were shared with project contacts. - Task 7 Travel and Other Direct Costs - 14.46%. - There were travel reimbursements for the April 28, 2025, Road Profile Users Group (RPUG) annual meeting Pooled Fund project Technical Advisory Committee (TAC) meeting was processed with Invoice P24-3401-4. Total Contract progress as of May 31, 2025: % Time: 11.4%; % Money: 14.97% - Invoice # P24-3401-5 [Performance Period = June 2025]. - Task 1 Kick-Off Meeting - 100.00%. - The task was closed-out by the contractor with final billing for the task completed on July 14, 2025. - Task 2.1 Quantifying Accuracy Requirements for Rut Depth and Cross Slope Based on End-User Applications - 97.1% complete: - Contractor update. - Task 3.1 Conduct preparatory activities to conduct TPP tests - 97.05% complete: The biweekly preparation meetings included discussion about the TPP event date and tests, testing location, testing site requirements, TPP Participation to confirm the equipment that will be on-site, Testing, TPP System Requirements / Pretesting submittal, confirmation for the scanning vendor, surveying, points of contact, confirm testing site address, confirm other invitees. - Task 3.2 Conduct TPP tests and assess TPP test procedures - 8.17%. - As outlined in the contract, the Contractor assessed the test procedures quality, practicality in conducting the tests, based on the host state testing location. The Contractor verified potential improvements to better meet the test objectives with the minimum resources. The determinations were discussed as part of the pre-testing coordination meetings. - Task 4.1 Develop Work Plan - 75.03%. - Contractor updates. - Technical Subcommittee (TS) 5a for balloting on June 9, 2025. - The Florida DOT TPP Assessment Event was held June 10-11, 2025. - The contractor is continuing preparation for the Montana TPP Testing Event. Total Contract progress as of June 30, 2025: % Time: 13.42%; % Money: 19.11% - Invoice # P24-3401-6 [Performance Period = June 1, 2025 – June 30, 2025], - Task 3.2 Conduct TPP tests and assess TPP test procedures - 8.97% The contractor completed the following activities. - Analyzed Florida DOT and Vendor data from the June 2025 Florida TPP event utilizing 2025 PP 106 to PP 110 AASHTO Standards. Also, analyzed Florida TPP event data utilizing AASHTO 2026 revisions to provide comparisons. Additional analysis of TPP vendor data from 2024 events was performed to troubleshoot/analyze skewness in vendor data. - Analyzed Florida TPP Data using the revised Navigation Drift Reference Object. - Began analyzing Florida TPP data using the revised Macrotexture Reference Object. - Task 7 Travel and Other Direct Costs - 18.18%. - Delayed Florida TPP testing travel billing by the sub-contractor. Total Contract progress as of June 30, 2025: % Time: 15.54%; % Money: 19.55%

Anticipated work next quarter: The work anticipated for next quarter includes TPP testing in Montana during the week of September 22, 2025. The Montana TPP Testing Event expects to include Idaho DOT and Washington State DOT.

Significant Results: The significant results for the project work completed thus far is related to completing the initial updates to the standards. The updated standards, including PP106, PP107, PP109, PP110, and PP111 were submitted to AASHTO Technical Subcommittee (TS) 5a on June 9, 2025. The AASHTO balloting process resulting in the updated standards being approved. The approved standards were included in the release of the AASHTO Standard Specifications for Transportation Materials and Methods of Sampling and Testing, August 8, 2025, 45th Edition. Furthermore, the standards are now referred to as PP 106-25, PP 107-25, PP 108-25, PP 109-25, PP 110-25, and PP 111-25. Furthermore, PP 107-25 and PP 108-25 are available for use in the pavement analysis software for piloting under TPF-5(354), as planned.

Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope and fiscal constraints set forth in the agreement, along with recommended solutions to those problems). A focus for the project scope of work includes processing standards based on transverse pavement profile (TPP) testing results collected during planned State DOT TPP Testing Events. In the TPF-5(399) Work Plan, Task 2.3, Building a Diverse TPP Database, the plan indicates that several DOTs have indicated interest in providing samples to the contractor. The State DOTs noted in the work plan include Texas, Washington, North Carolina, Virginia, Georgia, New Hampshire, North Dakota, Massachusetts, Ohio, and Oregon. As of June 30, 2025, the project contractor has completed TPP testing for the first event that was scheduled with Florida DOT (FDOT) as the host state. The FDOT TPP Testing event was held on June 10 – 11, 2025. Additionally, the contractor has confirmed that the next TPP testing location will be Montana. For the Montana DOT TPP Event, the states that expect to participate include Idaho, Washington, and possibly North Dakota

Potential Implementation: The planned implementation for the standards updated through this project include merging the standards into the pavement analysis software developed under TPF-5(354), Improving the Quality of Highway Profile Measurement, led by South Dakota DOT. The first standards planned for pilot implementation are PP107 and PP108.