TRANSPORTATION POOLED FUND PROGRAM

QUARTERLY PROGRESS REPORT

Lead Agency (FHWA or State DOT):  ___FHWA Pavement and Materials Team _______________________________________________

INSTRUCTIONS:

Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active.  Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any.  List all tasks, even if no work was done during this period.

| Transportation Pooled Fund Program Project # TPF-5(399) |  | Transportation Pooled Fund Program - Report Period: □Quarter 1 (January 1 – March 31) √ □Quarter 2 (April 1 – June 30) □Quarter 3 (July 1 – September 30) □Quarter 4 (October 1 – December 31) |  |
| --- | --- | --- | --- |
| Project Title: Improve pavement surface distress and transverse profile data collection and analysis, Phase II |  |  |  |
| Name of Project Manager(s): Christy Poon-Atkins | Phone Number: (202) 893-0559 |  | E-Mail Christy.Poon-Atkins@dot.gov |
| Lead Agency Project ID: N/A | Other Project ID (i.e., contract #): N/A |  | Project Start Date: December 17, 2024 |
| Original Project End Date: December 18, 2028 | Current Project End Date: December 18, 2028 |  | Number of Extensions: 0 |

√

Project schedule status:

□ On schedule	□ On revised schedule		□ Ahead of schedule		□ Behind schedule

Overall Project Statistics:

| Total Project Budget | Total Cost to Date for Project | Percentage of Work Completed to Date |
| --- | --- | --- |
| $995,392.00 | $268,779.48 | Time = 19.71%; Money = 27.00% |

Quarterly Project Statistics:

| Total Project Expenses and Percentage This Quarter | Total Amount of Funds Expended This Quarter | Total Percentage of Time Used to Date |
| --- | --- | --- |
| $0 | $0 | $0 |

Project Description: The scope of this work plan is to improve the existing American Association of State Highway and Transportation Officials (AASHTO) R87 rut and cross slope definitions, addressing any identified limitations in the current standard. The revised standard will include clear definitions, guidelines and algorithms for data collection, processing, and analysis. These definitions should balance accuracy with computational efficiency. The ultimate objective for this work plan is to standardize these definitions and algorithms in a robust and consistent manner similar to how IRI is standardized for widespread industry use. In revising the standard practice for collecting transverse pavement profiles, AASHTO R88 will also be updated to align with requirements stipulated in AASHTO PP 106-111 standards along with rutting and cross slope definitions in the revised AASHTO R87.The following tasks outline the planned approach to achieve the objectives. - Task 1 Kick-Off Meeting - The kick-off meeting was completed on December 20, 2024. Based on coordination, the research team met virtually with the project panel on Friday, March 21, 2025, to present some of the findings and facilitate a discussion on critical considerations for improving AASHTO R87 existing rut and cross slope definitions. The Technical Advisory Committee meeting was held in conjunction with the Road Profiler Users Group (RPUG) April 28, 2025, annual meeting Pooled Fund session. - Task 2.1 Quantifying Accuracy Requirements for Rut Depth and Cross Slope Based on End-User Applications - Task 2.2. Vendor Practices and Algorithm Review for Rut Depth and Cross Slope Standardization - Task 2.3. Building a Diverse TPP Database - Task 2.4 Development of Data Collection and Processing Protocols - Task 2.5 Development of Rut Depth and Cross-Slope Calculation Algorithm - Task 2.6 Validation of the Developed Definitions and Algorithms - Task 2.7 Refining the Rut Depth and Cross Slope Definitions and Revising AASHTO R88 - Task 2.8 Prepare the Work Plan for Remaining Items - Task 2.9 Execution of the Work Plan for Remaining Items (Optional Task 2.3 in RFP) - Task 2.10 Prepare the Draft Task 2 Report - Task 2.11 Prepare the Final Task 2 Report - Task 3.1 Conduct preparatory activities to conduct TPP tests - Task 3.2 Conduct TPP tests and assess TPP test procedures - Task 3.3 Prepare Task 3 Documents - Task 4.1 Develop Work Plan - Task 4.2 Execute Work Plan - Task 4.4 Prepare Task 4 Documents - Task 5 Technical Assistance and Analysis to implement products developed within TPF-5(299) / (399) and related to TPF-5(299) / (399) - Task 6 Final Report summarizing the work accomplished in Tasks 2, 3, 4, and 5. - Task 7 Travel and Other Direct Costs Task 2: Develop definitions to meet pavement and safety analyses requirements for rutting and cross slope that are not sensitive to equipment variability, operator use, and pavement deterioration. Additionally, the definitions are expected to be explicitly clear to support software algorithm development and improvements. This task will build upon AASHTO R87 and R88, as each section and subsection must be critically reviewed. The rutting and cross-slope definition validations will rely on using diverse pavement surface data sets. Task 3: Conduct transverse pavement profile (TPP) tests and analyze the results to improve AASHTO Transverse Pavement Profile, rutting, and cross slope Standards. More specifically, the standards that will be continually updated and verified by the AASHTO Technical Subcommittee (TS) 5a include the following: - PP106 – Standard Practice for Assessment of Static Performance in Transverse Pavement Profiling Systems. - PP107 – Standard Practice for Assessment of Body Motion Cancellation in Transverse Pavement Profiling Systems. - PP108 – Standard Practice for Assessment of Navigation Drift Mitigation in Transverse Pavement Profiling Systems. - PP109 – Standard Practice for Assessment of Highway Performance of Transverse Pavement Profiling Systems. - PP110 – Standard Practice for Assessment of Ground Reference Data for Transverse Pavement Profiling System Assessment. - PP111 – Standard Practice for Definition of Terms Related to Transverse Pavement Profiling Systems and Ground Reference Equipment. Task 4: Conduct activities such as a literature review, obtain information from industry and transportation agencies, and other activities to develop work plans to assess the feasibility of establishing a publicly accessible annotated quality pavement surface condition image library for developers’ and researchers’ use in developing automated image analysis tools. The image library can be accessed and used by end users, including state DOTs, to access the developer’s analysis tools. This task also includes developing and maintaining the image library functionality with clearly defined library attributes, key processes, and definitions.

Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.): State agency partners: AL, AR, CA, CO, FL, GA, IL, KS, KY, MD, MS, MT, NC, ND, NJ, OH, OR, PA, SD, TN, TX, VA, WA, WI This quarterly report covers the new project scope of work to develop improved rut and cross slope definitions and implement TPF-5(299) products. The objectives identified for TPF-5(299) include: improving the Quality of Pavement Surface Distress and Transverse Profile Data Collection and Analysis. To support this objective, the State DOT partners, FHWA, and industry representatives collaborate to: (1) Identify data collection integrity and quality issues, (2) Identify data analysis needs, (3) Suggest approaches to address identified issues and needs. This project includes focus on applying the TPP data collected to improve the AASHTO standards expected to be used with the State DOT pavement data analysis software. Based on invoices: The billing for activities included in the progress report may not reflect in the same month. Total Contract progress as of June 30, 2025: % Time: 15.54%; % Money: 19.55% - Invoice # P24-3401-7 [Performance Period: July 2025], - Task 2.1 Develop Work Plan [Quantifying Accuracy Requirements for Rut Depth and Cross Slope Based on End-User Applications] - 100.00% complete: - The research team had a meeting with the project panel in July 2025 to discuss the work plan. The final work plan was submitted in July 2025. - Task 2.2. Execute Work Plan [Vendor Practices and Algorithm Review for Rut Depth and Cross Slope Standardization] - 1.2% complete: - Developed two questionnaires on cross-slope and rutting, distributed to the 24 pooled fund agencies as well as to agencies not participating in the pooled fund. All 24 pooled fund agencies responded to the rutting questionnaire, 15 responded to the cross-slope questionnaire, and 8 agencies outside the pooled fund also provided responses. The research team is compiling and summarizing these responses as part of Subtask 1. - Developed a vendor questionnaire and received responses from Pavemetrics, Fugro, Pathway, ICC, Cyclomedia, SSI, and AMES. The information is being compiled and summarized as part of Subtask 2. - Task 3.2 Conduct TPP tests and assess TPP test procedures - 13.60%. - Analyzed TPP Data using improved alignment of TPP and GRE data and path coordinates. - Task 4.1 Develop Work Plan - 100.00%. - Contractor updates. QES completed the work plan in June and presented it to the panel in July. - Task 5 Technical Assistance and Analysis to implement products developed within TPF-5(299) / (399) and related to TPF-5(299) / (399) - 30.85% complete - Improvement to PP 109 regarding strip creation and alignment of GRE and TPP Data for cross slope and rut depth. - Analysis of Florida TPP Vendor data to correct data skewness. Correction was needed to analyze the TPP data. - Task 7 Travel and Other Direct Costs - 24.32%. - There were advanced travel payments for the September 22, 2025, Montana TPP Testing Event. Total Contract progress as of July 31, 2025: % Time: 15.54%; % Money: 23.00% - Invoice # P24-3401-8 [August 2025], - Task 2.2. Execute Work Plan [Vendor Practices and Algorithm Review for Rut Depth and Cross Slope Standardization] - 4.4% complete: - Developed a condition matrix to support the creation of a diverse Transverse Pavement Profile (TPP) database. The matrix is designed to capture the full spectrum of conditions that influence transverse profile shapes and will be used in Subtask 3 to guide obtaining data from agencies and vendors. - Task 3.2 Conduct TPP tests and assess TPP test procedures - 16.11%. - Held Montana DOT planning meetings/performed preparatory work for the Montana TPP Event. - Plan to conduct the Montana DOT TPP event the week of September 22, 2025, in Helena, Montana. - Task 5 Technical Assistance and Analysis to implement products developed within TPF-5(299) / (399) and related to TPF-5(299) / (399) - 32.37% complete - Modified the PP109 algorithm so that Vendor TPP data is converted to Path Coordinates. - Conducting literature review to improve AASHTO PP 106-111. - Task 7 Travel and Other Direct Costs - 25.74%. - There were other direct costs for TPP Assessment Events Equipment (Gauge blocks & 144” straight edge). Total Contract progress as of August 31, 2025: % Time: 17.65%; % Money: 24.52% - Invoice # P24-3401-9 [September 2025], - Task 2.2. Execute Work Plan [Vendor Practices and Algorithm Review for Rut Depth and Cross Slope Standardization] - 7.0% complete: - Developed a condition matrix to support the creation of a diverse Transverse Pavement Profile (TPP) database. The matrix is designed to capture the full spectrum of conditions that influence transverse profile shapes and will be used in Subtask 3 to guide obtaining data from agencies and vendors. - Task 3.2 Conduct TPP tests and assess TPP test procedures - 20.43%. - Held a final Montana DOT planning meetings/performed preparatory work for the Montana TPP Event. - Conducted the Montana DOT TPP event during the week of September 22, 2025, in Helena, Montana. - Task 3.3 Prepare Task 3 Documents - 6.73%. - Preparing a report documenting Task 3 activities, findings, conclusions, and recommendations, based on Florida and Montana TPP Testing Events. - Task 4.2 Execute Work Plan - 15.89%. - Preparing to present findings, items requiring further investigation, and recommendations to the oversight panel / Technical Advisory Committee. A meeting for the Florida results is being planned for the week of October 27, 2025. - Task 5 Technical Assistance and Analysis to implement products developed within TPF-5(299) / (399) and related to TPF-5(299) / (399) - 36.57% complete - Providing assessments of analysis approaches, as needed for the Montana TPP testing event. - Task 7 Travel and Other Direct Costs - 27.00%. - Travel costs for the Montana TPP Testing Event. Total Contract progress as of September 30, 2025: % Time: 19.71%; % Money: 27.00%

Anticipated work next quarter: Ongoing work on improving rut and cross slope definition. Preparing for transverse profiler pavement assessment testing. Developing work for feasibility study to create a reference quality annotated image library for AI/ML applications. Activities planned for Quarter 4 (October 1, 2025 – December 31, 2025) - Presentation for the Florida DOT TPP Event observations and results summary report out meeting. The meeting is planned to be scheduled for the week of October 27, 2025. - Presentation for the Montana DOT TPP Event observations and results summary report out meeting. The meeting is planned to be scheduled during the week of (TBD). - Coordinate a meeting with the TPF-5(354) project team to verify assistance needs for progress on incorporating PP 107-25 and PP 108-25 into modules for the pavement analysis software. - Confirm and schedule a TPP Testing Event with an interested state agency partner. The state agency partner participants are to be determined and confirmed.

Significant Results: The significant results for the project work completed thus far is related to completing the initial updates to the standards. The updated standards, including PP106, PP107, PP109, PP110, and PP111 were submitted to AASHTO Technical Subcommittee (TS) 5a on June 9, 2025. The AASHTO balloting process resulting in the updated standards being approved. The approved standards were included in the release of the AASHTO Standard Specifications for Transportation Materials and Methods of Sampling and Testing, August 8, 2025, 45th Edition. Furthermore, the standards are now referred to as PP 106-25, PP 107-25, PP 108-25, PP 109-25, PP 110-25, and PP 111-25. Furthermore, PP 107-25 and PP 108-25 are available for use in the pavement analysis software for piloting under TPF-5(354), as planned. Task 2 (TPP Study): The QES team began executing the work plan in August 2025. As part of this effort, the research team designed two questionnaires, one focused on cross-slope and the other on rutting which were distributed to all 24 pooled fund agencies. In parallel, the QES developed a vendor questionnaire, which was distributed to TPP vendors. Responses for both surveys were received and QES is currently compiling and summarizing this information for presentation to the oversight panel / Technical Advisory Committee. Task 3 (Rut Definition Study): QES conducted two Transverse Pavement events and continues to analyze event data using the 2025 AASHTO Standards. Additional analysis is ongoing to analyze TPP event data using the proposed 2026 AASHTO Standards and to incorporate revisions into TPP algorithms. Revisions to algorithms were made to allow an automative procedure to align the TPP and ground reference data sets as well as to transform GPS coordinates provided in TPP data into path coordinates. Task 4 (AI Reference Library Study): The final work plan was submitted to FHWA and participating State DOT panel staff. The QES team held a meeting with FHWA staff and State DOT panel members to review the final work plan. The State DOT panel members approved the plan. During the month of August, QES worked with FHWA staff to begin execution of the work plan. QES and FHWA staff developed a questionnaire for distribution to select DOTs to determine current requirements and existing QC/QA practices. FHWA staff performed an internal review of preliminary findings. Based on feedback and questions from FHWA staff, QES presented “typical QC/QA processes” to FHWA staff. Based on the results of interviews and the QES presentation, follow-up questions for the DOTs were developed.

Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope and fiscal constraints set forth in the agreement, along with recommended solutions to those problems). A focus for the project scope of work includes processing standards based on transverse pavement profile (TPP) testing results collected during planned State DOT TPP Testing Events. In the TPF-5(399) Work Plan, Task 2.3, Building a Diverse TPP Database, the plan indicates that several DOTs have indicated interest in providing samples to the contractor. The State DOTs noted in the work plan include Texas, Washington, North Carolina, Virginia, Georgia, New Hampshire, North Dakota, Massachusetts, Ohio, and Oregon. As of June 30, 2025, the project contractor has completed TPP testing for the first event that was scheduled with Florida DOT (FDOT) as the host state. The FDOT TPP Testing event was held on June 10 – 11, 2025. As of September 30, 2025, the project contractor completed TPP testing for the second event for September 23 in Montana. For states previously scheduled to participate in the Montana DOT TPP Event, there were cancellations. The states that did not participate as planned include Idaho, Washington, and North Dakota. The TPP testing was performed with Montana DOT only who provided two TPP’s.

Potential Implementation: The planned implementation for the standards updated through this project include merging the standards into the pavement analysis software developed under TPF-5(354), Improving the Quality of Highway Profile Measurement, led by South Dakota DOT. The first standards planned for pilot implementation are PP107 and PP108.