Pooled Fund Quarterly Report

For July-September 2025

Submitted by:  Daniel E. Jenkins, PE

Data collection for the 2024 core survey began on November 1, 2024 and will continue through November 2025.  We finalized documents (statement of work and independent cost estimate) to procure the New Era (2026/2027) core survey data.  The current plan for the New Era data collection is to cover 7,500 national households with our pooled fund participants surveying up to 40,000 additional households.  We held a technical advisory committee meeting in September in Detroit, MI to update members on the some of the preliminary findings of the 2024 survey thus far and to seek their input on their data needs for the 2026/2027  NHTS.