TRANSPORTATION POOLED FUND PROGRAM

QUARTERLY PROGRESS REPORT

Lead Agency (FHWA or State DOT):  ___FHWA_____________________________________

INSTRUCTIONS:

Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active.  Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any.  List all tasks, even if no work was done during this period.

| Transportation Pooled Fund Program Project # TPF-5(475) |  | Transportation Pooled Fund Program - Report Period: □ Quarter 1 (January 1 – March 31) □ Quarter 2 (April 1 – June 30) □ Quarter 3 (July 1 – September 30) X Quarter 4 (October 1 – December 31) |  |
| --- | --- | --- | --- |
| Project Title: ## Update Precipitation Frequency Estimates for Delaware, Maryland, North Carolina, Virginia, Pennsylvania, and South Carolina (NOAA Atlas 14, Vol. 13) |  |  |  |
| Name of Project Manager(s): Megan Frye | Phone Number: (303) 396-9847 |  | E-Mail megan.frye@dot.gov |
| Lead Agency Project ID: FHWA | Other Project ID (i.e., contract #): |  | Project Start Date: March 19, 2021 |
| Original Project End Date: June 2024 | Current Project End Date: June 2026 |  | Number of Extensions: |

Project schedule status:

□ On schedule	□ On revised schedule		□ Ahead of schedule		X Behind schedule

Overall Project Statistics:

| Total Project Budget | Total Cost to Date for Project | Percentage of Work Completed to Date |
| --- | --- | --- |
| $1,802,000 | $1,586,128 | 88% |

Quarterly Project Statistics:

| Total Project Expenses and Percentage This Quarter | Total Amount of Funds Expended This Quarter | Total Percentage of Time Used to Date |
| --- | --- | --- |
| $188,100 / 10% | $188,100 | 90% |

Project Description: The purpose of this project is to update precipitation frequency estimates for Delaware, Maryland, North Carolina, Virginia, Pennsylvania, and South Carolina published in NOAA Atlas 14 Volume 2. Like previous NOAA Atlas 14 volumes, the estimates and associated bounds of 90% confidence intervals will be provided at 30 arc-sec resolution for durations of 5-minute through 60-day at average recurrence intervals (ARIs) of 1-year through 1,000-year. The study results will be published as NOAA Atlas 14 Volume 13, a wholly web-based publication available at Precipitation Frequency Data Server (PFDS). The publication will include the artifacts provided in previous NOAA Atlas 14 Volumes, including access through the PFDS, base grids in standard formats together with error estimates, electronic copies of maps, charts of seasonal distributions and probabilistic temporal distributions of heavy precipitation, and detailed documentation. Updated areal reduction factors, which are needed to calculate analogous areal precipitation frequency estimates, will not be developed as a part of this project.

Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.): In this reporting period, NOAA began consolidating and reviewing the peer review responses. As a result of the public feedback, they have identified additional datasets to enhance mountains and coastal areas spatial patterns and data reliance, such as IFLOWS/HADS and the Duke University Great Smoky Mountain Rain Gauge Network. In this reporting period, IFLOWS/HADS outliers have been manually quality controlled, and the data was added to the analysis. Additional information on the status of the Atlas 14, Volume 13 work is available at: https://www.weather.gov/owp/hdsc_current_projects

Anticipated work next quarter: In the next quarter, NOAA will work on finalizing quality control of AMS data for all durations, completing the spatial review of mean annual maximum grids and beginning the revision of the final PF estimates for all durations. NOAA will address comments received from reviewers and work on developing the final precipitation frequency estimates and documentation.

Significant Results: Peer Review: NOAA consolidated comments, reviewed them, and started to address them accordingly. The (anonymous) reviewers’ comments with responses and resulting actions will be published as an Appendix 4 in the Volume 13 document. Mean annual maximum precipitation development During this reporting period, NOAA started reviewing for inconsistencies resulting from stations that may have had less reliable sampling (shorter record or missed several heavy events) relative to nearby stations or any inconsistent areas unduly influenced by the interpolation process or a lack of stations. The development of final gridded MAM estimates will require several iterations with the Atlas 15 contractor. In the process, NOAA reviewed MAM data for each station for inconsistencies relative to MAMs at nearby stations to identify locations where MAMs are affected by short periods of record or missed extreme amounts. Flagged MAMs were investigated and either adjusted or removed from the analysis. Additional Data Formatting – Additional observational networks, the Hydrometeorological Automated Data System (HADS) and Integrated Flood Observing and Warning System (IFLOWS), located along the Appalachian Mountains were investigated, collected, and formatted to enhance the accuracy of estimates in areas where preliminary hourly data has been scarce. In this reporting period, this data was auto-merged to extend the record at the locations where NOAA lack the data.

Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope and fiscal constraints set forth in the agreement, along with recommended solutions to those problems). Delay in finalizing the IAA with NOAA. Estimated timeline to complete the work is early 2026 now. Current schedule: - Data collection, formatting, and initial quality control [Q4 2024; Completed] - Extraction of annual maximum series (AMS); additional quality control and data reliability tests (e.g., outliers, independence, consistency across durations, duplicate stations, candidates for merging)] [Q1 2025; Completed] - Regionalization and frequency analysis [Q1 2025; Completed] - Initial spatial interpolation of precipitation frequency (PF) estimates and consistency checks across durations [Q2 2025; Completed] - Peer review [Q3 2025; Completed] - Revision of PF estimates [Q1 2026, In progress] - Remaining tasks (e.g., development of precipitation frequency estimates for partial duration series, seasonality, temporal distributions, documentation) [Q2 2026, In progress] - Web publication [Q2 2026]

Potential Implementation: All deliverables will be accessible through the Precipitation Frequency Data Server (PFDS). That includes: - Interactive map of the United States. Via this map, IDF/DDF tables and curves will be available for any location in the project area. - Precipitation frequency grids in GIS compatible formats. - Metadata in Federal Geographic Data Transfer Standard format. - Cartographic maps of precipitation frequency estimates. - Charts of the seasonal distribution of annual maxima - Probabilistic temporal distributions for 6-hour, 12-hour, 24-hour, and 96-hour durations in both chart and digital form - Rainfall frequency estimates with corresponding upper and lower bounds of 90% confidence intervals will be available at 30-arc sec grid for durations of 1, 2, 3, 6, 12 and 24 hours.