TRANSPORTATION POOLED FUND PROGRAM

QUARTERLY PROGRESS REPORT

Lead Agency (FHWA or State DOT):  Oregon Department of Transportation

INSTRUCTIONS:

Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active.  Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any.  List all tasks, even if no work was done during this period.

| Transportation Pooled Fund Program Project # (i.e, SPR-2(XXX), SPR-3(XXX) or TPF-5(XXX) TPF-5(524) |  | Transportation Pooled Fund Program - Report Period: □Quarter 1 (January 1 – March 31) X □Quarter 2 (April 1 – June 30) □Quarter 3 (July 1 – September 30) □Quarter 4 (October 1 – December 31) |  |
| --- | --- | --- | --- |
| Project Title: Stormwater Management to Address Highway Runoff Toxicity Due to 6PPD-Quinone from Tire Rubber |  |  |  |
| Name of Project Manager(s): Kira Glover-Cutter | Phone Number: 971.701.0051 |  | E-Mail: kira.m.glover-cutter@odot.oregon.gov |
| Lead Agency Project ID: RFI - 00081678 - 6PPD-Q Stormwater | Other Project ID (i.e., contract #): |  | Project Start Date: January 2024 |
| Original Project End Date: 2028 | Current Project End Date: 2028 |  | Number of Extensions: na |

Project schedule status:

□ On schedule	□ On revised schedule		□ Ahead of schedule		 □ X Behind schedule

Overall Project Statistics:

| Total Project Budget | Total Cost to Date for Project | Percentage of Work Completed to Date |
| --- | --- | --- |
| $1.08M | $144,146 | 13% |

Quarterly Project Statistics:

| Total Project Expenses and Percentage This Quarter | Total Amount of Funds Expended This Quarter | Total Percentage of Time Used to Date |
| --- | --- | --- |
| $144,146 | $144,146 | 13% |

Project Description: This research aims to equip DOTs with a targeted approach for effectively managing 6PPD-q in highway runoff by 1) developing methods/criteria for identifying locations that need focused treatment, 2) developing a better understanding of the fate and transport of 6PPD and 6PPD-q, 3) developing cost-effective design guidance for stormwater treatment and management techniques with a focus on reducing the effects of 6PPD-q on receiving waters, and 4) evaluating the degree of 6PPD-q release from pavement products made from recycled tire materials. This research will also assist with providing regulatory agencies with a better understanding of DOT management options including the feasibility, limitations, and effectiveness of treatment methods.

Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.): - Contract with USGS Fully Executed, Oregon site nearly completely instrumented, Washington and California sites selected with instrumentation in progress. Planning for data collection for MA soon. While budget spent has not changed, this is due to not yet receiving invoice for work performed. Will update this quarterly report once paid. TAC meeting in March to review proposed amendment changes highlighted below.

X

Anticipated work next quarter: - Complete instrumentation, start calibration of equipment, initiate Massachusetts data collection. Once CA, OR, WA sites instrumented and calibrated, will start data collection in WY27 Sept/October due to delay for the WY26 from the Federal shutdown. Adjusted amendment that reflects the time lost from the federal shutdown is needed and in progress.

Significant Results: na

Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope and fiscal constraints set forth in the agreement, along with recommended solutions to those problems). na

Potential Implementation: After TAC meeting and FHWA input refocused and slimmed down version of SOW deliverables will include: 1) 6PPD-Q focused highway runoff database and assessment of the performance of commonly used, low-cost and low-maintenance BMPs by implementing high-quality field-based monitoring approaches for six nationwide locations (California (2), Massachusetts (2), Oregon (1), Washington (1)). Each location will have site specific parameters that will be included in the database, and the site-specific performance of the BMP will also be assessed. 2) Monitoring of runoff and BMP performance at a location that incorporates recycled tire products, together with a control location that does not contain recycled tire material is also integrated in this scope of work. 3) To supplement this 6PPD research monitoring effort and support potential future needs of state DOTs, the USGS will also perform a complementary research effort to assess low-cost proxy methods for quantifying 6PPD-Q.