TRANSPORTATION POOLED FUND PROGRAM

QUARTERLY PROGRESS REPORT

Lead Agency (FHWA or State DOT):  ______FHWA_______________________________________

INSTRUCTIONS:

Lead Agency contacts should complete a quarterly progress report for each calendar quarter during which the projects are active.  Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any.  List all tasks, even if no work was done during this period.

| Transportation Pooled Fund Program Project # TPF-5(554) |  | Transportation Pooled Fund Program - Report Period: ýQuarter 1 (January 1 – March 31) □Quarter 2 (April 1 – June 30) □Quarter 3 (July 1 – September 30) □Quarter 4 (October 1 – December 31) |  |
| --- | --- | --- | --- |
| TPF Study Number and Title: TPF-5(554) Traffic Control Devices Pooled Fund Study |  |  |  |
| Lead Agency Contact: Laura Mero, FHWA | Lead Agency Phone Number: (202) 493-3377 |  | Lead Agency E-Mail Laura.Mero@dot.gov |
| Lead Agency Project ID: TPF-5(554) | Other Project ID (i.e., contract #): |  | Project Start Date: February 27, 2025 |
| Original Project Start Date: October 1, 2002 | Original Project End Date: N/A Continuing Effort |  | If Extension has been requested, updated project End Date: |

Project schedule status:

On schedule	□ On revised schedule		□ Ahead of schedule		□ Behind schedule

Overall Project Statistics:

| Total Project Budget | Total Funds Expended This Quarter | Percentage of Work Completed to Date |
| --- | --- | --- |
| Values indicate total commitments 2016 – $325,000 2017 – $375,000 2018 – $290,000 2019 – $335,000 2020 – $335,000 2021 – $405,000 2022 – $440,000 2023 - $395,000 | Ongoing Project (N/A) | Ongoing Project (N/A) |

Project Description: The purpose of the TCD PFS is to assemble a consortium composed of regional, State, local entities, appropriate organizations and the FHWA to 1) establish a systematic procedure to select, test, and evaluate approaches to novel TCD concepts as well as incorporation of results into the MUTCD; 2) select novel TCD approaches to test and evaluate; 3) determine methods of evaluation for novel TCD approaches; 4) initiate and monitor projects intended to address evaluation of the novel TCDs; 5) disseminate results; and 6) assist MUTCD incorporation and implementation of results.

Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.): ## Traffic Control Devices Pooled Fund Study Technical Support - Attended bi-weekly meeting with the TOCOR to discuss the status of the action items and activities under the task order (1/15/2026, 1/29/2026, 2/12/2026, 2/27/2026, 3/12/2026 and 3/26/2026) - Drafted and finalized the 2026 milestones and deliverables schedule. - Provided monthly progress reports to the TOCOR. - Submitted the draft Quarterly Report for Q4. Revised the quarterly report based on feedback from the TOCOR and uploaded the final Q4 Quarterly Report to the PFS website. - Updated the contact list as appropriate and requested changes to email list and Teams. Sent welcome emails to new representatives or members. - Finalized the Q4 meeting minutes and distributed them to the TCD PFS members. - Scheduled the Q1 meeting. Drafted, finalized, and distributed the Q1 agenda and prepared slides and virtual whiteboard. Helped facilitate the Q1 meeting and drafted meeting minutes. - Notified members of the voting results for the Annual Meeting region and began conducting cost estimates for multiple locations within that region. Reviewed initial cost estimate findings with the TOCOR and started gathering availability from hotels and requesting A/V cost estimates. Selected dates for the Annual Meeting. - Informed TCD PFS members of the results of the project selection process. Created a new sheet for 2026 in the research idea tracking spreadsheet and began adding ideas from members to the spreadsheet. - Initiated the TTC Guide Sign Color state-of-practice review and gathered availability for an informal kickoff meeting with the PFS project champion and the TOCOR. - Discussed with the TCD PFS members the concept of adding language on the voting process to the Charter. Pedestrian Signing at Unsignalized Crossings - Responded to comments regarding the project findings and tech transfer activities. - Submitted quarterly progress report. Comprehension and Legibility of Selected Symbol Signs Phase V - Attended bi-weekly meetings with the TOCOR to discuss project activities. - Supported round 4 and 5 of editorial review. - Supported round 1 and round 2 of layout review. Evaluation of Pavement Markings in Merge Areas - Attended bi-weekly meetings with the TOCOR to discuss project activities. - Completed data analysis for the laboratory study. - Identified State DOTs who are interested in volunteering for the field study. - Discussed potential sites with select states. Temporary Traffic Control Advance Warning Sign Placement - Attended bi-weekly meetings with the TOCOR to discuss project activities. - Completed a literature review. - Conducted an online state-of-practice review. Drafted, finalized, and distributed a practitioner feedback form as part of the state-of-practice review. - Submitted the draft work plan on 02/26/2026. - Revised the work plan based on comments received from the PFS members. - Summarized additional responses from the practitioner feedback form and included an updated summary in the revised work plan. - Developed an interview guide for follow-up practitioner interviews and discussed procedures for interviews (e.g., pre-review of questionnaire responses and State-specific documentation of practice to identify targeted interview questions before the interviews). Drafted outreach email for scheduling interviews. Continued reviewing State practices and began interviewing questionnaire respondents to gather more detailed information. Included an overview of planned interviews in the revised work plan.

Anticipated work next quarter: ## Traffic Control Devices Pooled Fund Study Technical Support - Continue holding bi-weekly meetings to discuss the status of the task order and will prepare the list of Action Items and Activities prior to each meeting. - Continue providing monthly progress reports. - Continue to maintain and/or upload documents (as appropriate) to the contact list, email group, and Microsoft Teams and keep track of internal position changes. - Finalize the location for the 2026 Annual Meeting, secure hotel and A/V contracts, and begin arranging travel for members. - Finalize and distribute Q1 meeting minutes. Solicit member availability for the Q2 virtual quarterly meeting, schedule and prepare meeting materials, and facilitate the meeting. Draft and finalize the meeting minutes. - Begin gathering research ideas from members in advance of the Annual Meeting. - Continue work on the TTC Guide Sign Color state-of-practice review. Pedestrian Signing at Unsignalized Crossings - No additional work planned. The period of performance will end on 4/26/2026. - The TOCOR will continue to monitor the publications process and distribute the report as appropriate. Comprehension and Legibility of Selected Symbol Signs Phase V - No additional work planned. The period of performance ended on 03/21/2026. - The TOCOR will continue to monitor the publications process and distribute the report as appropriate. Evaluation of Pavement Markings in Merge Areas - Attend bi-weekly meetings with the TOCOR to discuss project activities. - Finalize pavement marking selections for field testing. - Evaluate cameras for field testing operations. - Select sites for field testing. - Begin process for MUTCD experimentation request (pending confirmation of participating State DOTs). - Pilot test field study. - Begin data collection for the field study. Temporary Traffic Control Advance Warning Sign Placement - Continue conducting follow-up outreach interviews with select practitioners and incorporate relevant findings in the revised work plan. - Review and describe additional responses to practitioner feedback form and incorporate updated findings in the revised work plan. - Revise the work plan based on comments from the TOCOR and TCD PFS panel and submit the revised work plan. - Submit draft list of panel members. Revise based on feedback from FHWA and project champions and resubmit the list of potential panel members. Request commitment and availability from potential panel members. - Draft the Synthesis Summary. - Schedule the first expert panel meeting and begin planning.

Significant Results: The Comprehension and Legibility of Selected Symbol Signs Phase V project was concluded. The Pedestrian Signing at Unsignalized Crossings project was concluded.

Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope and fiscal constraints set forth in the agreement, along with recommended solutions to those problems). None at this time.

Potential Implementation: All results from the Traffic Control Devices Pooled Fund Study are considered by FHWA for inclusion in subsequent MUTCD versions and interim approvals.