{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":14,"n_cols":11,"rows_kept":14,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["Graphic View of Pooled Fund Study TPF 5(111)"]
[]
["Phase","Phase 1","Phase 2","Phase 2","Phase 2","Phase 2","Phase 2","Phase 2","Phase 2","Phase 3","Phase 3"]
["Task Number",1,2,3,4,5,6,7,8,9,10]
["Task","Develop straw survey","Send to GMS team","Finalize Survey Questions","Response comments from GMS","Distribute Survey","Reduce Survey Data","Draft out for comments","Final schema/dictionary delivered","Develop additional straw dictionaries, hierarchy and schema","Finalize new elements for  draft schema"]
["Deliverable","Preliminary draft survey (Prototype data dictionary & schema)","Finalized Survey – Consensus version (Preliminary Draft Dictionary available for DOT use)","Collected responses to survey","Draft dictionary ready for general comment ","Comments from general stakeholders on draft dictionary","Final data dictionary","Preliminary draft hierarchy and schema","Draft hierarchy and schema","New additions to phase 1 schema for additional elements","Final hierarchy and schema of new elements - ready for standards groups and use"]
["Estimated Completion Date","2005-11-30","2006-01-15","2006-01-31","2006-03-06","2006-05-15","2006-07-30","2007-01-31","2007-05-01","2007-03-01","2008-06-30"]
["Work Accomplished","Prototype schema and dictionary completed","Draft Dictionary and schema completed - Dictionary needed more work to complete","GMS returned comments","Draft Dictionary behind 2 weeks","Internal review of Draft circulated, no meetings, update to draft for public review by July 12","Draft corrected and readyed for Limited Public Review (new step added) - Launched Aug 7,06 - Completed Sept 15, 06 - New effort to make correction in Schema from Limited review comments - Expected completion by Jan 30 - Public release expected.  Public comments will be received by May 1.","Survey from GMS and limited public review completed.  Found inconsistencies in the schema.  New effort launched to convert to UML description which automatically creates the XSD files - no change in the hierarchy or an major changes to schema.","Working on putting all schema data into new tool (UML) -  v0.10 was delivered April 08 - final public review draft planned July 4th -  UML agreed by GMS & GDC - Cost is $40K - Draft Release will have wide dissemination and be treated as the Full public release.  New merged website is complete and operational for the public review.  V1Beta was released on July 18, 2008 for reveiw.  The forum is being monitored for revei comments. March 25&26 GMS meeting developed actions to release v1.0 schema and develop governance for future. - Two Consultants hired to give independent reviews and improvements to Schema (completed) - Consultant hired to make changes to schema for release - Version 1.1 to be released in April","A new Sig has been developed for Environmental data.  The kickoff meeting was held February 13-14, 07 in Orlando.  The SIG includes US EPA, US Army Corps, AGS, Earthsoft, Department of the Navy and UF.  The Dictonary Workshop was held June 18-21, 07 in Orlando to work out the rdetails of the inclusing of EPA schemas into DIGGS.  The group developed the ENV additions and added them directly to the UML description. The Nov workshop meeting in Salt Lake City finalized the draft schema which has been incorporated for the June 08 public review. New SIGs will be discussed once release is complete. ","Env schema is incorparated into the Base schema public review.  At end of public review - GMS needs to discuss future efforts and SIGs - Env schema is the only new schema that will be added - rest of efforts will be on tools, adoption, support, etc"]
["Actual Completion Date","2005-11-30","2006-01-17","2006-02-06","2006-08-08","2006-09-15","2007-01-10","2007-02-20","2009-12-01","2008-10-01"]
["Proposed expenditure for task",43240,51299,51140,51140,51140,43240,51140,40000,150000,105000]
["Proposed % Total expenditure",1,0.08549833333333333,0.17073166666666667,0.255965,0.3411983333333333,0.413265,0.4984983333333333,0.565165,0.815165,0.990165]
["Actual expenditure for task",38534,19777,18288,0,0,3400,0,188512,21241,50000]
["Actual % Total expenditure",0.8911655874190564,0.03296166666666667,0.06344166666666666,0.06344166666666666,0.06344166666666666,0.06910833333333333,0.06910833333333333,0.383295,0.41869666666666666,0.50203]
["Phase","Phase 1","Phase 2","Phase 2","Phase 2","Phase 2","Phase 2","Phase 2","Phase 2","Phase 3","Phase 3"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}