TRANSPORTATION POOLED FUND PROGRAM

QUARTERLY PROGRESS REPORT

Date:	11 October 2011

Lead Agency:  FHWA

INSTRUCTIONS:

Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active.  Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any.  List all tasks, even if no work was done during this period.

| Transportation Pooled Fund Program Project # TPFS 5(161) |  | Transportation Pooled Fund Program - Report Period: □Quarter 1 (January 1 – March 31) □Quarter 2 (April 1 – June 30) xx Quarter 3 (July 1 – September 30) □Quarter 4 (October 1 – December 31) |  |
| --- | --- | --- | --- |
| Project Title: Highway Infrastructure Security and Emergency Management Professional Capacity Building |  |  |  |
| Name of Project Manager(s): Dan Ferezan | Phone Number: 202-366-0507 |  | E-Mail dan.ferezan@dot.gov |
| Lead Agency Project ID: ATPFS 5(161) | Other Project ID (i.e., contract #): N/A |  | Project Start Date: 2008 |
| Original Project End Date: 2012 | Current Project End Date: 2012 |  | Number of Extensions: 0 |

Project schedule status:

xx On schedule	       □On revised schedule		□ Ahead of schedule		□ Behind schedule

Overall Project Statistics:

| Total Project Budget | Total Cost to Date for Project | Percentage of Work Completed to Date |
| --- | --- | --- |
| $480,000.00 | ~$420,000.00 | ~80% |

Quarterly Project Statistics:

| Total Project Expenses and Percentage This Quarter | Total Amount of Funds Expended This Quarter | Total Percentage of Time Used to Date |
| --- | --- | --- |
| See funding information in project description below | ~$29,700.00 | N/A |

Project Description: This is an unusual project. Donors asked for training products in the areas of Highway Infrastructure Security and Emergency Management. This resulted in the conduct of a solicitation and subsequent award of five separate contracts to develop each of the five products. The products were developed sequentially in a priority designated by the donors. This priority reflected importance of the training product and assured funding would be available for all products. Products and their current status are: • Product 1 (Organization roles and missions): Completed in December 2009. • Product 2 (Evacuation Principles): In pilot testing. Expected delivery is December 2011. • Product 3 (HSEEP for DOTs): Based upon recommendation of project manager and approval of donors this project was cancelled and replaced with Project 6. • Product 4 (NIMS for Frontline Transportation Workers): Completed in September 2009. • Product 5 (Component Level Risk Management Introduction/Familiarization): Completed in November 2010. • Product 6 (Security and Emergency Management Considerations for Highway Planners): Product is under development. Expected delivery is February 2012. There is approximately $60,000.00 of the original $480,000.00 remaining to complete product 6. PFS funds for product 2 (~$92,226.00) have been expended and FHWA funding is being used to complete the product.

Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.): Product 2: Completed technical review of pilot ready presenter files, complete with narration. Recruited initial group for pilot testing and conducted pilot test. Initiated recruitment of second group for pilot testing. Product 6: Conduct start of work meeting and initiated work. Initiated discussions with State DOT and MPO practitioners. Completed preliminary research and analysis.

Anticipated work next quarter: Product 2: Complete pilot testing, make adjustments, and deliver the product. Product 6: Develop and review draft tool. Obtain comments from State DOT and MPO practitioners.

Significant Results: Product 2: Pilot testing underway. Product 6: preliminary research and analysis completed. Tool development initiated.

Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope and fiscal constraints set forth in the agreement, along with recommended solutions to those problems). Product 2: N/A Product 6: N/A

Potential Implementation: Training material will be available for use as follows: Product 2: December 2011. Product 6: February 2012.