| Project Title | Agmt./Task No. | Item No. | Agency Bgt. No. |
| --- | --- | --- | --- |
| TPF-5(135) Tire/Pavement Noise Research Consortium | Y10704 |  |  |
| Research Agency | Start Date | Estimated Completion | Revised Completion |
| WSDOT | 7/1/06 | 12/31/12 |  |
| Principal Investigator(s) | Technical Contact |
| Illingworth & Rodkin, Transtec, Lodico | Bruce Rymer 916.653.6073, Tim Sexton 206.440.4549, Jeff Uhlmeyer 360.709.5485 |
| WSDOT Program Manager | FHWA or Other Technical Contact |
| Kim Willoughby 360.705.7978 | Mark Swanlund 202.366.1323 |
| Funding Source | Schedule Status |
| CA, FHWA, KS, MN, MT, NC, NM, OH, TX, WA | On schedule Ahead of schedule On revised schedule Behind schedule |
| Original Estimated Cost | Revised Cost | % Funds Expended | % Work Completed |
| $150,000 | $520,000 | 85% | 85% |
| Objective |
| The objectives are: (1) provide a forum for states to discuss tire/pavement noise issues and develop a proposed research plan, and (2) pool resources and efforts of multiple state agencies and industry to perform tire/pavement noise research in a similar manner (avoiding duplication) and sharing of data. |

Project Progress:

Illingworth & Rodkin/Transtec/Lodico have completed many of the tasks that they were assigned to accomplish – see below. The meeting on July 28th in Portland, OR discussed the next steps and determined research needs from this point forward. See list below table for new research focus.

| Task No. | Description | Status | Expected Completion |
| --- | --- | --- | --- |
| 1 | General Consultation | On-going | 8/31/2011 |
| 2 | OBSI Measurements - Montana DOT | Testing completed 9/18/09, final report submitted to MDOT 8/10 | Completed |
| 3 | OBSI Measurements - Ohio DOT | Testing completed 10/1/09, draft final report submitted to ODOT 1/10 | Completed |
| 4 | OBSI Measurements - Kansas DOT | Testing completed 10/30/09, draft report submitted 9/10 | Completed |
| 5 | Support for Volpe B&K Class | Completed October 7 & 8, 2009 | Completed |
| 6 | Volpe Training & Comparative OBSI | Testing at Honda PG completed 10/16, data analysis complete, report deferred to NCAT testing | Completed |
| 7 | NCAT Track OBSI Measurements | Testing at NCAT completed 11/3/09, draft report submitted 8/10 | Completed |
| 8 | OBSI Rodeo Support & Participation | Prelim GM Yuma PG testing 12/17/09, analysis & report pending | Completed |
| 8a | Comparative Testing with TxDOT, UT CTR, Transtec, & I&R | Testing completed 2/19/10 & 2/25/10, draft report submitted 8/10 | Completed |
| 9 | OBSI Calibrator | Active | 8/31/2011 |
| 10 | Scale for Tire Loading | Awaiting request for first usage | 8/31/2011 |
| 11 | B&K Pulse Data Analysis Routine | Inactive | 2/28/2011 |
| 12 | Quiet Pavement Folio | Final version published and distributed | Completed |
| 13 | NI System Development | Develop low cost OBSI system based on National Instruments analyzer | 6/30/2011 |
| 14 | OBSI Data Base Development | Initial IR and TGI data compiled and pending entry in the system | Completed |
| 15 | North Carolina Ambassador/Rodeo (FDOT, NCDOT, Volpe) | Rodeo completed 9/10, draft report completed in 1/11 | Completed |
| 16 | Washington State Rodeo | Planning | TBD |

List of priorities for 2011/2012

- NI OBSI Measurement System Development

- OBSI Calibrator

- B&K PULSE Data Analysis Routine

- New SRTT Evaluation

- OBSI Rodeo

- Outreach

- General Consultation

New Period Proposed Activity:

- Continue developing the low cost OBSI system with NI analyzer, along with beginning the second priority above.

- Finalize reports from the rodeos and ambassador tours