TRANSPORTATION POOLED FUND PROGRAM

QUARTERLY PROGRESS REPORT

Lead Agency (FHWA or State DOT):  _Missouri Department of Transportation    _________________

INSTRUCTIONS:

Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active.  Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any.  List all tasks, even if no work was done during this period.

| Transportation Pooled Fund Program Project # (i.e, SPR-2(XXX), SPR-3(XXX) or TPF-5(XXX) TPF-5(213) |  | Transportation Pooled Fund Program - Report Period: □Quarter 1 (January 1 – March 31) □Quarter 2 (April 1 – June 30) □Quarter 3 (July 1 – September 30) xQuarter 4 (October 1 – December 31) |  |
| --- | --- | --- | --- |
| Project Title: Performance of Recycled Asphalt Shingles in Hot Mix Asphalt |  |  |  |
| Name of Project Manager(s): R. Christopher Williams, Ph.D. | Phone Number: 515-294-4419 |  | E-Mail rwilliam@iastate.edu |
| Lead Agency Project ID: TRyy0928 | Other Project ID (i.e., contract #): |  | Project Start Date: 9/1/2008 |
| Original Project End Date: 10/31/2012 | Current Project End Date: 10/31/2012 |  | Number of Extensions: None |

Project schedule status:

X On schedule	□ On revised schedule		□ Ahead of schedule		□ Behind schedule

Overall Project Statistics:

| Total Project Budget | Total Cost to Date for Project | Percentage of Work Completed to Date |
| --- | --- | --- |
| $765,000 | $544,626 | 70% |

Quarterly Project Statistics:

| Total Project Expenses and Percentage This Quarter | Total Amount of Funds Expended This Quarter | Total Percentage of Time Used to Date |
| --- | --- | --- |
| $544,626 | $76,399 | 45% |

Project Description: The use of recycled asphalt shingles (RAS) in hot-mix asphalt (HMA) applications has grown across the U.S. over the last 10 years. Although the majority of states are using manufacturers RAS, there has been a rapidly growing interest in the use and applications of tear-off RAS in hot-mix asphalt (HMA). Many states share common concerns and questions in the use of tear-off shingles. Previous research has allowed for only limited laboratory testing and field surveys. Researchers and bituminous/material engineers still require additional research to study the effects of tear-off RAS on the performance of HMA and their economic value. Multiple state demonstration projects would provide adequate laboratory and field test results to more comprehensively answer the design, performance and environmental questions/concerns remaining. These concerns include the qualification of tear-off RAS for use in HMA and utilization of tear-off RAS ensuring acceptable long-term HMA performance. The primary goal of this study is to address research needs of state DOT and environmental officials to determine the best practices for the use of recycled asphalt shingles in hot-mix asphalt applications. The study will address the following research objectives: 1. To address the concerns of quality assurance (QA)/ quality control (QC) in the sourcing, processing and incorporation of the RAS to achieve a final product that would meet the requirements for use in state HMA applications. Create a specification that includes sufficient language to cover the QA/QC concerns. 2. To conduct demonstration projects to provide laboratory testing and field surveys to determine the behavior and performance of RAS in HMA at varying percentages, climates and traffic levels. 3.To create a comprehensive database on the performance of RAS in HMA applications.

Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.): During the eighth quarter, October 1, 2011 through December 31, 2011, the TPF-5(213) team achieved the following components on the project: - A Technical Advisory Committee (TAC) meeting was held on November 8-9, 2011 in Ames, Iowa. A list of action items was developed at the meeting and subsequently distributed to members of the TAC. - The Illinois DOT in partnership with the Illinois Tollway provided mixtures that were produced the previous quarter, were delivered as well as companion laboratory produced mixtures. - The Wisconsin DOT produced a control and experimental mixture using Evotherm as a compaction aid with shingles during late season paving. The mixtures were sampled and shipped to Iowa State University for subsequent testing. - Comments of the dynamic modulus test results draft report from Missouri, Iowa, Indiana, and Minnesota were received during the TAC meeting. The report has been updated reflecting the comments. The report will include the updated Witzcak and Hirsh models that will include RAS. - All remaining semi-circular bend (SCB) test samples from Illinois and Wisconsin have been compacted and will be delivered for subsequent testing at the University of Minnesota. - Mixture samples of for binder extraction/recovery from Illinois and Wisconsin have been split from field samples and will be delivered in the following quarter. - Beam fatigue testing on the Colorado mixtures are nearing completion and slabs have been procured for the Illinois DOT mixtures. Beams will need to be cut from the slabs for subsequent testing. - Pre-winter condition survey's for Colorado, and Illinois DOT project demonstrations were completed.

Anticipated work next quarter: - A web based meeting is being planned for the upcoming quarter to discuss additional testing results; - Schedule a workshop with CalTrans; - Finalize demonstration project(s) with California; - Complete draft reports on the binder characterization, beam fatigue test results, flow number test results, gradation and volumetric properties of all the mixes. - Continue mix and binder testing of materials received from Colorado as well as materials received from Illinois and Wisconsin; and - Send out TPF member website link for state members to review state front pages and to review state draft reports. The above accomplishments and future plans will be discussed at the forthcoming web meeting.

Significant Results: - RAS Mixes have been produced and tested in Colorado, Illinois, Iowa, Minnesota and Missouri. Follow up field condition inspections have also been done on these pavements. - A draft report of the dynamic modulus test results from Missouri, Iowa, Indiana, and Minnesota was completed. The report presented the results in the form of master curves and included statistical analysis of each state’s mixtures. - A workshop on using RAS in HMA pavements has been done for Colorado DOT and two more are planned for California in 2012.

Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope and fiscal constraints set forth in the agreement, along with recommended solutions to those problems).

Potential Implementation: Several states in the study have already put RAS into their asphalt pavement specifications and have approved many job mixes containing either tear off shingle mixes and/or manufacturers waste shingles contained in various amounts. The outcomes form this research will provide a method for characterizing shingles and provide Mix design specifications. This research will allow other highway agencies the opportunity to utilize these mixes while reducing the waste stream and gaining a source of a good percentage of useful asphalt binder as well as fiber filler for the mixes.