TRANSPORTATION POOLED FUND PROGRAM

QUARTERLY PROGRESS REPORT

Lead Agency:  Minnesota DOT

INSTRUCTIONS:

Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active.  Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any.  List all tasks, even if no work was done during this period.

| Transportation Pooled Fund Program Project # TPF-5(192) | Transportation Pooled Fund Program - Report Period: x Quarter 1 (January 1 – March 31) □ Quarter 2 (April 1 – June 30) □ Quarter 3 (July 1 – September 30) □ Quarter 4 (October 1 – December 31) |
| --- | --- |
| Project Title: Loop and Length Based Vehicle Classification |
| Name of Project Manager(s): Gene Hicks, Mn/DOT | Phone Number: 651/366-3856 | E-Mail Gene.Hicks@state.mn.us |
| Lead Agency Project ID: #95029 | Other Project ID (i.e., contract #): | Project Start Date: 1/29/2010 |
| Original Project End Date: 5/31/2012 | Current Project End Date: 10/31/2012 | Number of Extensions: 1 |

Project schedule status:

□ On schedule	x On revised schedule		□ Ahead of schedule		□ Behind schedule

Overall Project Statistics:

| Total Project Budget | Total Cost to Date for Project | Percentage of Work Completed to Date |
| --- | --- | --- |
| $485,000 | $388,475 (consultant expenses) $4,538 (kickoff meeting expenses) $10,600 (2010 NATMEC expenses) Total: $403,613 | 83 percent |

Quarterly Project Statistics:

| Total Project Expenses and Percentage This Quarter | Total Amount of Funds Expended This Quarter | Total Percentage of Time Used to Date |
| --- | --- | --- |
| $76,924 (consultant expenses) 16 percent | $76,924 (consultant expenses) | 79 percent |

Project Description: Field test installation methods for loops to determine the most cost effective and best performing procedures and materials. Determine the number of bins and the length spacing for each of those bins for uniform collection of length based classification data. Establish calibration standards for vehicle length based measurements.

Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.): Detector testing continued at the I-35 (Wyoming, MN) test site. Testing was also conducted at the Watertown, South Dakota PEEK ADR 6000 site. This data was compiled and processed. Laboratory tests of loop detectors were performed playing prerecorded inductive signatures to determine data repeatability. The Project Team began work on Task 6, Determine Feasibility of LBVC Bins and held a conference call with the TAC to discuss an approach for Task 6. Field test results were also shared during this conference call. The Draft Task 5 memo was submitted and feedback was gathered. Task Percent Complete Task 1 Literature Review 100% (on schedule) Task 2 Experimental Design 100% (on schedule) Task 3 Determine Error in Loop LBVC 97% (on schedule) Task 4 Determine Error in non-Loop LBVC 95% (on schedule) Task 5 Establish LBVC Accuracy Standards 100% (on schedule) Task 6 Feasibility of Common LBVC Bins 27% (on schedule) Task 7 Multi State Results 0% (on schedule) Task 8 Final Report 9% (on schedule)

Anticipated work next quarter: Complete field testing and submit Task 3/4 technical memorandum summarizing test results. This will complete Tasks 3 and 4. Complete Task 6, determine Feasibility of Common LBVC Bins. Complete Draft Final Report. Hold project meeting at NATMEC conference in June. Determine approach for Task 7 with TAC (Multi-State Results).

Significant Results: Field and laboratory test results are completed. Accuracy standards and calibration methodology have been submitted for comment.

Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope and fiscal constraints set forth in the agreement, along with recommended solutions to those problems). Delays in contracting and starting the project pushed the initial schedule back two months. Also, the loops installed at the Mn/ROAD Test Site were found to be unsuitable for this research, so an additional set of loops was installed at MnDOT’s automatic traffic recorder site in Wyoming, MN. The installation of these additional loops incurred additional expense for installation and coordination. The schedule was revised and the project is on schedule. Note: consultant contract has been split into two phases. Phase 1 consists of tasks 1 through 4, and phase 2 consists of tasks 5 through 8. Work on both phases is currently underway.

Potential Implementation: This project will recommend a loop detector calibration process and accuracy standards. This project will develop length-based vehicle classification schemes.