TRANSPORTATION POOLED FUND PROGRAM

QUARTERLY PROGRESS REPORT

Date:	August 1, 2012

Lead Agency (FHWA or State DOT):  Michigan DOT

INSTRUCTIONS:

Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active.  Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any.  List all tasks, even if no work was done during this period.

| Transportation Pooled Fund Program Project # TPF-5(254) |  | Transportation Pooled Fund Program - Report Period: □Quarter 1 (January 1 – March 31) □Quarter 2 (April 1 – June 30) □Quarter 3 (July 1 – September 30) □Quarter 4 (October 1 – December 31) |  |
| --- | --- | --- | --- |
| Project Title: Bulb-T Beam As Alternate ABC to Side-by-Side Box Beam. |  |  |  |
| Name of Project Manager(s): David Juntunen, P.E./ Matthew Chynoweth, P.E | Phone Number: 517-335-2993 517-322-3322 |  | E-Mail juntunend@michigan.gov ChynowethM@michigan.gov |
| Lead Agency Project ID: MDOT Job No. 114419; OR11-010 | Other Project ID (i.e., contract #): 2010-0293 |  | Project Start Date: September 19, 2011 |
| Original Project End Date: September 30, 2014 | Current Project End Date: September 30, 2014 |  | Number of Extensions: None. |

Project schedule status:

□On schedule	□On revised schedule		□Ahead of schedule		□Behind schedule

Overall Project Statistics:

| Total Project Budget | Total Cost to Date for Project | Percentage of Work Completed to Date |
| --- | --- | --- |
| $349,000. | $101,637. | 26% |

Quarterly Project Statistics:

| Total Project Expenses and Percentage This Quarter | Total Amount of Funds Expended This Quarter | Total Percentage of Time Used to Date |
| --- | --- | --- |
| $101,637. (29%) | $48,609. | 26% |

Project Description: To analyze and evaluate the decked bulb-T beam (or decked I- beam) as a viable replacement for the side-by-side box-beam bridge. The project description uses the term bulb- T beam as a general description of an I- beam shape, with a wide top flange that can serve as a deck surface. For this type of beam to be a viable replacement to a box beam, it must have a very robust cross-section designed to have a shallow depth-to-span ratio; which makes it very different than the standard AASHTO section used by some states. The use of a bulb- T beam cross section would eliminate inherent problems associated with the ability to inspect and repair box-beam type structures. The Bulb-T beam cross-section will provide enough space at the section bottom for ease of periodical inspections and maintenance of critical elements; such as beam web and the suffit of the bridge deck slab.

Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.): Project On Time: The project is on schedule: Task 1 is 100% completed. Task 2 is approximately 55% completed. Task 3 is approximately 36% completed. This quarter period the PI continued work on the Experimental Investigation (EI); ~36% complete, and the Numerical Simulation (NS); ~55% complete, portions of the research plan. Percent Completions By Category: By Time- approximately 26% completed. By Work- approximately 26% completed. By Budget- approximately 29% completed. Project Within Budget: Project expenditures to date- $101,637. Planned budget for FY 2012- $115,281. The TAC accepted an invite from FHWA to make a presentation at the 2012 Mid-North Regional Peer-to-Peer Exchange on PBES in Detroit, Michigan. Mr. Matthew Chynoweth, MDOT Co-Project Manager gave a power presentation sharing the study’s purpose/progress at the exchange on May 2, 2012.

Anticipated work next quarter: Continue work activities on Task 2 (Theoretical Analysis) and Task 3 (Experimental Program). Next progress meeting planned for late September 2012.

Results This Period: The theoretical analysis work continued. Construction of the decked bulb t beams continued. The principal investigator began pre-stressing of decked bulb t beams under the experimental program of the study’s work plan.

Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope and fiscal constraints set forth in the agreement, along with recommended solutions to those problems).

Potential Implementation: