HSM Implementation Pooled Fund Study

TPF-5(255)

Quarterly Report

Jul-Sept 2012

Participating Agencies: CA, ID, IL, NC, KS, OK, MS, PA, MO, LA, WV, WI, WA, OR, and OH.

Total Funding Committed: 1.085M

Total Funding spent as of 9/30/2012: 250K

Activities accomplished during Reporting Period:

- Held a kick off calls with the consultants and the Pooled Fund states to initiate work with Contractor on 3 projects focusing on SPF calibration, development and resource development

- Held call with participating states

- Approved work plan for SPF Guides and Assessment projects

- Reviewed outline for SPF guides

- Held initial calls with TAG states for SPF Assessment

- Solicited interest in SPF workshop in January during TRB week

- Initiated plans for TPF Annual meeting in January 2013

Activities planned for next quarter:

- Issue memo of results for SPF Assessment.

- Submit executive summary of the SPF Guides

- Hold call with participating states

- Finalize plans for SPF Workshop for 25 participants mainly from pooled fund states at the Marriott

- Develop agenda for TPF Annual Meeting on January 14, 2013 at Keck Center in DC