| State Planning and Research Program Annual Report |
| --- |
| PROJECT TITLE: Pavement Surface Characteristics Rehabilitation MnROAD Study. TPF 5-(134). OBJECTIVES: To demonstrate and field-validate some lab-tested unique diamond grinding configurations that optimize noise, Friction, Texture and Ride Quality |
| PERIOD COVERED: April – June 2012 (2nd Quarter). STATUS: Active. LEAD STATE: Minnesota Department of Transportation |
| PARTICIPATING AGENCIES: Mn/DOT, TXDOT, FHWA, ACPA, IGGA. |
| PROJECT MANAGER: Bernard Izevbekhai PhD LEAD AGENCY: Mn/DOT Data Collection : MnDOT PRINCIPAL INVESTIGATORs: Data Collection : MnDOT Data Analysis, W. James Wilde, PhD, P.E. MSU Rolling Resistance Jerzy Ejsmont DSc. Tech University of Gdansk, Poland (3) Statistical Pass By Tim Casey (HDR) Inc (4) ROBOTIC Texture evaluation R.O. Rasmussen, PhD, P.E. Transtec Inc (5) Multivariate Analysis of ROBOTEX & Surface Variables R. Sohaney, P.E. (Transtec Inc) | SP&R PROJECT NO: TPF5-(134) | PROJECT IS: Planning X Research & Development |
| ANNUAL BUDGET: $275,000 for 5 years +$40,000 for Rolling Resistance | PROJECT EXPENDITURES TO DATE: Non-Federal Match. In-Kind Cost of Grinding And Noise Testing On Cell 37 MnRoad. As A Proof Of Concept. Full Width Grinding On Cells 7-8 MnRoad Mainline I-94 Mn/DOT Initial Testing, Mn/Dot Rodeo (June 2008) Spring Noise Texture, Ride Friction Measurements Consultant Appointed For Data Analysis And Reporting Strategies For Additional Testing Testing And Monitoring of Cell 9 Draft Brief on cell 9 Construction Report 7 8 & 9. Spring OBSI testing Spring Ride Quality testing Publication of Task 1 (Jim Wilde) Completion of Draft Report on SPPB Tests on I-94 and MnROAD Cells Completion of HDR SPPB /Mn/DOT OBSI Final Report. Development of Rolling Resistance Initiative Assistance with Technology Deployment: Mn/DOT Metro, Mn/DOT District 1 Duluth Projects Summer OBSI, Ride Texture and Friction measurement Fall OBSI, Ride Texture and Friction Measurement Test Strip #5 Ground on Cell 37. Innovative with Improved friction. Contract extended to accommodate Rolling Resistance testing Contract documents initiated for comprehensive Robotex texture evaluation of cells at MnROAD Draft Final Report of Rolling Resistance in the Press Draft final Robotex Report submitted Extension of texture studies for RR multivariate analysis |
| WORK COMPLETED: ACPA / IGGA performed the Grinding of 3 configurations at MnROAD Cell 37 for a proof –of –Concept and Preliminary On-Board -Sound –Intensity (OBSI) pre and post grind measurements on the 3 configurations + control. Mn/DOT performed Ride Friction, and Texture measurements on the same pre and post grind configurations. Memorandum of Understanding with Diamond Surface Incorporated to perform the Diamond Grinding Full width on cell 7 and 8 MnROAD. Measurements of Surface Characteristics parameters on the MnROAD Low volume Road Actual grinding of the Mainline cells 7 and 8 to the current and Innovative grinding configurations. Pre-grind Measurements for the MnROAD Mainline Grinding of Cells 7 and 8 full Width by Diamond Surfaces Inc. Initial Post Construction Ride texture friction Ride measurement by Mn/.DOT Draft Construction (Grinding Report for cells 7 and 8 Innovative Grinding & Conventional configurations) Development of Limited Scope of Consultant Activity for MnSCU Mankato Mn/DOT Initial Testing, Mn/DOT Rodeo (June 2008) Spring Testing Noise texture, Ride friction Measurements Consultant (Minnesota State University, Mankato) Appointed for Data Analysis and Reporting. Principal Investigator is W. James Wilde, PhD. MnROAD Cell 9 Ultimate Grinding Cell Created Ground and Tested. Spring Testing (Texture ASTM E-965, E-2157, Friction GN & FN, IRI, OBSI) Proposal to Conduct comprehensive evaluation (OBSI, CPB, SPB) on a Real Roadway. (Prescott WI or Monticello TH 94 MN) Estimated to Cost $62,000. ($20,000 Approved from by the Pooled Fund) Contract with HDR executed. OBSI and SPB in Progress near Hasty MN. The 1000-ft section is ground and east of that section an unground portion is being evaluated. Successful Web meeting on June 1 2009. Plans for a RODEO discussed but not yet done. Analysis of Friction Ride and OBSI over time Presented by W.J. Wilde Omnibus Cell 7 8 & 9 Report Mn/DOT Transtec Rodeo on Cells 37 7,8, 9 and others. OBSI and SPB in Progress near Hasty MN. The 1000-ft section is ground and east of that section an unground portion is being evaluated. Draft SPB Report Review. Summer 2009 Measurements Fall 2009 Measurements Statistical Pass Bys Testing Completed. Statistical Pass Bys Testing Completed. Draft report on Statistical Pass Bys Testing Completed. Spring testing by Mn/DOT OBSI Ride and texture. Final Statistical pass-by report Submitted for Publication Test Strip #5 ground on cell 37. Cell 71 ground innovative Driving and conventional passing Subcontract for Rolling Resistance measurements Rolling Resistance measurements on all MnROAD cells Performed in September Robotex Measurements performed on all MnROAD Cells Pooled fund meeting on 10/5/11 Final Report of Rolling Resistance Report Published http://www.mrr.dot.state.mn.us/research/pdf/201207.pdf Final Report Completion Date extended to March 2013 Final Robotex Report submitted Final Robotex Report Submitted Rolling Resistance Report Published Contract for |
| SUMMARY OF ACTIVITIES EXPECTED TO BE PERFORMED NEXT QUARTER: Continuous monitoring Final Report on Rolling Resistance Final Report on Robotex Measurements Possible time series/ temperature analysis contract Draft Final Report of the entire project Robotex/ RR Multivariate analysis Final Project Report |
| STATUS AND COMPLETION DATE: Project is on schedule. Data Analysis (OBSI Friction, texture , IRI) Can be completed On Schedule Draft Final Report to be on schedule Draft Final Report |