**TRANSPORTATION POOLED FUND PROGRAM**

**QUARTERLY PROGRESS REPORT**

Lead Agency (FHWA or State DOT): Alabama DOT

**INSTRUCTIONS:**

*Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active. Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any. List all tasks, even if no work was done during this period.*

|  |  |  |  |
| --- | --- | --- | --- |
| **Transportation Pooled Fund Program Project #**  *(i.e, SPR-2(XXX), SPR-3(XXX) or TPF-5(XXX)*  TPF-5(228) | | **Transportation Pooled Fund Program - Report Period:**  **√** Quarter 1 (January 1 – March 31) 2014  Quarter 2 (April 1 – June 30)  Quarter 3 (July 1 – September 30)  Quarter 4 (October 1 – December 31) | |
| **Project Title:**  Superpave Regional Center, Southeastern Region | | | |
| **Name of Project Manager(s):**  Don Watson and Randy West | **Phone Number:**  (334) 844-7306 | | **E-Mail**  watsode@auburn.edu |
| **Lead Agency Project ID:**  ALDOT Research Project No. 930-763P | **Other Project ID (i.e., contract #):**  224574 | | **Project Start Date:**  April 28, 2010 |
| **Original Project End Date:**  September 30, 2012 | **Current Project End Date:**  September 30, 2014 | | **Number of Extensions:**  2 |

Project schedule status:

On schedule √ On revised schedule Ahead of schedule Behind schedule

Overall Project Statistics:

|  |  |  |
| --- | --- | --- |
| **Total Project Budget** | **Total Cost to Date for Project** | **Percentage of Work**  **Completed to Date** |
| $1,037,129 | $490,670.50 | 59 |

***Quarterly*** Project Statistics:

|  |  |  |
| --- | --- | --- |
| **Total Project Expenses**  **and Percentage as of This Quarter** | **Total Amount of Funds**  **Expended This Quarter** | **Total Percentage of**  **Time Used to Date** |
| $490,670.5 (47.3% of budget) | $24,382.65 | 85 |

|  |
| --- |
| **Project Description**:  The Southeastern Superpave Center has been supported by state agencies through a pooled-fund project that has been largely used to provide training, verify ruggedness of equipment, check equipment calibrations, provide materials research, and aid in keeping agency personnel abreast of changes in asphalt technology. In order to continue the efforts in training, technology transfer, and implementable research, it is essential that the pooled-fund effort be continued.  ***NOTE:*** *This pooled-fund project is not limited to states located in the southeast. Agencies throughout the country are invited to participate and take advantage of the research and training opportunities provided by the Southeastern Superpave Center.*  **OBJECTIVES**  Several short-term and long-term objectives of the Southeastern Superpave Center are listed below. Several objectives deal with evaluating recently-developed performance test equipment and conducting research to address materials and tests issues. Objectives of the Center are:   1. Conduct training in regard to Superpave binders, mix design, and performance testing. Provide training on special topics as requested by participating agencies at their on-site locations. 2. Perform research, both cooperatively and agency-specific, sponsored by members of the pooled-fund. 3. Perform precision and bias testing for asphalt-related performance test equipment. 4. Conduct noise studies in an effort to develop quieter pavements. 5. Perform forensic evaluations on materials or projects that have experienced premature distress. 6. Prepare research articles of regional and national interest. |

|  |
| --- |
| **Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.):**  **MEPDG CLIMATE DATABASE:**  The research team coordinated with LTRC to identify three representative pavement sections for use in verifying the climate files. The work for the first phase of this research has been completed, and LTRC recently asked that the research be extended to include more information.  Progress on the project has been delayed while the pooled fund administrative process clears the funding for the additional tasks. The project is scheduled to be completed in 2014.  **4.75mm Study**  The objective of this study is to examine the performance of 4.75mm asphalt mixes with that of a 9.5mm mix used as a “control.” Comparisons will be made with neat asphalt and with modified asphalt using two aggregate sources. The binder modification will be made with polymers for one set of mixtures and with crumb rubber for an additional set of mixtures. Mixtures with PG64-22 neat asphalt will also be compared with the performance of mixtures with a PG 67-22 binder grade. Performance tests will be conducted to address the three distresses common to asphalt pavements - rutting, stripping, and cracking. The Hamburg device will be used to evaluate resistance to rutting and stripping, and the AMPT device will be used to evaluate resistance to reflective cracking.  Testing of the asphalt mixes for this project is complete. Preliminary results indicate that the 4.75 mm mixes perform as good, or better, in the Hamburg rut testing and moisture susceptibility testing as the 9.5 mm mix used as a control standard. The 4.75 mm mixes performed lower in the AMPT Overlay Test for resistance to reflective cracking than the 9.5 mm mix, and the polymer-modified binder performed better than the crumb rubber-modified binder  **Crumb Rubber Mixture**  A study for Puerto Rico to evaluate the effect of crumb rubber in asphalt mixtures began last quarter. This quarter, additional friction testing and noise evaluation of the test sections was conducted. Performance will be compared over time with a standard Marshall mix with unmodified binder. Initial testing conducted one month after construction indicated similar friction values for both the crumb rubber and standard mix sections. Friction values were also similar to a four year old crumb rubber project. The older project is performing well except that some individual aggregate pop-outs are beginning to occur.  **TRAINING**  A series of technician training and certification courses have been prepared in March and are scheduled to begin in April, 2014. Twelve courses have been scheduled for Puerto Rico.  Additional training for Superpave binder and mix design certification for GDOT technicians is being planned in 2014. The binder course and mix design courses are scheduled for June.  **TECHNOLOGY TRANSFER/TECHNICAL MEETINGS:**  Several agencies used funds this period to pay travel and registration expenses for employees to attend technical meetings such as ASTM, AASHTO, SEAUPG, and national meetings of technical interest.  **Anticipated work next quarter**:  Work is expected to resume on the LA DOTD project. The research panel has met and  decided on the type of pavement distresses to be Included in the analysis.  A final report on the 4.75 mm mix study will be submitted.  A study of South Carolina aggregates used in OGFC mixtures has been agreed on and aggregates for that study should be submitted soon. The study will include a petrographic analysis of thin sections to evaluate mica content in the aggregate particles. |
|  |
| **Significant Results:**  N/A |
| **Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that**  **might affect the completion of the project within the time, scope and fiscal constraints set forth in the**  **agreement, along with recommended solutions to those problems).**  The 4.75 mm mix study has been delayed while waiting on additional material to arrive. |

|  |
| --- |
| **Potential Implementation:**  The climate data being obtained will be useful for one agency by providing specific climate data that is more compre-  hensive and more accurate than the original data used in the MEPDG development.  The crumb rubber research is being used to verify the potential benefit of using ground tire rubber in asphalt mixes in  order to conserve the environment.  The training and certification courses being developed and taught will help ensure qualified technicians who are  familiar with agency specifications and test procedures will be involved in the asphalt binder and mixture acceptance  process. |