TRANSPORTATION POOLED FUND PROGRAM

QUARTERLY PROGRESS REPORT

Lead Agency (FHWA or State DOT):  _______Iowa DOT__________________________________

INSTRUCTIONS:

Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active.  Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any.  List all tasks, even if no work was done during this period.

| Transportation Pooled Fund Program Project # TPF-5(275) |  | Transportation Pooled Fund Program - Report Period: X Quarter 1 (January 1 – March 31), 2014_ Quarter 2 (April 1 – June 30), _______ Quarter 3 (July 1 – September 30), _______ Quarter 4 (October 1 – December 31), 2013___ |  |
| --- | --- | --- | --- |
| Project Title: 2014 Asset Management Conference and Training on Implementation Strategies |  |  |  |
| Name of Project Manager(s): Matthew Haubrich, Iowa DOT Tom Palmerlee, TRB | Phone Number: (515) 233-7902 (202) 334-2907 |  | E-Mail: Matthew.Haubrich@dot.iowa.gov TPalmerlee@nas.edu |
| Lead Agency Project ID: RT1025 | Other Project ID (i.e., contract #): |  | Project Start Date: 9-21-2012 |
| Original Project End Date: 10-1-2014 | Current Project End Date: 10-1-2014 |  | Number of Extensions: |

Project schedule status:

X On schedule	□ On revised schedule		□ Ahead of schedule		□ Behind schedule

Overall Project Statistics:

| Total Project Budget | Total Cost to Date for Project | Percentage of Work Completed to Date |
| --- | --- | --- |
| $235,000 | $105,268.74 | 42% |

Quarterly Project Statistics:

| Total Project Expenses and Percentage This Quarter | Total Amount of Funds Expended This Quarter | Total Percentage of Time Used to Date |
| --- | --- | --- |
| $29,649 13% | $29,649 |  |

Project Description: TRB will organize an Asset Management Conference attended by member states and interested parties to exchanges information the challenges of asset management implementation. A venue for pooled fund partners will be developed to share state DOT best practices and strategies for overcoming challenges.

# Report 4th Quarter, 2013 10th National Conference on Transportation Asset Management TPF-5(275) Asset Management ## Progress 3rd Quarter, 2013 Oct-2013 Track Leaders Update Session Titles Oct-2013 Send to Publications for layout: AASHTO & Ohio Conference Announcement Oct-2013 Print Announcement Oct-2013 Final session titles, descriptions, and speakers set & entered into software Oct-2013 Workshop Leaders. Provide speakers and presentation topics for inclusion in the preliminary program. Oct-2013 Conference Chair complete preliminary slotting of sessions to times, distribute to track teams. Oct-2013 Final track team slotting comments due Oct-2013 AASHTO Annual Meeting in Denver. 500 announcement copies Oct-2013 Transit GIS Conference, 150 Announcement copies Oct-2013 Final slotting of sessions to times Oct-2013 Track leaders provide name of their Closing Session speaker Oct-2013 Track teams finish poster selection Oct-2013 AMPO, Portland, OR, 200 Announcement copies Oct-2013 Ohio Transportation Conference "Managing the Assets: Priorities, Partnerships & Performance" http://www.otecohio.org.- Andrew Williams Oct-2013 FPTA Annual Conference, Clearwater Beach, Florida, Bittner, Send 400 copies Oct-2013 TRB Publications starts on 11x17 Advance Program Oct-2013 Send Presenter Acceptances Oct-2013 Reminder re Track Webinar Applications due Nov 15 Oct-2013 Send Presenter Rejects Nov-2013 Preliminary Program (full) editing complete, to TRB Publications Nov-2013 11x17 Advance Program- PDF complete and posted Dec-2013 11x17 Advance Program Layout to Printer (1000 copies) Dec-2013 Preliminary Program Posted Dec-2013 Deadline for Presenter Confirmations Dec-2013 E-News announcement that Prelim Program posted Dec-2013 11x17 Advance Program Deliver to TRB Dec-2013 Track Webinar Applications due to Lisa Marflak, TRB Webinar Director ## Anticipated 1st Quarter, 2014 Work Jan-2014 Distribute 1,000 Advance Programs at the TRB Annual meeting Jan-2014 Planning Committee at TRB Annual Meeting Jan-2014 Early Bird Registration Deadline Feb-2014 Planning Committee Call Mar-2014 AASHTO March 25 Washington Briefing. 200 Advance Programs to Matt Hardy Mar-2014 Final Program Text Deadline for planning committee Mar-2014 Advance Registration Deadline Apr-2014 Final Program editing complete, to TRB TRB Publications Apr-2014 Send to Printer Apr-2014 Final Program to TRB Apr-2014 Ship to Miami Apr-2014 Conference Starts ## Significant Results Conference Announcement printed and distributed to several appropriate meetings, including the AASHTO annual meeting and the Ohio “Managing Your Assets” conference. Special transit announcements were distributed to the Florida Public Transportation Association meeting, the APTA sustainability conference and the TRB Transit GIS conference.. Advance Program document with all sessions and session description developed. 1,000 copies to be printed for distribution at the TRB Annual Meeting and other events. Contains link to posted Preliminary Program. Preliminary Program document with 20 pages, showing all sessions, presentations and speakers layout and posted to be the main reference. Approximately 85% of approximately 150 speakers confirmed. Needs calculated for state and local government speakers determined, compared to budgeted funds, and available amount committed to all those needing support. 54 people registered.

Anticipated work next quarter: ## 2nd Quarter Anticipated Activities Apr 08 All Tech Reps Conference Call Apr 12 Leadership Conference Call Apr 15 Developed Detailed Program Development Conference Call Apr 15 Established Program Tracks Apr 16 Transit SGR Track Conference Call Apr 16 Traditional Tracks Conference Call Apr 23 Adaptation Track Conference Call Apr 24 Revised Announcement Text Final Apr 26 Pooled Fund Tech Reps Chairs & TRB Staff Call Apr 29 Revised Announcement Layout Complete, Send to Printer for AASHTO Spring Meeting May 01 Finalize Track Objectives May 03 Revised Announcement Copies Delivered to AASHTO May 08 Call for Presentations text complete. Call to Pubs for Layout May 13 All Tech Reps Conference Call May 15 Registration Site Ready May 15 Call for Presentations Posted May 21 E News notice re Call for Presentations May 22 Finalize Track Objectives May 29 Call for Presentations text complete. Call to Pubs for Layout Jun 05 Call for Presentations Posted Jun 07 Meetings send notice that Call is open Jun 07 Reminder email on Call for Presentations deadline from Meetings Jun 07 E News reminder to Call for Presentations Deadline Jun 07 Distribute Call for Presentations Jun-2013 All Tech Reps Conference Call Jun 26 Planning Team Preliminary Decisions on Review Approach # Report 3rd Quarter, 2013 Revised 10th National Conference on Transportation Asset Management TPF-5(275) Asset Management ## Progress 3rd Quarter Jul-2013 Research Contract with ISU Approved by NAS Jul-2013 Promotion at RAC/TRB State Reps Meeting in Baton Rouge Jul-2013 TRB E News reminder to Call Deadline Jul-2013 Reminder email on Call deadline to be sent by TRB Meetings Staff Jul-2013 Promotion at 2013 Subcommittee on Maintenance with the Subcommittee on Asset Management Meeting. 7/21-25/13. Matt Hardy Jul-2013 Florida Promotion Conference Call Jul-2013 Adaptation Track Conference Call Jul-2013 Promotion at APTA’s Sustainability & Public Transportation Workshop, San Francisco. Weeks Oct-2013 3 Workshop Leads re (a) workshop title and (b) description, (c) A one or two pager on who should attend and what they will gain. Jul-2013 Planning Committee Conference Call July 31, 2013 Presentation Proposals Due Jul-2013 Session Planning Software Training/Plan Cm Call Aug-2013 Promotion at Subcm on Transportation Finance Policy & SCOP in Minneapolis (Michael Bridges & Matt Hardy) Aug-2013 Conversion abstracts into Session Planning Software complete Aug-2013 Registration Site Ready Aug-2013 Meeting of Principals re AASHTO Asset Mgt Subcommittee Peer Exchange in Miami Aug-2013 Distribute Abstracts to Planning Committee for Review Aug-2013 Track Leaders Conference Call Aug-2013 Webinar on using session building software Sep-2013 Promotion at Transportation Association of Canada (TAC), Winnipeg Sep-2013 Planning Committee Call Sep-2013 Promotion at Amotia Conference, Tampa, FL. Tim Lattner & Jennifer Brandenburg Sep-2013 Promotion at APTA Annual Meeting on SGR Track . Weeks Sep-2013 Draft Session Titles for the AASHTO Announcement ## Anticipated 4th Quarter Work Oct-2013 Track Leaders Update Session Titles Oct-2013 Set up Planning Committee Meeting for the TRB Annual Meeting Oct-2013 Send the draft AASHTO Announcement to Pubs for AASHTO & Ohio Conference Announcement layout Oct-2013 AASHTO Announcement ready for Matt Hardy to pick up Oct-2013 Final session titles, descriptions, and speakers set & entered into software Oct-2013 Workshop Leaders. Provide speakers and presentation topics for inclusion in the preliminary program. Oct-2013 Conference Chair complete preliminary slotting of sessions to times, distribute to track teams. Oct-2013 Final track team slotting comments Oct-2013 Promotion at Transit GIS Conference Oct-2013 Final slotting of sessions to times Oct-2013 Track teams finish poster selection Oct-2013 Promotion at AMPO, Portland, OR, Matt Hardy, 200 Oct-2013 Promotion at Ohio Transportation Conference "Managing the Assets: Priorities, Partnerships & Performance" http://www.otecohio.org.- Andrew Williams Oct-2013 Promotion at FPTA Annual Conference, Clearwater Beach, Florida, Bittner, 400 copies to Hilton Clearwater Hotel by Oct 25 Oct-2013 Send Presenter Acceptances Oct-2013 Publication start on 11x17 Preliminary Program Oct-2013 Send Presenter Rejections Nov-2013 Preliminary Program (full) editing complete, to TRB Pubs Nov-2013 11x17 Prelim Program- PDF complete and posted Nov-2013 Track Webinar Applications due to Lisa Marflak Nov-2013 Preliminary Program (full) Posted Nov-2013 E-News Announcement on the Prelim Program Dec-2013 11x17 Preliminary Program Layout to Printer (1000 copies) Dec-2013 Deadline for Presenter Confirmation Dec-2013 11x17 Delivered to TRB for Annual Meeting ## Significant Results 150 Total presentation proposal abstracts submitted, 50% more than for 2012 conference Planning team complete review of abstracts and develop sessions. Website with registration capability became operational Customized promotional material made available at numerous conferences.

Significant Results:

Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope and fiscal constraints set forth in the agreement, along with recommended solutions to those problems).

Potential Implementation: