**TRANSPORTATION POOLED FUND PROGRAM**

**QUARTERLY PROGRESS REPORT**

**Lead Agency: Utah Department of Transportation**

**INSTRUCTIONS:**

*Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active. Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any. List all tasks, even if no work was done during this period.*

|  |  |
| --- | --- |
| **Transportation Pooled Fund Program Project #****TPF-5(244)** | **Transportation Pooled Fund Program - Report Period:** **x Quarter 1 (January 1 – March 31, 2014)**\_ Quarter 2 (April 1 – June 30, 2014)\_ Quarter 3 (July 1 – September 30, 2014)\_ Quarter 4 (October 1 – December 31, 2014) |
| **Project Title:**Shaking Table Testing to Evaluate Effectiveness of Vertical Drains for Liquefaction Mitigation |
| **Name of Project Manager(s):**David Stevens | **Phone Number:** 801-589-8340 | **E-Mail** davidstevens@utah.gov |
| **Lead Agency Project ID:**5H07074H, 42046, ePM PIN 9933UDOT PIC No. UT07.708 | **Other Project ID (i.e., contract #):** UDOT Contract No. 138731  | **Project Start Date:** May 1, 2013 |
| **Original Project End Date:**March 31, 2016 | **Current Project End Date:** March 31, 2016 | **Number of Extensions:** |

Project schedule status:

 \_ On schedule \_ On revised schedule \_ Ahead of schedule **X** Behind schedule

Overall Project Statistics:

|  |  |  |
| --- | --- | --- |
|  **Total Project Budget** |  **Total Cost to Date for Project** |  **Percentage of Work**  **Completed to Date** |
| $115,000.00 | $5,000.00 | 4% |

***Quarterly*** Project Statistics:

|  |  |  |
| --- | --- | --- |
|  **Total Project Expenses**  **and Percentage This Quarter** |  **Total Amount of Funds**  **Expended This Quarter** |  **Total Percentage of**  **Time Used to Date** |
| $0, 0% | $0 | 29% |

|  |
| --- |
| **Project Description**:The vision for this study is to determine the viability of large diameter (100 mm) prefabricated vertical drains for preventing liquefaction and associated settlements or lateral spreading under full-scale conditions. If viable, drainage alternatives offer substantial advantages in comparison to conventional densification approaches. In production, drains can often be installed at 25% to 40% of the cost of stone columns. In addition, the drains can be installed in about one-third to one-half of the time required for stone columns. Finally, the time and cost associated with post-treatment in-situ testing to evaluate improvement produced by densification may not be required with drains. In an era when construction budgets are becoming increasingly tight and projects are increasingly placed on fast-track schedules, innovative alternative solutions are required to deal with liquefaction hazards.Although limited blast liquefaction testing (Rollins et al. 2003, Rollins et al. 2004), vibration testing (Chang et al. 2004) and centrifuge testing (Yang et al. 2004 ) suggest that vertical drains can be effective, no full-scale drain installation has been subjected to earthquake induced ground motions. This lack of performance data under full-scale conditions has been a major impediment to expanding the use of this technique. To remedy this problem we will conduct full-scale tests with vertical drains in liquefiable sand using the laminar shear box and high speed actuator system at NEES-Univ. at Buffalo. Tests will involve level ground conditions with two drain spacings and will be integrated with a previously funded NEESR study currently underway so that the control tests without drains will already be available. We will use the same sand installation techniques, as well as the same instrumentation plan and shaking protocols which have already been developed and proven successful. This collaborative approach will significantly reduce the cost of the study in comparison to a completely independent study. In addition, it will provide a comparison between the performance of the soil profile with drains relative to subsequent tests where piles will be involved. If full-scale tests prove the effectiveness of the drainage technique, significant time and costs savings can be achieved for both new construction and for retrofit situations. Three objectives are outlined for this study:1. Evaluate the ability of earthquake drains to reduce excess pore pressure and settlement for level ground conditions at progressively higher acceleration levels.2. Define the influence of drain spacing on the effectiveness of the drains for mitigating liquefaction hazard.3. Provide well-documented case histories which can be used to calibrate/validate numerical models for predicting the performance of vertical drains.The scope of work consists of eight specific tasks:1. Perform a literature review to summarize the state of the art in the area of liquefaction mitigation through drainage.2. Conduct level ground shaking table tests with drains at 4 ft spacing.3. Conduct level ground shaking table tests with drains at 3 ft spacing.4. Reduce the test data, analyze, and compare with previous test on untreated sand.5. Evaluate predictive methods by comparing measured behavior with behavior computed using computer models and simplified models.6. Prepare a final report on effectiveness of the drain technique.7. Disseminate the research results.8. Hold technical advisory committee meetings.Dr. Kyle Rollins of BYU is the Principal Investigator for this research project. The TPF-5(244) testing is scheduled to begin at the SUNY-Buffalo shaking table testing facility in the summer of 2014. BYU has been approved for shared-use status on the NEES-Buffalo shake table. Individual task reports will be prepared for Tasks 1 through 5 when these are completed. Up to two in-person meetings with the multi-state technical advisory committee (TAC) are planned to be held in Salt Lake City, Utah during the project. Other TAC meetings will be tele-conference or web meetings. |

|  |
| --- |
| **Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.):**Task 1 – 100% complete. BYU updated the literature review report, and this was shared with the TAC. Task 2 – 5% complete. BYU updated the testing plan.Task 3 – No work yet.Task 4 – No work yet.Task 5 – No work yet.Task 6 – No work yet.Task 7 – No work yet.Task 8 – 10% complete. A kickoff web meeting was held in January with the TAC. PowerPoint slides from the meeting were distributed to the TAC for their use. |
| **Anticipated work next quarter**:Task 1 – None.Task 2 – The updated testing plan will be shared with the technical advisory committee. Dr. Rollins will coordinate with faculty at UB to prepare for the BYU test and to explore opportunities for the TAC to remotely view related testing going on at the facility. The revised schedule calls for the first and second BYU tests to be performed in the summer of 2014 on the NEES-Buffalo shake table. This next quarter could involve beginning the first BYU test on the shake table.Task 3 – None.Task 4 – None.Task 5 – None.Task 6 – None.Task 7 – None.Task 8 – None. |

|  |
| --- |
| **Significant Results:** None at present |
| **Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that** **might affect the completion of the project within the time, scope and fiscal constraints set forth in the** **agreement, along with recommended solutions to those problems).**Due to some technical difficulties on other projects currently being tested at the SUNY-Buffalo facility, there has been a delay in starting testing for this pooled fund project at the facility as previously planned for summer or fall of 2013. Dr. Rollins has been notified that the pooled fund project testing is scheduled for July through September 2014. |

|  |
| --- |
| **Potential Implementation:**  |