TRANSPORTATION POOLED FUND PROGRAM

QUARTERLY PROGRESS REPORT

Date:	16 August 2014

Lead Agency :  Louisiana Department of Transportation & Development

INSTRUCTIONS:

Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active.  Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any.  List all tasks, even if no work was done during this period.

| Transportation Pooled Fund Program Project # (i.e, SPR-2(XXX), SPR-3(XXX) or TPF-5(XXX) TPF-5(273) |  | Transportation Pooled Fund Program - Report Period: □ Quarter 1 (January 1 – March 31) X Quarter 2 (April 1 – June 30) □Quarter 3 (July 1 – September 30) □Quarter 4 (October 1 – December 31) |  |
| --- | --- | --- | --- |
| Project Title: Latin American Trade and Transportation Studies |  |  |  |
| Name of Project Manager(s): Dennis Decker | Phone Number: (225) 379-1248 |  | E-Mail Dennis.Decker@la.gov |
| Lead Agency Project ID: 13-ITTS | Other Project ID (i.e., contract #): 2000004871/H.005319.5 |  | Project Start Date: 1 Dec 2012 |
| Original Project End Date: 30 Jun 2017 | Current Project End Date: 30 Jun 2017 |  | Number of Extensions: 0 |

Project schedule status:

x On schedule	□ On revised schedule		□ Ahead of schedule		□ Behind schedule

Overall Project Statistics:

| Total Project Budget | Total Cost to Date for Project | Percentage of Work Completed to Date |
| --- | --- | --- |
| $1,519,083 | $402,666.96 | 32% |

Quarterly Project Statistics:

| Total Project Expenses and Percentage This Quarter | Total Amount of Funds Expended This Quarter | Total Percentage of Time Used to Date |
| --- | --- | --- |
| $402,666.96 (27%) | $61,960.32 | 32% |

Project Description: OBJECTIVES:

Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.): 1. Network - No substantial work on network. Funding challenges continue. 2. Data - Worked with Tableauview on Proposal for member states - Met with USACE Staff in Huntington to discuss waterway performance metrics - Met with USACE staff in New Orleans to discuss integrating databases into a public releasable database 3. Communications - Follow-up details from ITTS Conference (closing out billing, and related financial matters) - Assisted states in ITTS related travel reimbursement 4. Service to States - Assisted Louisiana in Developing Freight Session at SASHTO - Worked with Florida DOT on updating them on ITTS related freight activities - Provided materials for Mississippi DOT concerning ITTS Conference in 2015 - Organized ort of Bienville tour for MDOT and LADOTD Staff - Assisted on MoDot freight plan - In West Virginia, I met with WVDOT staff, while speaking at the KYOVA Interstate Planning Commission on urban freight movements and a second speech for the WV Regional Planning and Development Councils Conference. - In Arkansas, I spoke at the TRC & Engineering Conference and meet with the Arkansas Waterways Commission and Arkansas State Highway and Transportation staff. 5. Related Tasks - Attended World Trade Center Transportation Committee, and made report on ITTS activities and State Freight Plan work (at the request of Matt Johns) - Attended the Critical Commodities Conference in New Orleans - Moderated session at “The 4th Annual Manufacturing Summit” at Mississippi State. - Meet with Rahill Institute Staff to discuss freight research programs - Submitted coauthored Chapter for Book on “the Governance of Intermodal Facilities”. Chapter title is “Operational Constraints of Effective Governance of Intermodal Transport”

Anticipated work next quarter: Network - Work on developing a SOW with CDM Smith and CS to finish data programs for remainder of year - Work on Transcad on routing assignments and rail networks Data - Continue to work on data integration and data outlining for planning related research Communications - ITTS Newsletter - Speech on Regional Corridors at SASHTO - Begin work on ITTS 2015 Conference with Mississippi - Prepare materials for SASHTO Board of Directors Meeting - Tolling and topical briefs - Prepare Workplan meeting for ITTS States on Aug 7th - Review all state reimbursements for travel related to summer meeting - Update ITTS Website for international trade statistics Service to States - Assist Louisiana in Developing Freight Session at SASHTO - Working with Florida DOT on Bluetooth technologies and autonomous vehicles - Attend IAME Meeting - Providing materials for Mississippi DOT concerning ITTS Conference in 2015 Related Tasks

Significant Results: - Closed out all funding and organization matters from the ITTS Freight in the Southeast Conference - Meet with several states to discuss freight analysis, planning and policy issues

Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope and fiscal constraints set forth in the agreement, along with recommended solutions to those problems).

Potential Implementation: