HSM Implementation Pooled Fund Study

TPF-5(255)

Quarterly Report

July – September 2015

Participating Agencies: CA, ID, IL, LA, NC, KS, OH, OK, OR, MS, PA, MO, NV, UT, WA, WV, and WI

Total Funds Committed: 			$1,135,000

Total Funds Transferred to FHWA: 	$1,015,078

Total Funds Obligated: 			$   541,556

Available Unobligated Funds: 		$   473,522

Activities Accomplished During Reporting Period (July 1 – September 30, 2015):

- Pooled-fund State representatives participated in the Highway Safety Manual Peer Exchange, jointly sponsored by NCHRP Project 17-50 and TPF-5(255) on August 31-September 1, 2015, in Nashville, TN.

- A TPF-5(255) business meeting was held 9/1/2015 in conjunction with the Peer Exchange.

- FHWA awarded a task order for a TPF-5(255) funded project entitled “Model State Policies and Procedures for Use of the HSM.” Two Pooled-Fund State representatives participated on the proposal technical evaluation panel.  A project kickoff meeting was held 9/21/2015

- “Scale and Scope of HSM Implementation in the Project Development Project”:

  - Contractor delivered 2nd draft informational guide on 9/21/2015.

  - Contractor delivered a draft marketing plan on 7/24/2015 and a final marketing plan on 8/5/2015.

- The FHWA Office of Acquisitions Management issued a request for proposals for a TPF-5(255) funded project to conduct an HSM resource needs assessment to assist with HSM implementation.

- Utah DOT joined TPF-5(255)

Activities Planned for Next Quarter (October 1 – December 31, 2015):

- “Scale and Scope of HSM Implementation in the Project Development Project”:

  - Complete review of 2nd draft of informational guide.

- “Model State Policies and Procedures on Use of the HSM”:

  - Complete Task 2.

- Initiate contracted effort with AASHTO for HSM resource needs assessment and HSM implementation support.

- Conduct an analysis of HSM implementation needs identified during the HSM Peer Exchange and suggest possible courses of action for TPF-5(255).

- Hold a virtual meeting of TPF-5(255) State representatives.