TRANSPORTATION POOLED FUND PROGRAM

QUARTERLY PROGRESS REPORT

Lead Agency (FHWA or State DOT):  _Minnesota Dept of Transportation__________________

INSTRUCTIONS:

Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active.  Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any.  List all tasks, even if no work was done during this period.

| Transportation Pooled Fund Program Project # (TPF-5(134) |  | Transportation Pooled Fund Program - Report Period: Quarter 1 (January 1 – March 31) 2013 Quarter 2 (April 1 – June 30) 2013 XQuarter 3 (July 1 – September 30) 2013 Quarter 4 (October 1 – December 31) 2013 |  |
| --- | --- | --- | --- |
| Project Title: Pavement Surface Characteristics Rehabilitation MnROAD Study. TPF 5-(134). |  |  |  |
| Name of Project Manager(s): Bernard Igbafen Izevbekhai, P.E., Ph.D. | Phone Number: 651366 5454 |  | E-Mail: Bernard.izevbekhai@state.mn.us |
| Lead Agency Project ID: | Other Project ID (i.e., contract #): |  | Project Start Date: |
| Original Project End Date: June 2013 | Current Project End Date: October 2014 |  | Number of Extensions: 1 |

Project schedule status:

x□ On schedule	□ On revised schedule		□ Ahead of schedule		□ Behind schedule

Overall Project Statistics:

| Total Project Budget | Total Cost to Date for Project | Percentage of Work Completed to Date |
| --- | --- | --- |
| $315000 $275,000 for 5 years +$40,000 for Rolling Resistance | $250000 Actual work done but not fully billed | 85% |

Quarterly Project Statistics:

| Total Project Expenses and Percentage This Quarter | Total Amount of Funds Expended This Quarter | Total Percentage of Time Used to Date |
| --- | --- | --- |
| ≈85% | $5000 Robotex (Transtec) $25000 RR analysis (Transtec) $ 24000 DG Final report (MSU) $ 99000 Monitoring Cost (MnDOT | ≈85% with extension |

Project Description: OBJECTIVES: To demonstrate and field-validate some lab-tested unique diamond grinding configurations that optimize noise, Friction, Texture and Ride Quality PROJECT MANAGER: Bernard Izevbekhai PhD LEAD AGENCY: MnDOT Data Collection : MnDOT PRINCIPAL INVESTIGATORs: - Data Collection : MnDOT - Data Analysis, W. James Wilde, PhD, P.E. MSU - Rolling Resistance Jerzy Ejsmont DSc. Tech University of Gdansk, Poland (3) Statistical Pass By Tim Casey (HDR) Inc (4) ROBOTIC Texture evaluation R.O. Rasmussen, PhD, P.E. Transtec Inc (5) Multivariate Analysis of ROBOTEX & Surface Variables R. Sohaney, P.E. (Transtec Inc) PROJECT EXPENDITURES TO DATE: Non-Federal Match. In-Kind Cost of Grinding And Noise Testing On Cell 37 MnRoad. As A Proof Of Concept. Full Width Grinding On Cells 7-8 MnRoad Mainline I-94 MnDOT Initial Testing, MnDOT Rodeo (June 2008) Spring Noise Texture, Ride Friction Measurements Consultant Appointed For Data Analysis And Reporting Strategies For Additional Testing Testing And Monitoring of Cell 9 Draft Brief on Cell 9 Construction Report 7 8 & 9. Spring OBSI testing Spring Ride Quality testing Publication of Task 1 (Jim Wilde) Completion of Draft Report on SPPB Tests on I-94 and MnROAD Cells Completion of HDR SPPB /MnDOT OBSI Final Report. Development of Rolling Resistance Initiative Assistance with Technology Deployment: MnDOT Metro, MnDOT District 1 Duluth Projects Summer OBSI, Ride Texture and Friction measurement Fall OBSI, Ride Texture and Friction Measurement Test Strip #5 Ground on Cell 37. Innovative with Improved friction. Contract extended to accommodate Rolling Resistance testing Contract documents initiated for comprehensive Robotex texture evaluation of diamond ground cells at MnROAD Draft Final Report of Rolling Resistance in the Press Draft final Robotex Report submitted Extension of texture studies for RR multivariate analysis

Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.): Final Report on Diamond grinding Study Posted Final Report on Multivariate Analysis of RR and texture variables Posted WORK COMPLETED: - ACPA / IGGA performed the Grinding of 3 configurations at MnROAD Cell 37 for a proof –of –Concept and Preliminary On-Board -Sound –Intensity (OBSI) pre and post grind measurements on the 3 configurations + control. MnDOT performed Ride Friction, and Texture measurements on the same pre and post grind configurations. - Memorandum of Understanding with Diamond Surface Incorporated to perform the Diamond Grinding Full width on cell 7 and 8 MnROAD. - Measurements of Surface Characteristics parameters on the MnROAD Low volume Road - Actual grinding of the Mainline cells 7 and 8 to the current and Innovative grinding configurations. - Pre-grind Measurements for the MnROAD Mainline - Grinding of Cells 7 and 8 full Width by Diamond Surfaces Inc. - Initial Post Construction Ride texture friction Ride measurement by Mn/.DOT - Draft Construction (Grinding Report for cells 7 and 8 Innovative Grinding & Conventional configurations) - Development of Limited Scope of Consultant Activity for MnSCU Mankato - MnDOT Initial Testing, MnDOT Rodeo (June 2008) - Spring Testing Noise texture, Ride friction Measurements - Consultant (Minnesota State University, Mankato) Appointed for Data Analysis and Reporting. Principal Investigator is W. James Wilde, PhD. - MnROAD Cell 9 Ultimate Grinding Cell Created Ground and Tested. - Spring Testing (Texture ASTM E-965, E-2157, Friction GN & FN, IRI, OBSI) - Proposal to Conduct comprehensive evaluation (OBSI, CPB, SPB) on a Real Roadway. (Prescott WI or Monticello TH 94 MN) Estimated to Cost $62,000. ($20,000 Approved from by the Pooled Fund) Contract with HDR executed. - OBSI and SPB in Progress near Hasty MN. The 1000-ft section is ground and east of that section an unground portion is being evaluated. - Successful Web meeting on June 1 2009. Plans for a RODEO discussed but not yet done. - Analysis of Friction Ride and OBSI over time Presented by W.J. Wilde - Omnibus Cell 7 8 & 9 Report - MnDOT Transtec Rodeo on Cells 37 7,8, 9 and others. - OBSI and SPB in Progress near Hasty MN. The 1000-ft section is ground and east of that section an unground portion is being evaluated. Draft SPB Report Review. - Summer 2009 Measurements - Fall 2009 Measurements - Statistical Pass Bys Testing Completed. - Draft report on Statistical Pass Bys Testing Completed. - Spring testing by MnDOT OBSI Ride and texture. - Final Statistical pass-by report Submitted for Publication - Test Strip #5 ground on cell 37. - Cell 71 ground innovative Driving and conventional passing - Subcontract for Rolling Resistance measurements - Rolling Resistance measurements on all MnROAD cells Performed in September - Robotex Measurements performed on all MnROAD Cells - Pooled fund meeting on 10/5/11 - Final Report of Rolling Resistance Report Published - http://www.lrrb.org/media/reports/201207.pdf - Final Report Completion Date extended to Oct 2013 - Final Report on Diamond grinding Study Posted - Final Report on Multivariate Analysis of RR and texture variables Posted

Anticipated work next quarter: - No Cost Extension Request to Rerun Rolling Resistance - Contract Documents with MSU/ Tech University of Gdansk Poland

Significant Results: Report of Rolling Resistance Multivariate Analysis Quietness of Innovative Diamond Grind

Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope and fiscal constraints set forth in the agreement, along with recommended solutions to those problems). To accomplish testing of Rolling resistance in 2014, Funds in the TPF were insufficient but MnDOT added $27000 to make up the $75000 to facilitate this testing. This will be the final activity in this Pooled Fund Study.

Potential Implementation: Already Quiet grind is being implemented:. - MnDOT Duluth 50 million Dollar rehab project - MnDOT TH 52 Rehab Project - Smooth tire friction of innovative grind is equal or higher than ribbed tire - Second rolling resistance measurements at MnROAD