**TRANSPORTATION POOLED FUND PROGRAM**

**QUARTERLY PROGRESS REPORT**

Lead Agency (FHWA or State DOT): \_Michigan Department of Transportation\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**INSTRUCTIONS:**

|  |  |  |  |
| --- | --- | --- | --- |
| **Transportation Pooled Fund Program Project #**  TPF-5(231) | | **Transportation Pooled Fund Program - Report Period:**  x  □Quarter 1 (January 1 – March 31)  □Quarter 2 (April 1 – June 30)  □Quarter 3 (July 1 – September 30)  □Quarter 4 (October 1 – December 31) | |
| **Project Title:** ITS Pooled Fund Program (ENTERPRISE) | | | |
| **Project Manager:** Lee Nederveld **Phone:** (517) 335-5317 **E-mail:** [nederveldl@michigan.gov](mailto:nederveldl@michigan.gov) | | | |
| **Project Investigator:** Dean Deeter, Athey Creek **Phone:** 503.343.9602 **E-mail:** deeter@acconsultants.org | | | |
| **Lead Agency Project ID:** | **Other Project ID (i.e., contract #):**  2010-0316 | | **Project Start Date:** January 2010 |
| **Original Project End Date:**  September 2012 | **Current Project End Date:**  September 2015 | | **Number of Extensions:** 3 |

Project schedule status:

x

□  **On schedule** □ On revised schedule □ Ahead of schedule □ Behind schedule

Overall Project Statistics:

|  |  |  |
| --- | --- | --- |
| **Total Project Budget** | **Total Cost to Date for Project** | **Total Percentage of Work**  **Completed** |
| $2,200,000 (5 year estimated budget, final  Budget dependent on member contributions) | $1,437,876 | 65% |

***Quarterly*** Project Statistics:

|  |  |  |
| --- | --- | --- |
| **Total Project Expenses**  **This Quarter** | **Total Amount of Funds**  **Expended This Quarter** | **Percentage of Work Completed**  **This Quarter** |
| $59,599 | $59,599 | 3% |

**Project Description:**

The ENTERPRISE Pooled Fund Program performs technical projects to serve the needs of the member agencies. Currently, 16 member agencies participate in the ENTERPRISE Pooled Fund. Each year, the members identify current needs of their organization that they feel are most suited to be addressed by pooled fund projects. After identifying candidate projects, the members discuss and ultimately vote to elect the projects to be included in the year’s Work Plan. Technical projects are then performed to execute the projects and address member needs. Overall, three high level tasks are performed:

* ***Management support*** to the program, the lead state, and to members;
* ***Administrative support*** to organize and conduct in-person meetings and monthly webinars; and
* ***Technical support*** to execute the technical projects selected for each year’s Work Plan.

**Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.):**

Administrative/Management Task:

* Three conference calls were held during the 1st Quarter with the ENTERPRISE board members. The purpose of the calls were to provide project updates and begin planning for the 2016 Work Plan.

Technical Task:

* Project 15: ITS Warrants Review Support

Project Goal: To continue to coordinate with the SCOTE ITS Warrants Review Task Force and other review committees for periodic review of the ITS Warrants. The project will also continue to maintain the ITS Warrants documentation, develop additional warrants for ITS devices and conduct outreach to promote use of the warrants.

* January 2015 – ENTERPRISE and FHWA worked together to develop a scope of work to develop guidance for connected vehicle pre-deployment.
* February 11, 2015 – A call was held with FHWA to review the draft scope of work for connected vehicle pre-deployment guidelines. It was agreed that ENTERPRISE should develop a ‘pilot’ connected vehicle guideline with funds available through Project 15. After the ‘pilot’ guideline is developed further steps will be discussed with FHWA on funding additional connected vehicle warrants.
* Project 16: Investigating Distribution Mechanisms for ENTERPRISE Technical Products

Project Goal: To investigate mechanisms (e.g. libraries and databases) for distribution of ENTERPRISE Final Reports, exploring requirements, procedures, and related costs that would be involved if the wider distribution mechanisms were selected and to facilitate discussions among ENTERPRISE Board members to discuss the dissemination mechanisms and debate the benefits vs. costs and ultimately to determine if any additional distribution should be pursued.

* Project completed. Project summary report available at: <http://www.enterprise.prog.org/Projects/2014/technical_products.html>
* Project 17: ICWS Support and Outreach

Project Goal: To provide support to ENTERPRISE members seeking to deploy ICWS, to support peer exchange webinars on ICWS topics, conduct ICWS outreach and support coordination with national standards groups, industry associations and other pooled fund programs that have been engaged through the ENTERPRISE ICWS work.

* January 2015 – First group webinar was planned for 2/26 and it is titled, “ICWS 101.” It will feature Ken Hansen, MnDOT, as the keynote presenter providing an introduction to ICWS. Contacted ELCSI about co-hosting second group webinar in April featuring ICWS CMF. ICWS briefing was prepared for Kansas and plans were confirmed for introductory presentation at Kansas Traffic Engineering Conference on 4/15.
* February 2015 – ICWS 101 webinar was held on 2/26 with 68 participants. Plans have been confirmed for second group webinar with ELCSI on 4/23. Webinar will feature Scott Himes, VHB, sharing results of national safety effectiveness evaluation and CMF for ICWS. Additional contact was made with ENTERPRISE members regarding individual
* March 2015 – Details for second webinar on 4/23 have been confirmed with ELCSI. Plans and outline for third webinar on 6/24 have been developed with Jon Jackels, SRF Consulting. Presentation and plans finalized for Kansas Traffic Engineering Conference. ICWS brochure outline has been developed.
* Project 18: Countermeasures for Wrong Way Driving on Freeways (Wrong Way Vehicles and Freeways)

Project Goal: Create a matrix of wrong way systems being tested and developed by building off previous related projects and research. The matrix will include details of the wrong way system (e.g. location of wrong way system, type of system deployed, data being collected). The project will also track research results of each deployment. By tracking the deployments, this project will seek to understand which approaches have the greatest impacts, which are socially acceptable, and which have institutional issues.

* February and March – Task 2 is underway. Interviews to collect information about active wrong way deployments have been conducted with the following agencies: Arizona DOT, Central Florida Expressway Authority, Connecticut DOT, Michigan DOT, Missouri DOT, Rhode Island DOT, Texas DOT, Washington State DOT, and Wisconsin DOT.
* Project 19: Performance Measures and Reporting

Project Goal: Research and summarize the implications of performance-based management, current practices among agencies that have established performance efforts, and then document a series of case studies where technologies are used to collect and analyze performance.

* January 2015 – Original scope was reviewed with board and options for revising the scope were presented for board consideration.
* February 2015 – Scope revisions were emailed to board and no further comments were received.
* March 2015 – Scope revisions presented to board, along with options to 1. Cancel project, 2. Proceed with revised focus on targets and decision-making, or 3. Develop additional scope options. Board requested additional scope options (e.g. border crossing performance measures) for discussion at annual meeting.
* Project 20: Integrating ITS with Planning and Operations (ITS Operational Plans and Resources and Decision Tree for Planners)

Project Goal: This project will assess what guidance exists for including ITS in operational plans. Such guidance can be used to describe the placement of IT devices, who will operate, maintain and own them, and how the devices will be used in daily or other operational scenarios.

* January 2015 – Project Authorized 1.8.15
* February 2015 – Confirmed plans for 4/7 working meeting to kick off project prior to board annual meeting.
* March 2015 – Initiated research. Prepared agenda and materials for 4/7 working meeting.
* Project 21: Traffic Safety and Traveler Information Mobile Apps

Project Goal: To research and document a current snapshot of the safety and traveler information apps available and the potential benefits and services they provide to users. Based on the research found identify the role of DOT’s with apps and app standards.

* January and February 2015 – Reviewed and documented traffic safety and traveler information apps.
* March 2015 – Presented traffic and safety traveler information apps reviewed for the project to the ENTERPRISE Board. Distributed Milestone 1: Matrix of Safety and Traveler Information Apps that summarizes the apps reviewed for the project. Started to interview DOTs to document the motivation behind the development and operation of apps.
* Project 22: Communications to Support Rural ITS

Project Goal: To conduct a literature search of rural communications issues and solutions and complete a RFI.

* February 2015 – Project kick off held during February Board Meeting.
* March 2015 – Scheduled and conducted interviews with DOTs to document lessons learned, successes and challenges with rural communications.

**Anticipated work next quarter:**

Administrative/Management Support Task:

* Monthly webinars will be held in May and June.
* In person meeting will be held in April 2015 in Arizona.

Technical Task:

* Additional projects from the 2013-2015 Work Plans will begin to commence during the next quarter.
* Continue to complete project tasks for the active work plan projects.

**Significant Results:**

Projects authorized:

* Project 20: Integrating ITS with Planning and Operations

Projects completed:

* Project 16: Investigating Distribution Mechanisms for ENTERPRISE Technical Products

**Circumstance affecting project or budget (Describe any challenges encountered or anticipated that might affect the completion of the project within the time, scope, and fiscal constraints set forth in the agreement, along with recommended solutions to those problems).**

N/A