|  | OREGON DEPARTMENT OF TRANSPORTATION SPR Quarterly Progress Report 4/1/16 through 6/30/16 | Research Section Mill Creek Building 555 13th Street, Salem, OR 97301 ph: 503-986-2700 fax: 503-986-2844 |
| --- | --- | --- |

Date:	Monday, June 27, 2016

TO:	Technical Advisory Committee (TAC) Members:

Bruce Johnson (Chair), Oregon State Bridge Engineer, 		ph: (503) 986-3344

Email Bruce.V.johnson@odot.state.or.us

Jon Lazarus, Lead Agency Contact (Oregon),	 		ph: (503) 986-2852

Email jon.m.lazarus@odot.state.or.us

Bijan Khaleghi, Washington State Bridge Design Engineer, 	ph (360) 705-7181

Email	KhalegB@wsdot.wa.gov

Michael Knapp, Alaska Statewide Hydraulics Engineer, 	ph: (907) 465-8893

Email: michael.knapp@alaska.gov

Dean Takiguchi, Hawaii State Bridge Engineer			ph (808) 692-7614

Email: Dean.Takiguchi@hawaii.gov

Tom Shantz, California State Bridge Engineer,			ph: (916) 207-8841

Email: tom.shantz@dot.ca.gov

Sheila Duwadi, FHWA,	 				ph (202) 493-3106

Email sheila.duwadi@dot.gov
	Mr Michio Osumi, PWRI (Japan)				ph ()

Email: m-oosumi@pwri.go.jp

FRIENDS OF THE TAC:

Albert Nako, ODOT Seismic Standards		albert.nako@odot.state.or.us

Kornel Kerenyi, FHWA Turner Fairbanks		Kornel.Kerenyi@dot.gov

Rich Pratt, Alaska					richard.pratt@alaska.gov

Elmer Marx, Alaska					elmer.marx@alaska.gov

Tom Ostrom, Caltrans					tom.ostrom@dot.ca.gov

Kevin Baskin, BC					Kevin.Baskin@gov.bc.ca

Solomon Yim, OSU					yims@ENGR.ORST.EDU

Michael Scott, OSU					michael.scott@oregonstate.edu

Ian Buckle, UNR					igbuckle@unr.edu

Marc Eberhard, UW					eberhard@u.washington.edu

Michael Motley, UW					mrmotley@uw.edu

Steve Mahin, PEER					mahin@berkeley.edu

Mark Yashinski, Caltrans, 				mark.yashinsky@dot.ca.gov

FROM:	Patrick Lynett, PEER Project Manager, Professor Coastal Engineering @ USC

Ph (213) 740-3133				Email: plynett@usc.edu

And

Yousef Bozorgnia, Executive Director, PEER, University of California Berkley

Ph (510) 642-3489				Email: yousef@berkeley.edu

1. 	Project

Validation of Tsunami Design Guidelines for Coastal Bridges

SPR 	TPF 5(307)

Project Description

The functionality and survivability of coastal bridges under earthquake and tsunami excitations is a major concern of western US states.  A significant number of these bridges are vital to the emergency first response transportation of coastal cities immediately after a Cascadia Subduction Zone earthquake or other major earthquake events that generate tsunami waves in the Pacific Ocean, which will likely be followed by a local tsunami 15 to 60 minutes afterward.  At least two numerical studies sponsored by California and Oregon of tsunami loads on a number of coastal bridges have been completed or nearly completed. Several studies have also been conducted on the effects of the “Great Japan Earthquake” of 2011 by Japanese research institutes as well as at UNR.  Significant progress in the development of a tsunami design guideline has been made and the results appear promising. However, the reliability of the numerical results is unknown at this point due to a lack of experimental data needed for verification and validation.  Thus, it is essential that experiments be conducted to provide data to verify and validate the numerical results to assess the accuracy of the load prediction equations.  When validated, the numerical model can then be used to further improve the numerical analysis and development of practice design guidelines.

2.	Key Dates

Start Date for ODOT:					April 16, 2015 (contract execution)

Completion Date for ODOT:				June 30, 2018

3.	Principal Investigator and Teams

Patrick Lynett, Project Manager	plynett@usc.edu			213-740-3133

Yousef Bozorgnia, PEER		yousef@berkeley.edu			510-642-3489

Jon Lazarus, Lead Agency Contact	jon.m.lazarus@odot.state.or.us 	503-986-2852

Hong Kie Thio, 			hong.kie.thio@aecom.com		213-996-2250

Michael Scott				michael.scott@oregonstate.edu	541-737-6996

Tom Murphy								    717-790-9565 x425

Tom Shantz									916-227-7245

Relationship/Project Chart

Planned Project Schedule

4.	Progress

| Working Group 1: Tsunami Hazard and Mapping | 30% of total project |
| --- | --- |
| Percent completed reported in last quarterly report: | 25% |
| Percent completed after this quarter: | 50% |

Key Progress-To-Date

WG1 has reviewed the current status of tsunami hazard databases, including the up-to-date progress of the ASCE7 inundation maps.  Preliminary conclusions of these efforts indicate that uncertainties in any one model can be very large for a local velocity prediction, but that using an ensemble approach (either many trials of the same model or using different models) can yield a more stable and thus higher confidence result.

Although there are some limited efforts underway in various states to produce tsunami hazard maps, we find that the procedures and input models are far from uniform and also not consistent with the ASCE maps. Therefore, to produce the 1000 year design maps, we are currently comparing and calibrating our inundation models using 30-60m grids for 2500 years to those produced by NOAA for ASCE 7-16. Once we have established a good correlation between our results and the ASCE 7-16 inundation zones, we will be able to proceed with the development of 1000 year inundation maps that are consistent with the procedures used to create the 2500 years ASCE maps.

WG1 has begun to investigate the available alternatives for site-specific hydrodynamic predictions.  In particular, the use of transect models is being pursued.  While numerical model base transect analysis (i.e. not using the Energy Grade Line method) would be preferred, some infrastructure is needed to maintain and disperse such tools.

- WG1 has collected high-resolution bathymetry data for the western states from a variety (mostly NOAA-based) sources. An overview map of these areas has been distributed to the panel for review.

- WG1 has received some input (from Oregon) regarding target areas with rankings. The intent is to model most areas with 30m resolution, but to use 10m resolution for the top-tier locations. Setup for these areas is now underway.

- [NEW]: A PEER-based project to develop the necessarily infrastructure to host transect modeling tools has initiated.  Lynett and PEER research Silvia Mazzoni have begun discussions about the project framework

- [NEW]: A report discussing the uncertainties in modeling overland tsunami flow has initiated

- [NEW]: Lynett has begun to construct a methodology for determining the site-specific tsunami hazard

Problems

- [NEW]: The project team has experienced delays in determining if and where additional high resolution numerical modeling is needed

Work Planned for Next Quarter

Building database of tsunami hazard maps [TASK WG1.1]

  - Check with the remaining stakeholders regarding areas of interest for modeling

  - Developing new maps at the 1000-yr hazard level, developing using a mix of the “scaling” approach and new modeling in selected locations

  - Task completion expected 10/16

- Quantification and inclusion of uncertainties in the onshore propagation and other uncertainties not formally or rigorously included in the ASCE7 probabilistic maps [TASK WG1.2]

  - Will be based on ongoing work by the PEER Tsunami group (PTG)

  - With the results from the PEER project, some discussion in WG1 will be needed in order to determine a method to incorporate this uncertainty on a site-specific basis

  - Task completion expected 10/16

- Method to provide the hydrodynamic information needed (max, mins, time series, etc) for design using the ASCE7 maps as input [TASK WG1.3]

  - Options include using the Energy Method (ASCE7) or some Numerical Model Transect tool in the general vicinity of the structure

  - Easiest path will be to use the ASCE7 Energy method

  - Will require WG1 consensus, and review/discussion with WG2

  - Task completion expected 10/16

| Working Group 2: Tsunami Loading of Bridges | 30% of total project |
| --- | --- |
| Percent completed reported in last quarterly report: | 8% |
| Percent completed after this quarter: | 15% |

Key Progress-To-Date

Literature review of available experimental data is complete.  This includes tsunami bore impact on bridge decks at PWRI in Japan; tsunami bore impact on bridge decks at OSU (with UNR); and tsunami bore impact on bridge columns at UW.  Additional data is available from experiments on storm surge loading of bridge decks at OSU.  While this is not tsunami bore impact, the data will provide additional confidence in simulation models.  Data for tsunami bore impact on buildings (experiments at OSU) will be available in the coming months and will also provide increased confidence of simulation models.  With the NSF-funded NHERI system coming online this year and the awarding of OSU’s wave research lab as an experimental facility, more data will likely become available during the project.

New additions to the literature review in light of presentation by Denis Istrati and Ian Buckle at the PEER annual meeting in late January.  Additional experimental data will thus be available for this project.  Review of analytical methods is nearing completion.

[NEW]: Detailed comparisons made between PWRI experiments and participant submissions from the 2014 OSU Tsunami Bridge Modeling workshop.

[NEW]: Simulations carried out (by Motley at UW) in 3D using OpenFOAM to investigate the distribution of forces in bridges with various amounts of skew, slope, and super-elevation.  This should help guide the design of any additional experiments.

Problems

- N/A

Work Planned for Next Quarter

- TAC meeting and WG2 workshop on the OSU campus organized for July 21-22.  The objective of the workshop is to determine gaps in knowledge for numerical simulation of tsunami loads on bridges to a) determine what model refinements are necessary and to b) determine if additional experiments are needed in order to increase our confidence in the numerical models.

- Continue detailed analyses of simulation results from 2014 OSU workshop

- Continue 3D simulations to look at effects of bridge geometry

- Compare available tsunami loading equations with data from PWRI experiments and determine if refinements are necessary

- Document and make plans to fill knowledge gaps identified at WG2 workshop in July 2016

| Working Group 3: Bridge Detailing for Tsunami Loads | 3% of total project |
| --- | --- |
| Percent completed reported in last quarterly report: | 0% |
| Percent completed after this quarter: | 0% |

Key Progress-To-Date

N/A

Problems

- N/A

Work Planned for Next Quarter

Efforts in WG3 are scheduled to initiate in July, 2017

| Working Group 4: Geotechnical Issues (Scour and drawdown induced liquefaction) | 4% of total project |
| --- | --- |
| Percent completed reported in last quarterly report: | 0% |
| Percent completed after this quarter: | 0% |

Key Progress-To-Date

N/A

Problems

- N/A

Work Planned for Next Quarter

Efforts in WG4 are scheduled to initiate in April, 2017

| Working Group 5: Guide Specifications for Bridge Design for Tsunami Hazard | 33% of total project |
| --- | --- |
| Percent completed reported in last quarterly report: | 0% |
| Percent completed after this quarter: | 0% |

Key Progress-To-Date

N/A

Problems

- N/A

Work Planned for Next Quarter

Efforts in WG5 are scheduled to initiate in October, 2016

| CONTINGENCY PLAN FOR DEVELOPING 1000-YR HAZARD MAPS | 0% |
| --- | --- |
| Percent completed reported in last quarterly report: | 0% |
| Percent completed after this quarter: | 0% |

Key Progress-To-Date

Problems

Work Planned for Next Quarter

There is currently no identified need or authorization to proceed with the development of these hazard maps

7.	Finances

SPR Project Summary

8.	Project Summary (Completed by ODOT)

SPR Project Summary

| State | Commitment | Transferred | Comments |
| --- | --- | --- | --- |
|  | FY15 | FY16 | FY17 | FY18 | Total | FY15 | FY16 | FY17 | FY 18 | Total |  |
| Alaska | 25000 | 25000 | 25000 |  | 75000 | 25000 | 25000 | 25000 |  | 75000 | $75,000 in 3 payments of $25,000 starting in 2013 (recommitted by e-mail May 2014) |
| Oregon | 20000 | 120000 | 20000 | 20000 | 180000 | 20000 | 120000 | 20000 | 20000 | 180000 | $60,000 in 3 payments of $20,000 starting in 2014. Payments will be increased to cover research coordinator's time. 5/12/15 an additional 100,000 was committed by the ODOT bridge section. |
| FHWA |  |  |  |  | 100000 | 100000 |  |  |  | 100000 | $100,000 allocated by FHWA memo from HIBT may 2014 |
| Hawaii | 20000 | 20000 | 20000 |  | 60000 | 20000 |  |  |  | 20000 | E-mail intent to contribute $60,000 in 3 payments starting in 2014 (recommitted by e-mail May 2014) |
| Washington | 20000 | 20000 | 20000 |  | 60000 | 20000 | 20000 | Pend-ing |  | 40000 | E-mail intent to contribute $60,000 in three payments of $20,000 starting in 2015 (recommitted by phone call May 2014) |
| California | 20000 | 20000 | 20000 |  | 60000 | 20000 | 20000 | 20000 |  | 60000 |  |
|  |  |  |  |  | $535,000 |  |  |  |  | $475,000 |  |

# Text boxes

Technical Advisory Committee,

Chair Jon Lazarus

Patrick Lynett, PM and

Yousef Bozorgnia

Working Group 1, Tsunami Hazard and Mapping, Lead Hong Kie Thio

Working Group 2, Tsunami Loading of Bridges,

Lead Michael Scott

Working Group 3, Bridge Detailing for Tsunami Loads, Lead Tom Murphy

Working Group 4, Geotechnical Issues,

Lead Tom Shantz

Working Group 5, Guide Specifications for Bridge Design, Lead Tom Murphy