**TRANSPORTATION POOLED FUND PROGRAM**

**QUARTERLY PROGRESS REPORT**

Date: 5 July 2017

Lead Agency : Louisiana Department of Transportation & Development

**INSTRUCTIONS:**

*Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active. Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any. List all tasks, even if no work was done during this period.*

|  |  |  |  |
| --- | --- | --- | --- |
| **Transportation Pooled Fund Program Project #**  *(i.e, SPR-2(XXX), SPR-3(XXX) or TPF-5(XXX)*  TPF-5(273) | | **Transportation Pooled Fund Program - Report Period:**  □Quarter 1 (January 1 – March 31)  X Quarter 2 (April 1 – June 30)  □Quarter 3 (July 1 – September 30)  □Quarter 4 (October 1 – December 31) | |
| **Project Title:**  **Latin American Trade and Transportation Studies** | | | |
| **Name of Project Manager(s):**  **Dennis Decker** | **Phone Number:**  (225) 379-1787 | | **E-Mail**  **Laura.Phillips@la.gov** |
| **Lead Agency Project ID:**  **13-ITTS** | **Other Project ID (i.e., contract #):**  **2000004871/H.005319.5** | | **Project Start Date:**  **1 Dec 2012** |
| **Original Project End Date:**  **30 Jun 2017** | **Current Project End Date:**  **30 Jun 2017** | | **Number of Extensions:**  **0** |

Project schedule status:

x On schedule □ On revised schedule □ Ahead of schedule □ Behind schedule

Overall Project Statistics:

|  |  |  |
| --- | --- | --- |
| **Total Project Budget** | **Total Cost to Date for Project** | **Percentage of Work**  **Completed to Date** |
| $1,519,083 |  |  |

***Quarterly*** Project Statistics:

|  |  |  |
| --- | --- | --- |
| **Total Project Expenses**  **and Percentage This Quarter** | **Total Amount of Funds**  **Expended This Quarter** | **Total Percentage of**  **Time Used to Date** |
|  |  |  |

|  |
| --- |
| **Project Description**:  **OBJECTIVES:**  The purpose of ITTS is to estimate trade volumes with Latin America and other international trade, evaluate infrastructure investments needed to support growth in international trade, and develop strategies to guide infrastructure investments. The overall goal is to help the Southeastern Transportation Alliance states develop their competitive advantages to capture trade opportunities and the associated economic benefits.    The scope of work will consist of, but not be limited to, the following:   * Update the Latin America Trade and Transportation Study but expand to include all international trade. * Organize and facilitate workshops attended by ITTS member states to review trade forecasts and freight flows, and to present and compare member state transportation plans to ensure proper coordination. * Organize and sponsor an annual “Freight in the Southeast” conference to provide a continuing education and peer exchange opportunity for member states. * Within budgetary allowances, provide support to member states such as speaking at member state conferences, offering expert advice, etc. * Provide technical assistance in meeting the requirements of MAP-21 including but not limited to State Freight Plans, Freight networks and identifying Regional Freight corridors. |

|  |
| --- |
| **Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.):**  Network  Data   * Meet with Louisiana DOTD to present Tableau training * Compiled all the data into Tableau formats. Began working on training packages. * Integrated the LATTS network into Tableau.   Discussed data integration work for States. Posted County Business Pattern Database, Freight Analysis Framework, State and National Gross Domestic Product, Population and SHIFT OD Patterns  Meetings   * ITTS Peer Meeting in Irvine, CA-organized, attended, and hosted an ITTS Peer meeting in conjunction with the “Innovations in Freight Data Workshop” * Organized conference call with FHWA to discuss State Freight Plans. Conference call materials were posted online. <http://www.ittsresearch.org/stateplanning.html> * Attended local meetings with various transportation groups in New Orleans   Communications   * ITTS newsletters * Working on developing ITTS Youtube channel * Received 3-D Paper- resubmitted to editor * ITTS Freight in the Southeast Conference Summary published   Service to States   * Participated in Mississippi Freight Advisory Council Meeting * Invited travel to Arkansas for a presentation and training * Meet with Virginia DOT * Meet with Georgia DOT |
| **Anticipated work next quarter**:  Network      Data   * Finish ITTS Training for states for Tableau   Meetings   * Finish all training for states related to FEAT Model   Communications   * Publish Container on Barge/Over-dimensional freight paper * Publish paper on 3d Printing   Service to States |
|  |

|  |
| --- |
| **Significant Results:**     * Organized ITTS Peer Meeting in conjunction with TRB “Innovations in Freight Data Workshop”. |
| **Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that**  **might affect the completion of the project within the time, scope and fiscal constraints set forth in the**  **agreement, along with recommended solutions to those problems).** |

|  |
| --- |
| **Potential Implementation:** |