**TRANSPORTATION POOLED FUND PROGRAM**

**QUARTERLY PROGRESS REPORT**

**Lead Agency: Utah Department of Transportation**

**INSTRUCTIONS:**

*Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active. Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any. List all tasks, even if no work was done during this period.*

|  |  |  |  |
| --- | --- | --- | --- |
| **Transportation Pooled Fund Program Project #**  **TPF-5(338)** | | **Transportation Pooled Fund Program - Report Period:**  **x Quarter 1 (January 1 – March 31, 2018)**  \_ Quarter 2 (April 1 – June 30, 2018)  \_ Quarter 3 (July 1 – September 30, 2018)  \_ Quarter 4 (October 1 – December 31, 2018) | |
| **Project Title:**  Simplified CPT Performance-Based Assessment of Liquefaction and Effects | | | |
| **Name of Project Manager(s):**  David Stevens | **Phone Number:**  801-589-8340 | | **E-Mail**  [davidstevens@utah.gov](mailto:davidstevens@utah.gov) |
| **Lead Agency Project ID:**  FINET 42074, ePM PIN 14239  UDOT PIC No. UT15.402 | **Other Project ID (i.e., contract #):**  UDOT Contract No. 169826 | | **Project Start Date:**  May 17, 2016 |
| **Original Project End Date:**  November 30, 2018 | **Current Project End Date:**  May 31, 2019 | | **Number of Extensions:**  1 |

Project schedule status:

\_ On schedule **X** On revised schedule \_ Ahead of schedule \_ Behind schedule

Overall Project Statistics:

|  |  |  |
| --- | --- | --- |
| **Total Project Budget** | **Total Cost to Date for Project** | **Percentage of Work**  **Completed to Date** |
| $142,000.00 (current contract)  $142,000.00 (total commitments) | $74,250.00 | 60% |

***Quarterly*** Project Statistics:

|  |  |  |
| --- | --- | --- |
| **Total Project Expenses**  **and Percentage This Quarter** | **Total Amount of Funds**  **Expended This Quarter** | **Total Percentage of**  **Time Used to Date** |
| 0% | $0.00 | 65% |

|  |
| --- |
| **Project Description**:  Conventional “pseudo-probabilistic” procedures to evaluate liquefaction triggering and its effects have been shown through recent research to produce estimates of liquefaction factor of safety at inconsistent and often unacceptable levels of risk. These errors are introduced through the incorrect assumption that using probabilistic ground motions in a deterministic liquefaction analysis will yield a probabilistic estimate of liquefaction factor of safety. The inconsistent consideration of liquefaction risk could contribute to undesirable performance or even collapse of various important structures such as bridges or retaining walls in the event of an earthquake. Conversely, the inconsistent consideration of liquefaction risk could also potentially contribute to the unnecessary and expensive over-design of liquefaction mitigation alternatives. Utilization of a fully-probabilistic or performance-based liquefaction triggering procedure, which considers both uncertainty in the seismic loading and the liquefaction triggering relationship, could effectively solve these problems. Furthermore, probabilistic evaluation of liquefaction triggering could potentially be taken into account when considering liquefaction effects such as lateral spreading or free-field liquefaction settlements. However, current performance-based liquefaction procedures (e.g. Kramer & Mayfield 2007) are quite complex and beyond the level of practical application for most practicing engineers. Additionally, available performance-based methods generally focus on using the standard penetration test (SPT). Increasingly, the cone penetration test (CPT) is becoming a preferred instrument for performing in-situ assessment of liquefaction hazard. Development of code-compatible simplified approximations of performance-based analysis methods for the CPT to assess liquefaction triggering and its effects could be a viable solution to overcome these challenges.  Objectives for this study include:  1. Develop performance-based procedures for the CPT modeled after recent performance-based procedures for the SPT to compute the hazard from liquefaction triggering, lateral spread displacement, and post-liquefaction free-field settlement at select return periods (475, 1033, and 2475 years).  2. Develop simplified performance-based procedures for the CPT modeled after recent simplified performance-based procedures for the SPT to closely approximate the performance-based analysis results for liquefaction triggering, lateral spread displacement, and post-liquefaction free-field settlement at select return periods (475, 1033, and 2475 years).  3. Develop liquefaction triggering, lateral spread displacement, and post-liquefaction reference parameter maps in GIS format at return periods of 475 years, 1033 years, and 2475 years for each of the states participating in the study.  Contract tasks for this study include, regarding the participating states:  1. Develop full performance-based liquefaction triggering procedure  2. Develop full performance-based lateral spread procedure  3. Develop full performance-based post-liquefaction, free-field settlement procedure  4. Develop a numerical tool that will allow the calculation of performance-based liquefaction triggering, post-liquefaction settlement, and lateral spread displacement  5. Derivation and validation of a new simplified liquefaction triggering procedure  6. Derivation and validation of a new simplified lateral spread displacement procedure  7. Derivation and validation of simplified post-liquefaction free-field settlement procedure  8. Development of liquefaction reference parameter maps  9. Comparison of simplified, conventional (AASHTO), and deterministic analysis methods  10. Development of a simplified design procedure that incorporates both performance-based and conventional methods  11. Preparation of the Annual and Final Reports  12. Dissemination of Results  13. Technical Advisory Committee (TAC) Meetings  Dr. Kevin Franke of BYU is the Principal Investigator for this research project. The technical advisory committee (TAC) for the study currently includes representatives from UT, CT, OR, and SC state DOTs. |

|  |
| --- |
| **Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.):**  **Task 1** – 100% complete.  **Task 2** – 100% complete.  **Task 3** – 100% complete.  **Task 4** – 100% complete. Posted final versions of the Year 1 Quarter 3 report (April 2017 TAC Update Report - Task 4) and the Year 1 Quarter 4 update report (June 2017 TAC Update Report - Tasks 1-4) to the pooled fund study webpage.  **Task 5** – 95% complete.  **Task 6** – 50% complete.  **Task 7** – 90% complete.  **Task 8** – No work yet.  **Task 9** – No work yet.  **Task 10** – No work yet.  **Task 11** – 50% complete.  **Task 12** – No work yet.  **Task 13** – 30% complete.  **Contract** – No changes. |
| **Anticipated work next quarter**:  **Task 1** – Completed.  **Task 2** – Completed.  **Task 3** – Completed.  **Task 4** – Completed.  **Task 5** – Focus on this task.  **Task 6** – Focus on this task.  **Task 7** – Focus on this task. Prepare the Year 2, Quarter 1 update report.  **Task 8** – None.  **Task 9** – None.  **Task 10** – None.  **Task 11** – Continue report preparation.  **Task 12** – Begin preparation of two or three journal papers.  **Task 13** – Consider holding another TAC web-conference to review and discuss additional results from the study.  **Contract** – No changes planned. |

|  |
| --- |
| **Significant Results:**  Focus this quarter was on the validation and testing of the simplified performance-based liquefaction triggering and post-liquefaction settlement methods. Calibration functions were tested and derived to produce the best possible approximation of full performance-based results using the simplified method. In comparing the full performance-based results with the simplified performance-based results, there is generally a 1:1 relationship with R2 values exceeding 0.9 for all the models tested. |
| **Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that**  **might affect the completion of the project within the time, scope and fiscal constraints set forth in the**  **agreement, along with recommended solutions to those problems).**  This project has also been affected by several delays in the availability and the functionality of the new USGS Uniform Hazard Tool used to obtain deaggregation values, thus the change in contract end date. Now that the tool is available, the study is progressing at a good pace. However, we discovered a bug in our analysis towards the end of January 2018 in the USGS offline deaggregation tool which required attention from the USGS to fix. We have received word that the bug is fixed, and we are in the process of modifying CPTLiquefY to be able to process the new USGS deaggregation output files. In addition, one of the BYU students on this project has had some health issues, and this has slowed down our progress on the project. However, two other graduate students are working on this project, and they are seeing great results with the CPT liquefaction assessment method. |

|  |
| --- |
| **Potential Implementation:**  While CPTLiquefY could be implemented in design, it is not recommended because it was developed to serve as a research tool. A simplified spreadsheet will be developed as part of the research later in Year 2 of the study, and will be useful for practical implementation of the performance-based methods in engineering practice. The procedures that are currently being developed will be those that will be implemented in this spreadsheet. |