|  | OREGON DEPARTMENT OF TRANSPORTATION SPR Quarterly Progress Report 10/1/17 through 12/31/17 | Research Section Mill Creek Building 555 13th Street, Salem, OR 97301 ph: 503-986-2700 fax: 503-986-2844 |
| --- | --- | --- |

Date:	Monday, June 27, 2016

TO:	Technical Advisory Committee (TAC) Members:

Bruce Johnson (Chair), Oregon State Bridge Engineer, 	ph: (503) 986-3344

Email Bruce.V.johnson@odot.state.or.us

Jon Lazarus, Lead Agency Contact (Oregon),	 		ph: (503) 986-2852

Email jon.m.lazarus@odot.state.or.us

Bijan Khaleghi, Washington State Bridge Design Engineer, 	ph (360) 705-7181

Email	KhalegB@wsdot.wa.gov

Michael Knapp, Alaska Statewide Hydraulics Engineer, 	ph: (907) 465-8893

Email: michael.knapp@alaska.gov

Dean Takiguchi, Hawaii State Bridge Engineer			ph (808) 692-7611

Email: Dean.Takiguchi@hawaii.gov

James Fu, Incoming Hawaii State Bridge Engineer		ph (808) 692-7611

Email: james.fu@hawaii.gov

Tom Shantz, California State Bridge Engineer,			ph: (916) 207-8841

Email: tom.shantz@dot.ca.gov

Sheila Duwadi, FHWA,	 					ph (202) 493-3106

Email sheila.duwadi@dot.gov
	Mr Michio Osumi, PWRI (Japan)					ph ()

Email: m-oosumi@pwri.go.jp

FRIENDS OF THE TAC:

Albert Nako, ODOT Seismic Standards		albert.nako@odot.state.or.us

Kornel Kerenyi, FHWA Turner Fairbanks		Kornel.Kerenyi@dot.gov

Rich Pratt, Alaska					richard.pratt@alaska.gov

Elmer Marx, Alaska					elmer.marx@alaska.gov

Tom Ostrom, Caltrans					tom.ostrom@dot.ca.gov

Kevin Baskin, BC					Kevin.Baskin@gov.bc.ca

Solomon Yim, OSU					yims@ENGR.ORST.EDU

Michael Scott, OSU					michael.scott@oregonstate.edu

Ian Buckle, UNR					igbuckle@unr.edu

Marc Eberhard, UW					eberhard@u.washington.edu

Michael Motley, UW					mrmotley@uw.edu

Mark Yashinski, Caltrans, 				mark.yashinsky@dot.ca.gov

FROM:	Patrick Lynett, PEER Project Manager, Professor Coastal Engineering @ USC

Ph (213) 740-3133				Email: plynett@usc.edu

And

Amarnath Kasalanati, Executive Director, PEER, University of California Berkley

Ph (510) 642-6475				Email: amarnath1@berkeley.edu

1. 	Project

Validation of Tsunami Design Guidelines for Coastal Bridges

SPR 	TPF 5(307)

Project Description

The functionality and survivability of coastal bridges under earthquake and tsunami excitations is a major concern of western US states.  A significant number of these bridges are vital to the emergency first response transportation of coastal cities immediately after a Cascadia Subduction Zone earthquake or other major earthquake events that generate tsunami waves in the Pacific Ocean, which will likely be followed by a local tsunami 15 to 60 minutes afterward.  At least two numerical studies sponsored by California and Oregon of tsunami loads on a number of coastal bridges have been completed or nearly completed. Several studies have also been conducted on the effects of the “Great Japan Earthquake” of 2011 by Japanese research institutes as well as at UNR.  Significant progress in the development of a tsunami design guideline has been made and the results appear promising. However, the reliability of the numerical results is unknown at this point due to a lack of experimental data needed for verification and validation.  Thus, it is essential that experiments be conducted to provide data to verify and validate the numerical results to assess the accuracy of the load prediction equations.  When validated, the numerical model can then be used to further improve the numerical analysis and development of practice design guidelines.

2.	Key Dates

Start Date for ODOT:			April 16, 2015 (contract execution)

Completion Date for ODOT:			June 30, 2018 (Amended to Dec 30, 2018)

3.	Principal Investigator and Teams

Patrick Lynett, Project Manager	plynett@usc.edu			213-740-3133

Jon Lazarus, Lead Agency Contact	jon.m.lazarus@odot.state.or.us 	503-986-2852

Hong Kie Thio, 			hong.kie.thio@aecom.com		213-996-2250

Michael Scott				michael.scott@oregonstate.edu	541-737-6996

Tom Murphy				TPMurphy@modjeski.com		717-790-9565 x425

Tom Shantz				tom.shantz@dot.ca.gov		916-227-7245

Relationship/Project Chart

Planned Project Schedule

4.	Progress

| Working Group 1: Tsunami Hazard and Mapping | 30% of total project |
| --- | --- |
| Percent completed reported in last quarterly report: | 90% |
| Percent completed after this quarter: | 90% |

Key Progress-To-Date

WG1 has reviewed the current status of tsunami hazard databases, including the up-to-date progress of the ASCE7 inundation maps.  Preliminary conclusions of these efforts indicate that uncertainties in any one model can be very large for a local velocity prediction, but that using an ensemble approach (either many trials of the same model or using different models) can yield a more stable and thus higher confidence result.

Although there are some limited efforts underway in various states to produce tsunami hazard maps, we find that the procedures and input models are far from uniform and also not consistent with the ASCE maps. Therefore, to produce the 1000 year design maps, we are currently comparing and calibrating our inundation models using 30-60m grids for 2500 years to those produced by NOAA for ASCE 7-16. Once we have established a good correlation between our results and the ASCE 7-16 inundation zones, we will be able to proceed with the development of 1000 year inundation maps that are consistent with the procedures used to create the 2500 years ASCE maps.

WG1 has begun to investigate the available alternatives for site-specific hydrodynamic predictions.  In particular, the use of transect models is being pursued.  While numerical model base transect analysis (i.e. not using the Energy Grade Line method) would be preferred, some infrastructure is needed to maintain and disperse such tools.

- WG1 has collected high-resolution bathymetry data for the western states from a variety (mostly NOAA-based) sources. An overview map of these areas has been distributed to the panel for review.

- WG1 has received some input (from Oregon) regarding target areas with rankings. The intent is to model most areas with 30m resolution, but to use 10m resolution for the top-tier locations. Setup for these areas is now underway.

- In preparation for the inundation mapping, WG1 has finalized the 1000yr offshore hazard waveheights for areas outside California.

- A report discussing the uncertainties in modeling overland tsunami flow has been delivered to the TAC

- [CONTINUED]: WG1 is finalizing the models for the inundation maps, using 10m for Oregon and 60m for Washington, Alaska and Hawai’i.

- [CONTINUED]: A PEER-based project to develop the necessarily infrastructure to host transect modeling tools is under development.  Lynett and PEER research Silvia Mazzoni have been collaborating on this development.  An initial working example of the transect model and online tool have been created.

- [CONTINUED]: Lynett is has developed a methodology for determining the site-specific tsunami hazard.  Report completion expected shortly after first draft of inundation maps provided.

- [CONTINUED]: Provided draft version of Level 1 analysis tool to the TAC in the form of a set of MatLab scripts.  Final version will be provided, with documentation, once inundation maps are completed.

Problems

- [CONTINUED]: The project team has experienced delays in completing the inundation maps, due to the additional effort required to create the contingency effort maps for Oregon. All remaining WG1 tasks are effectively on hold until maps are completed.

Work Planned for Next Quarter

Building database of tsunami hazard maps [TASK WG1.1]

  - Developing new maps at the 1000-yr hazard level

  - Task completion expected 3/18

- Method to provide the hydrodynamic information needed (max, mins, time series, etc) for design using the inundation maps as input [TASK WG1.3]

  - Report completion expected shortly after first draft of inundation maps provided.

  - Task completion expected one month after maps (task WG1.1) completed

| Working Group 2: Tsunami Loading of Bridges | 30% of total project |
| --- | --- |
| Percent completed reported in last quarterly report: | 60% |
| Percent completed after this quarter: | 70% |

Key Progress-To-Date

Literature review of available experimental data is complete.  This includes tsunami bore impact on bridge decks at PWRI in Japan; tsunami bore impact on bridge decks at OSU (with UNR); and tsunami bore impact on bridge columns at UW.  Additional data is available from experiments on storm surge loading of bridge decks at OSU.  While this is not tsunami bore impact, the data will provide additional confidence in simulation models.  Data for tsunami bore impact on buildings (experiments at OSU) will be available in the coming months and will also provide increased confidence of simulation models.  With the NSF-funded NHERI system coming online this year and the awarding of OSU’s wave research lab as an experimental facility, more data will likely become available during the project.

New additions to the literature review in light of presentation by Denis Istrati and Ian Buckle at the PEER annual meeting in late January.  Additional experimental data will thus be available for this project.  Review of analytical methods is nearing completion.

Detailed comparisons made between PWRI experiments and participant submissions from the 2014 OSU Tsunami Bridge Modeling workshop.

Simulations carried out (by Motley at UW) in 3D using OpenFOAM to investigate the distribution of forces in bridges with various amounts of skew, slope, and super-elevation.  This should help guide the design of any additional experiments.

TAC meeting and WG2 workshop help at OSU July 21-22.  Knowledge gaps were identified along with a proposed loading methodology based on various multipliers of “reference” steady-state hydrodynamic loads that are easily computed from site-specific flow height and velocity information to be provided by WG1.  The primary knowledge gap is how to account for debris in tsunami flow.

Comparisons of available tsunami loading equations with data from PWRI experiments indicate a need for further refinements in tsunami loading equations for bridges

Advanced three-dimensional models developed by Michael Motley at UW for hydrodynamic tsunami loading show the important effects of bridge skew and incident angle of the bridge deck

Provided overview of progress to date and presented at the TAC meeting at Oregon state on Juley 27-27, 2017.

Generated an example calculation for a bridge in OR, using a few different loading equations.  Discussed at TAC meeting

[CONTINUED]  2D and 3D modeling has been initiated to test various loading equations on different types of bridge decks

Problems

- N/A

Work Planned for Next Quarter

- Develop analytical models for “Tier 1” bridges along the Oregon coast (bridge details to be provided by ODOT) and for critical bridges along the Washington coast (bridge details to be provided by WashDOT)

- Perform simulations of UNR experiments conducted at OSU in 2016 in order to investigate the effects of substructure flexibility

- Address gaps noted in the TAC workshop, specifically working towards resolving the following questions:

  - How many different loading equations are needed in the guidespec?

  - Should we specify different load cases, not just a single case with max depth and max u?

  - How is the load distributed across the bridge?

  - How to capture bridge specific effects on loads, such as cross-section types and flexibility?

| Working Group 3: Bridge Detailing for Tsunami Loads | 3% of total project |
| --- | --- |
| Percent completed reported in last quarterly report: | 10% |
| Percent completed after this quarter: | 10% |

Key Progress-To-Date

Initial discussions about the scope, effort, and forward-looking plan took place at the TAC meeting in July, 2017

Problems

- N/A

Work Planned for Next Quarter

Initial efforts to development a detailing document; an outline of the document

| Working Group 4: Geotechnical Issues (Scour and drawdown induced liquefaction) | 4% of total project |
| --- | --- |
| Percent completed reported in last quarterly report: | 10% |
| Percent completed after this quarter: | 10% |

Key Progress-To-Date

Initial discussions about the scope, effort, and forward-looking plan took place at the TAC meeting in July, 2017

Problems

- N/A

Work Planned for Next Quarter

An outline of the expected geotechnical document will be developed

| Working Group 5: Guide Specifications for Bridge Design for Tsunami Hazard | 33% of total project |
| --- | --- |
| Percent completed reported in last quarterly report: | 10% |
| Percent completed after this quarter: | 10% |

Key Progress-To-Date

A draft outline of the guidespec was created, and presented at the TAC meeting in July, 2017

Problems

- N/A

Work Planned for Next Quarter

Continued effort on filling out the draft version of the guidespec

| CONTINGENCY PLAN FOR DEVELOPING 1000-YR HAZARD MAPS | 0% |
| --- | --- |
| Percent completed reported in last quarterly report: | 90% |
| Percent completed after this quarter: | 90% |

Key Progress-To-Date

[CONTINUED] Developing 1000-yr tsunami hazard maps for Oregon

Problems

Work Planned for Next Quarter

[CONTINUED]  Work and quality control checks for these maps will continue

7.	Finances

SPR Project Summary

Total expendatures as of 4/1/2017 = $127,487		Total contract = $435,000.00

Total commitments received = $535,000.00

See March 2018 Quarterly report for financials.

8.	Project Summary (Completed by ODOT)

The amendment was completed on 11/30/2017. See March 2018 Quarterly report for progress reporting.

# Footnotes

This value includes the Oregon contingency work and is identified as not to exceed in Amendment 1 (signed 11/30/2017).

# Text boxes

Technical Advisory Committee,

Chair Bruce Johnson, rep Jon Lazarus

Patrick Lynett, PM and

Yousef Bozorgnia

Working Group 1, Tsunami Hazard and Mapping, Lead

Hong Kie Thio

Working Group 2, Tsunami Loading of Bridges, Lead Michael Scott

Working Group 3, Bridge Detailing for Tsunami Loads, Lead Tom Murphy

Working Group 4, Geotechnical Issues,

Lead

Tom Shantz

Working Group 5, Guide Specifications for Bridge Design, Lead Tom Murphy