8th, 9th and 10th Quarterly Progress Reports

Ohio DOT Research

Eighth, Ninth and Tenth Quarters Ending on June 30, 2020

“Quarterly Report: State Job #31347”

| For Quarter Ending: | June 30, 2020 |
| --- | --- |
| Date Submitted: | July 8, 2020 |

| Project Title: | Structural Design Methodology for Spray Applied Pipe Liners in Gravity Storm Water Conveyance Conduits |
| --- | --- |
| Research Agency: | CUIRE/The University of Texas at Arlington |
| Principal Investigator(s): | PI: Mohammad Najafi, Ph.D., P.E., F. ASCE, Professor and Director, CUIRE Co-PI: Xinbao Yu, Ph.D., P.E., Associate Professor |
| State Job Number: | 5501.03 | Agreement Number: | 31347 |
| Project Start Date: | 20 December 2017 | Contract Funds Approved: | 25 September 2017 |
| Project Completion Date: | 20 December 2020 | Spent to Date: | $441,095.73 |
| % Funds Expended: | 83% | % Work Done: | 90% | % Time Expired: | 83% |

List the ODOT Technical Liaisons and other individuals who should receive a copy of this report:

- Jeffrey E. Syer, P.E. – Ohio DOT

- Brian R. Carmody, P.E. – NYSDOT

- Matthew S. Lauffer, P.E. and Charles Smith P.E. – NCDOT

- Paul Rowekamp and Aislyn Ryan – MnDOT

- Sheri Little – PennDOT

- Carlton Spirio – FDOT

- Jonathan Karam and Nicholas Dean – DelDOT

# Contents

Schedule of Research Activities Tied to  Each Task Defined in the Proposal  and Percentage Completion  of the Research	3

Comparative Status of Actual Versus  Estimated Expenditures	6

Brief Description of the Activities Accomplished by  Each Member of the Research Team as  Listed in the Project Budget	9

Principal Investigator: Dr. Mohammad Najafi	10

Co-Principal Investigator: Dr. Xinbao Yu	11

Subcontractor: Mr. Ed Kampbell Rehabilitation Resource Solutions, LLC	12

Proposed Work for New Quarter	15

Principal Investigator: Dr. Mohammad Najafi	17

Co-Principal Investigator: Dr. Xinbao Yu	18

Subcontractor: Mr. Ed Kampbell Rehabilitation Resource Solutions, LLC	19

Implementation (if any):	22

Problems & Recommended Solutions (if applicable):	22

Equipment Purchased (if any):	22

Contacts and Meetings	23

Progress Meeting	24

# Schedule of Research Activities Tied to 
Each Task Defined in the Proposal 
and Percentage Completion 
of the Research

Table 1: SAPL Research Project Schedule

Table 2: Completion Percentage of SAPL Research Project Tasks over the 1st through 10th Quarters

| Structural Design Methodology for Spray Applied Pipe Liners in Gravity Storm Water Conveyance Conduits |
| --- |
| Task Number | Task Description | Percentage Completed by the end of: |
|  |  | 1st - 8th Quarters | 9th Quarter | 10th Quarter |
|  |  | Dec 2017 through Dec 2019 | Apr 2018 through Jun 2018 | Jul 2018 through Sep 2018 |
| 1 | Survey of US DOT’s and Canadian Agencies | 100% | 100% | 100% |
| 2 | Literature Search/Participation Material Vendors | 100% | 100% | 100% |
| 3 | Additional Reinforcement | 100% | 100% | 100% |
| 4 | Evaluation if Corrugations Needed to be Completely Filled by the Spray Applied Liner as Part of the Structural Design | 100% | 100% | 100% |
| 5 | Life Cycle Cost Analysis | 90% | 100% | 100% |
| 6 | Review the Cured in Place (CIPP) Design Equations | 100% | 100% | 100% |
| 7 | Field Data Collection and Assistance from DOT Partners | 100% | 100% | 100% |
| 8 | Develop a Recommended Structural Design Equations | 60% | 70% | 80% |
| 9 | Develop Performance Construction Specification | 60% | 80% | 100% |
| 10 | Computational Modeling | 70% | 80% | 90% |
| 11 | Lab Testing | 70% | 80% | 90% |
| 12 | QA/QC | 67% | 78% | 89% |

*Percentages are changed based on the budget and time extension.

# Comparative Status of Actual Versus 
Estimated Expenditures

Table 3: The 8th, 9th and 10th Quarterly Progress Work of SAPL Research Project

| Structural Design Methodology for Spray Applied Pipe Liners in Gravity Storm Water Conveyance Conduits |
| --- |
| Task Number | Task Description | Total Duration (Months) | Duration Completed (Months) | Budgeted Amount ($) | Percentage of Total Budget (%) | Percentage of Completion Based on Schedule (%) | Percentage Completed These Three Quarters (%) | Actual Amount Completed this Quarter ($) |
| 1 | Survey of US DOT’s and Canadian Agencies | 7 | 7 | $25,751 | 5.09 | 100 | 0 | 0 |
| 2 | Literature Search/Participation Material Vendors | 7 | 7 | $21,875 | 4.32 | 100 | 0 | 0 |
| 3 | Additional Reinforcement | 3 | 3 | $2,100 | 0.41 | 100 | 0 | 0 |
| 4 | Evaluation if Corrugations Needed to be Completely Filled by the Spray Applied Liner as Part of the Structural Design | 4 | 4 | $3,900 | 0.77 | 100 | 0 | 0 |
| 5 | Life Cycle Cost Analysis | 12 | 12 | $29,123 | 5.75 | 100 | 10 | $2,912.3 |
| 6 | Review the Cured in Place (CIPP) Design Equations | 5 | 6 | $13,751 | 2.72 | 100 | 0 | 0 |
| 7 | Field Data Collection and Assistance from DOT Partners | 5 | 5 | $71,704 | 14.17 | 100 | 0 | 0 |
| 8 | Develop a Recommended Structural Design Equations | 21 | 11 | $34,081 | 6.73 | 52 | 10 | $21,658.92 |
| 9 | Develop Performance Construction Specification | 22 | 12 | $27,392 | 5.41 | 55 | 14 | $13,670.92 |
| 10 | Computational Modeling | 32 | 21 | $60,013.44 | 11.86 | 90 | 24 | $8,527.49 |
| 11 | Lab Testing | 32 | 21 | $115,137.94 | 22.75 | 90 | 24 | $25,993.74 |
| 12 | QA/QC | 36 | 21 | $13,000 | 2.57 | 89 | 30 | $1,700.00 |
| 13 | Draft Final Report and Fact Sheet | 7 | Not Started | $88,270 | 17.44 | 0 | 0 | 0 |
| 14 | Final Report and Presentation | 3 | Not Started |  |  |  |  |  |
| Total | $506,098.38** | 100 | - | - | $74,463.37 |

* Percentages are changed based on the budget and time extensions.

** The total budget does not reflect the indirect cost of additional budget.

Table 4: Expenditures Summery of SAPL Research Project (October 2019 - July 2020)

| Structural Design Methodology for Spray Applied Pipe Liners in Gravity Storm Water Conveyance Conduits |
| --- |
| Description | Sum Amount |
| Salaries and Benefits |
| Students Salaries and Benefits |
| Faculty Salaries will be Paid During Summer Months |
| Subtotal | $27,167.99 |
| Partner Companies |
| American Structurepoint, Inc. | $5,541.83 |
| Rehabilitation Resource Solutions | $18,888.00 |
| LEO Consulting | $12,600.00 |
| Subtotal | $37,029.83 |
| Direct Costs |
| Hardware and Materials |
| Subtotal | $2,818.70 |
| Other Indirect Costs |
| F&A |
| Fringe Benefits |
| Subtotal | $7,446.84 |
| Total | $74,463.36 |

# Brief Description of the Activities Accomplished by 
Each Member of the Research Team as 
Listed in the Project Budget

## Principal Investigator: Dr. Mohammad Najafi

Task 5: Construction and Environmental Cost Analysis

- Completed and submitted the draft final report.

Task 11: Laboratory Testing

Research Managers: 	Zahra Kohankar Kouchesfehani, Ph.D. Candidate

Amin Darabnoush Tehrani, Ph.D. Candidate

Soil Box Test Setup

- cementitious SAPL material from Standard Cement for

- Completed soil box test of polymeric SAPL material from Sprayroq for invert-cut circular CMPs.

  - SAPL thicknesses: 0.25 in., 0.5 in. and 1.0 in.

  - Submitted results to Ohio DOT through the monthly meetings.

- Completed soil box test of polymeric SAPL material from Sprayroq for invert-cut arch CMPs

  - SAPL thicknesses: 0.25 in., 0.5 in. and 1.0 in.

  - Submitted results to Ohio DOT through the monthly meetings.

- Completed soil box test of cementitious SAPL material from Standard Cement for invert-cut arch CMPs.

  - SAPL thicknesses: 1.0 in., 2.0 in. and 3.0 in.

Participation in the Meetings during Conferences, Internal Meetings, Progress Meetings

- Attended nine monthly progress meetings with DOTs.

- Held internal meetings with CUIRE team and research partners (Dr. Xinbao Yu, Dr. Firat Sever, Mr. Ed Kampbell and Mr. Lyn Osborn).

- Submitted four journal papers to Canadian Journal of Civil Engineering and Transportation Geotechnics Journal.

- Submitted two abstracts to No-Dig Show Conference 2021.

## Co-Principal Investigator: Dr. Xinbao Yu

The following are the tasks performed this quarter:

Task 10: Computational Modeling

- Completed the FEM modeling of invert-cut bare circular and arch CMPs.

- Completed the FEM modeling of polymeric SAPL for invert-cut circular and arch CMPs.

## Subcontractor: Mr. Ed Kampbell
Rehabilitation Resource Solutions, LLC

Accomplishments in the Quarter that ended on June 30, 2020:

Task 6: Review the Cured-in-Place Pipe (CIPP) Design Equations

- Completed a final write up of Task 6 – CIPP Design acting on the comments received from the DOTs

Task 8: Develop Structural Design Equations

- Completed the writing of Task 8 - Design Equations.

- Prepared recommended design equations for the polymeric materials per the existing methodology in the AASHTO LRFD Design Specifications; modified as appropriate for the trenchless installation method.

- Reviewed and prepared a set of design equations for the cementitious liners. Because there was no soil cell information available from UTA, I cited examples of other testing that gave credence to the proposed design method.

Subcontractor: Dr. Firat Sever
American Structurepoint, Inc. (ASI)

- American Structurepoint’s progress in this period is included in Lynn Osborn’s report as they work jointly on the performance specification development.

- American Structurepoint contract with UTA is terminated on February 28, 2020.

Subcontractor: Mr. Lynn Osborn
LEO Consulting, LLC

For work completed April 1 through June 30, 2020 (Q2):

SUMMARY OF PROGRESS FOR QUARTER:

Task 9: Prepare Performance Construction Specifications

- Completed the working draft of the cementitious specification and transmitted the master file to UTA.

- Completed a checklist of items left to be answered by the SAPL study that will lead to modifications of the cementitious specification working draft.

- Completed the working draft of the polymer specification and transmitted the master file to UTA.

- Completed a checklist of items left to be answered by the SAPL study that will lead to modifications of the polymer specification working draft.

Task 12. QA/QC

As QA/QC Reviewer, much of my work depends upon the work and progress of other team members and items that require quality checks.

- Reviewed and modified the cementitious specification as a result of DOT review comments.

- Reviewed and modified the polymer specification as a result of DOT review comments.

- Reviewed the Task 8 (Design) document.

- Reviewed the Task 4 Document - Fill Corrugation Valleys or Follow Corrugations

# Proposed Work for New Quarter

Table 5: SAPL Research Project Tasks for 11th Quarter (July 1 through September 30, 2020)

| Structural Design Methodology for Spray Applied Pipe Liners in Gravity Storm Water Conveyance Conduits |
| --- |
| Task Number | Responsibility | Task Description | Percentage of Work to be Completed by the end of 11th Quarter |
|  |  |  | July 1st through September 30th |
|  |  |  | July | August | September |
| 8 | Mr. Ed Kampbell Dr. Firat Sever | Develop a Recommended Structural Design Equations | To be Completed |
| 9 | Mr. Lyn Osborn | Develop Performance Construction Specification | To be Completed |
| 10 | Dr. Xinabo Yu | Computational Modeling | To be Completed |
| 11 | Dr. Mo Najafi | Lab Testing | To be Completed |
| 12 | Mr. Lynn Osborn | QA/QC | To be Continued |

## Principal Investigator: Dr. Mohammad Najafi

Task 11: Soil Box Testing

Research Managers:	Zahra Kohankar Kouchesfehani, Ph.D. Candidate

Amin Darabnoush Tehrani, Ph.D. Candidate

- To complete soil box tests of cementitious SAPL material from Standard Cement for circular CMPs.

- To perform data analysis on the results of soil box tests of cementitious SAPL for circular and arch CMPs.

- To prepare the draft reports.

- To prepare journal papers out of the results of soil box tests of cementitious SAPL for circular and arch CMPs.

## Co-Principal Investigator: Dr. Xinbao Yu

Planned Task for the Next Quarter

Following are the tasks planned for the coming quarter:

Task 10: Computational Modeling

- To prepare the final report of the FEM work.

## Subcontractor: Mr. Ed Kampbell
Rehabilitation Resource Solutions, LLC

Task 8: Develop Structural Design Equations

- Updating of Task 8 report once the testing is completed by UTA and comments have been received from the DOT’s.

Subcontractor: Dr. Firat Sever
American Structurepoint, Inc. (ASI)

Task 8: Develop Structural Design Equations

- Updating of Task 8 report with Mr. Kampbell.

Subcontractor: Mr. Lynn Osborn
LEO Consulting, LLC

Task 12. QA/QC.

QA/QC reviews will continue on design and development planning, inputs, control and outputs. This will include general project oversight as required.

# Implementation (if any):

N/A

# Problems & Recommended Solutions (if applicable):

N/A

# Equipment Purchased (if any):

N/A

Contacts and Meetings

## Progress Meeting

Table 6: SAPL Progress Meeting during the 8th, 9th and 10th Quarters

October 1, 2019 through June 30, 2020

| No. | Progress Meeting Agenda | Date |
| --- | --- | --- |
| 21 | Schedule Update Task 5: Life Cycle Cost Analysis Task 11: Soil Box Testing Task 10: Finite Element Modeling Task 9: Develop Performance Construction Specifications | October 9, 2019 |
| 22 | Schedule Update Task 11: Soil Box Testing Phase Two: Invert-cut Circular CMP with Spraywall Liner Task 10: Finite Element Modeling Comparison of Experiment with Numerical Analysis of Invert-cut Circular CMP | November 13, 2019 |
| 23 | Schedule Update Task 11: Soil Box Testing Polymeric SAPL: Invert-cut Circular CMP with Spraywall Liner | December 11, 2019 |
| 24 | Schedule Update Task 10: Finite Element Modeling | January 08, 2020 |
| 25 | Schedule Update Task 11: Soil Box Update 3rd Soil Box Test Setup Preparation: Polymeric SAPL – Arch CMP Task 5: Life Cycle Cost Analysis (Draft Report) Task 9: Performance Construction Specification (Status Update) Task 8: Develop a Recommended Structural Design Equations Allocation of 10 Hours for Mr. Kampbell | February 12, 2020 |
| 26 | Schedule Update Task 11: Soil Box Update Completion of 3rd Soil Box Test Setup: Polymeric SAPL - Arch CMP Preparation of 4th Soil Box Test Setup: Cementitious SAPL - Arch CMP Cementitious SAPL Vendor | March 11, 2020 |
| 27 | Schedule Update Additional Time and Budget (due to COVID-19) Task 9: Performance Construction Specification (Presented by Mr. Osborn) Draft of Polymeric SAPL Specifications are ready to be Reviewed by DOTs. Cementitious SAPL Thickness Measurement – Research Team Recommendation is to Fill the Corrugations. Task 8: Design Equations Internal Meeting with Mr. Kampbell, Mr. Osborn and Dr. Sever April/May Timeframe Design Equations will be Completed Refine in June/July Based on Soil Box Testing Task 11: Soil Box Update 4th Soil Box Test Setup is Ready for Cementitious SAPL – Invert-cut Arch CMP Cementitious SAPL Vendor? Can we have a Second Vendor? CentriPipe? 7-Day Curing Time Material Property Results – Correct Young Modulus? Structurepoint Budget Reallocation Additional $10,000 Allocated to Rehabilitation Resource Solutions Task 10: Finite Element Modeling | April 08, 2020 |
| 28 | 1. Schedule Update 2. Task 11: Soil Box Update 4th Soil Box Test Setup is Ready for Cementitious SAPL – Invert-cut Arch Soil Box Testing Cementitious SAPL Vendor? CMP Strong Seal or CentriPipe? How about Milliken (ClOCK SPRING/GeoTree), Quadex, A.W. Cook, Standard Cement Schedule Delay SAPL Field Inspection and Strong Company Project in Delaware Budget Reallocation | May 13, 2020 |
| 29 | Schedule Update Task 11: Soil Box Update – Standard Cement Installation on Saturday, June 6, 2020 Task 10: Finite Element Modeling Update | June 10, 2020 |