**TRANSPORTATION POOLED FUND PROGRAM**

**QUARTERLY PROGRESS REPORT**

Lead Agency (FHWA or State DOT): \_\_\_\_\_Minnesota Department of Transportation\_\_\_\_\_\_\_\_

**INSTRUCTIONS:**

*Project Managers and/or research project investigators should complete a quarterly progress report for each calendar quarter during which the projects are active. Please provide a project schedule status of the research activities tied to each task that is defined in the proposal; a percentage completion of each task; a concise discussion (2 or 3 sentences) of the current status, including accomplishments and problems encountered, if any. List all tasks, even if no work was done during this period.*

|  |  |
| --- | --- |
| **Transportation Pooled Fund Program Project #***(i.e, SPR-2(XXX), SPR-3(XXX) or TPF-5(XXX)*TPF 153 | **Transportation Pooled Fund Program - Report Period:**□Quarter 1 (January 1 – March 31)Quarter 2 (April 1 – June 30)Quarter 3 (July 1 – September 30)XQuarter 4 (October 1 – December 31) |
| **Project Title:****Optimal Timing of Preventive Maintenance for Addressing Environmental Aging in HMA Pavements (MnROAD Study)** |
| **Name of Project Manager(s):****Thomas J. Wood** | **Phone Number:****651/366/5573** | **E-Mail**thomas.wood@state.mn.us |
| **Lead Agency Project ID:****95099** | **Other Project ID (i.e., contract #):****95099** | **Project Start Date:**March 31, 2010 |
| **Original Project End Date:****11/30/2013** | **Current Project End Date:****11/30/2013** | **Number of Extensions:****None** |

Project schedule status:

X On schedule □ On revised schedule □ Ahead of schedule □ Behind schedule

Overall Project Statistics:

|  |  |  |
| --- | --- | --- |
|  **Total Project Budget** |  **Total Cost to Date for Project** |  **Percentage of Work**  **Completed to Date** |
| $452205.00 | $97743.16 | 27% |

***Quarterly*** Project Statistics:

|  |  |  |
| --- | --- | --- |
|  **Total Project Expenses**  **and Percentage This Quarter** |  **Total Amount of Funds**  **Expended This Quarter** |  **Total Percentage of**  **Time Used to Date** |
| 0% | $0.00 as of 10/23/12 |  |

|  |
| --- |
| **Project Description**:The goal of this study is to determine the proper timing of preventive maintenance treatments in order to optimize life cycle costs and pavement performance. Environmental aging of the asphalt binder in the underlying pavement is not well understood, and this project will seek to better understand the aging mechanism and how it can be reduced through pavement preservation. |

|  |
| --- |
| **Progress this Quarter (includes meetings, work plan status, contract status, significant progress, etc.):**Testing is started on cores taken from MnRoad summer of 2012. Web meeting was held early December betweeninvestigators and MnDOT personnel to discuss early finding and make sure project is on track.  |
| **Anticipated work next quarter**:Hope to have a web meeting with all the members of the pooled fund to discuss status.  |

|  |
| --- |
| **Significant Results:****The project plan has modified based on input from member states. Based on this input the Asphalt Institute (AI) is testing cores taken from test section last year and will be testing core take this year to determine the change in aging. Hopefully AI will have significant finding to report either in this quarter or early the next quarter.**  |
| **Circumstance affecting project or budget. (Please describe any challenges encountered or anticipated that** **might affect the completion of the project within the time, scope and fiscal constraints set forth in the** **agreement, along with recommended solutions to those problems).****None as of today.** |

|  |
| --- |
| **Potential Implementation:** Based on this research the States should be able to better plan when to do their pavement preventive maintenance treatment. This will allow them budget and plan to receive maximum benefit.  |