Pooled Fund Quarterly Report

For July-September 2020

Submitted by: Daniel E. Jenkins, PE

FHWA and its contract partners (Macrosys and Oak Ridge National Laboratory (ORNL)) continue to provide technical support to the 2017 NHTS pooled fund participants. In September 2020, we began beta testing the latest enhancements to the data analytics tools ORNL is developing for the pooled fund agencies. These tools should be finished in the next quarter.